## projects
project_code | project_name | studio
13042 | SEA BREEZE VERANDAS BAUILIDING D REDESIGN | STUDIO 1
13056 | THE VERANDA (PHASE2 BUILDING A2 + B2) | STUDIO 3
13058 | BPI CEBU CORPORATE CENTER | STUDIO 3
13089 | NORTHGATE ALABANG BPO | STUDIO 3
13113 | ALVEO DESIGN STANDARDS AND GUIDELINES | STUDIO 3
13121 | HSS VERVE RESIDENCES TOWER 2 | STUDIO 3
14048 | LEGASPI MIXED-USED DEVELOPMENT | STUDIO 2
14098 | CENTRIS WALK EXTENSION - RETAIL STRIP | STUDIO 1
14099 | WIDUS CLARK TOWER 3 | STUDIO 1
14101 | ETON CITY MASTERPLANNING | STUDIO 1
14112 | THE BAY MALL | STUDIO 3
15005 | HERMES BOUTIQUE GRRENBELT 3 | STUDIO 2
15009 | MAXIMS HOTEL LOCAL COUNTERPART ID | undefined
15019 | WIDUS MIXED-USE DEVELOPMENT | STUDIO 1
15023 | ETON CENTRIS MASTERPLANNING | STUDIO 1
15041 | HMRID WAREHOUSE | STUDIO 3
15058 | GRIND GASTROPUB RESTAURANT | STUDIO 2
15070 | VERTIS NORTH PARCEL O SITE PLANNING | STUDIO 2
15086 | CITI TOWER LEVEL 31 PILOT FITOUT | STUDIO 2
15094 | SHERATON BACK OFFICE | STUDIO 2
15106 | SUNTECH IPARK BPO BUILDING 2 | STUDIO 3
15130 | IMMACULATE CONCEPTION ACADEMY | STUDIO 1
15166 | SUPERSTAR MASTERPLAN | STUDIO 1
15173 | KIDZANIA BOH EXTENSION OFFICE | STUDIO 2
16025 | CIVIL REGISTRY - IT PROJECT PHASE 2 | STUDIO 6
16030 | CITI PLAZA ADDTL ID SERVICES | STUDIO 2
16031 | CITI PLAZA EGD | STUDIO 2
16105 | ETON CITY STAND ALONE RETAILS | STUDIO 1
16137 | GENSLER CITI PLAZA 16F | STUDIO 2
17022 | ATLAS OFFICE ID ENHANCEMENT | STUDIO 2
17047 | LA FILIPINA BGC-ID | STUDIO 3
17122 | CGC MASTERPLAN | STUDIO 4
17126 | AG NEW WORLD ANNEX BUILDING | STUDIO 1
17150 | MANDANI BAY BOARDWALK | STUDIO 5
17153 | GAMING CAFE OUTLET | STUDIO 4
18008 | GUADANOVILLE MASTERPLANNING | undefined
18068 | MAKINO OFFICE ID | STUDIO 2
18148 | L'AVENIR CLARK | STUDIO 1
18165 | NET PARK AURORA CODE REVIEW | STUDIO 2
18171 | *LUISITA-BTS OFFICE TEST-FIT | STUDIO 1
18213 | *ACCI RENOVATION PROJECT | STUDIO 2
18216 | MANULIFE 6789 RENOVATION | STUDIO 2
18217 | ROBINSONS LUISITA VILLAS TEST FIT | STUDIO 1
18229 | DLI BPO BULACAN | STUDIO 3
18235 | DINSMORE RENDERING | STUDIO 2
18262 | *ULI LIBRARY ID | STUDIO 2
19001 | ISOC CLARK SCALE MODEL | STUDIO 4
19040 | UDENNA 10TH AND 11TH FLOOR DESIGN BUILD | STUDIO 2
19059 | PROJECT GARNET - BIM | STUDIO 1
19087 | PROJECT CORAL RENDERING | STUDIO 2
19111 | *ROD HENSON RESIDENCE | STUDIO 2
19128 | JUNCTION RENDERING | STUDIO 2
19163 | ISOC BPO | STUDIO 4
19174 | DLI CLARK DORMITEL | STUDIO 3
19186 | PARKLINKS RENDERING | STUDIO 2
19226 | THE JUNCTION PLACE RENDERING | STUDIO 2
19246 | ISOC CLARK CASINO | undefined
19252 | P&G NET PARK RENOVATION | STUDIO 2
19265 | PROJECT HOLLOW | STUDIO 6
20004 | PROJECT BARRIO | STUDIO 6
20006 | NOVELLINO MP | STUDIO 6
20007 | FERRARI SHOWROOM | STUDIO 4
20016 | HABI BEACH RESORT | STUDIO 3
20018 | Banyan Tree Manila -BP SET | STUDIO 1
20027 | DGT- PREMIER OFFICE | STUDIO 1
20046 | PHILEXCEL BPO COMPLEX PHASE 1 | STUDIO 4
20049 | DLI CLARK BPO PH1 | STUDIO 3
20050 | DLI CLARK HOTEL PH1 | STUDIO 3
20051 | NESTLE ID RENDERING | STUDIO 2
20055 | BACLARAN CHURCH MASTERPLAN | undefined
20057 | AEON GRACE PROPERTY MIXED USE | STUDIO 6
20058 | AEON CHINA TOWN MIXED USE | STUDIO 6
20063 | DATEM ETON BPO PHASES 1 & 2 | STUDIO 5
20064 | DATEM ETON RETAIL STRIP | STUDIO 5
20069 | GARDEN TOWERS - TOWER 2 SUPPLEMENTARY SERVICES | undefined
1309502 | ONE & TWO PASEO VARIATION ORDER NO. 02 | STUDIO 4
1310203 | DOWELL TOWER EXTENSION OF CONSTRUCTION VO.03 | STUDIO 3
1405102 | WEST END MAKATI VARIATION ORDER NO. 02 | STUDIO 3
1504101 | HMRID WAREHOUSE - JRDC | STUDIO 3
1506802 | CALLISTO TOWER 1 VARIATION ORDER NO.2 | STUDIO 4
1506803 | CALLISTO TOWER 2 VARIATION ORDER NO.3 | STUDIO 4
1506804 | CALIISTO TOWER 1 VARIATION ORDER NO.4 | STUDIO 4
1607302 | MANDANI BAY QUAY VO NO.2 | STUDIO 5
1607304 | MANDANI BAY QUAY VO NO.4 | STUDIO 5
1702901 | DAVAO CENTRRALLE VO NO. 01 | STUDIO 3
1704401 | AUREO APARTELLE BUILDING VARIATION ORDER NO.01 | STUDIO 3
1705602 | UDENNA OFFICE INTERIORS VARIATION ORDER NO.02 | STUDIO 2
1706801 | MGI DISTRIBUTION CENTER VARIATION ORDER NO. 1 | STUDIO 4
1712201 | CGC MASTERPLAN REALIGNMENT | STUDIO 4
1712401 | SLMC DAVAO VARIATION ORDER NO. 01 | STUDIO 2
1712402 | SLMC DAVAO VARIATION ORDER NO. 02 | STUDIO 2
1712405 | SLMC DAVAO VARIATION ORDER NO. 05 | STUDIO 2
1712406 | SLMC DAVAO VARIATION ORDER NO. 06 | STUDIO 2
1712407 | SLMC DAVAO VARIATION ORDER NO. 07 | STUDIO 2
1713101 | EMERALD VO No. 01 | STUDIO 4
1720101 | HABI BEACH RESORT VARIATION ORDER NO.01 | STUDIO 3
1722302 | PATIO SUITES TOWER 2 VARIATION ORDER 2 | STUDIO 3
1800903 | WEST AEROPARK PHASE 2 CONSTRUCTION SERVICES V.O NO.03 | STUDIO 4
1800904 | WAP 2ND EXTENSION OF CONSTRUCTION | STUDIO 4
1806902 | GOOGLE VERTIS NORTH VARIATION ORDER NO.02 | STUDIO 2
1813601 | MANULIFE VARIATION ORDER | STUDIO 2
1813602 | MANULIFE EGD | STUDIO 2
1912501 | WHITE & CASE MANILA ATG - VARIATION ORDER NO.01 | STUDIO 2
1922701 | CLI ABACA HOTEL-VARIATION ORDER NO.01 | STUDIO 3
1924201 | MLA RESIDENTIAL SIERRA MADRE -VARIATION ORDER NO.01 | STUDIO 2
15057G | SBV BLDG E - BIM | STUDIO 1
16010 | EDI SUPPORT FACILITIES | STUDIO 1
17131H01 | THE EMERALD HOTEL RESORT & CASINO-SITE ARCHITECT EXTENSION OF CONTRACT | STUDIO 4
17145 | ABS-CBN Q.C. MASTERPLANNING | STUDIO 2
17185 | ROBINSON'S LUISITA MP | STUDIO 1
17212 | LEGAZPI MIXED USE INTERIM PODIUM PARKING | STUDIO 2
18016J | UST GENSAN CAMPUS -PHASE1B | STUDIO 1
18051 | CORON MASTERPLANNING | STUDIO 1
18152 | CARMELTOWN MASTER PLAN | STUDIO 1
18163 | CLARK MONACO PLAZA MP (ISOC CLARK INTEGRATED HOTEL AND CASINO) | STUDIO 4
19088 | ISOC IBIS HOTEL | STUDIO 4
19144 | PHILEXCEL RETAIL REDEVELOPMENT | STUDIO 4
19166 | KZ SODA FOUNTAIN - ID | STUDIO 2
19198J | PROJECT ESPADA ID | STUDIO 2
19265J | PROJECT HOLLOW ID | STUDIO 7
20096 | DDTKI SUNNY COAST | STUDIO 3
18138 | THE MAPLE CENTER (CHALCEDONY PLACE) | STUDIO 3
18188 | CCPI OFFICE FIT-OUT | STUDIO 3
14119 | LBL BUILDING RENOVATION | STUDIO 3
16028 | PAZ MADRIGAL | STUDIO 3
17201 | LIO LONG STAY HOTEL | STUDIO 3
16035 | WEST END SQUARE: ID EGD LANDSCAPE SPECIAL LIGHTING FAÇADE | STUDIO 3
18103 | DATA LAND OFFICE BUILDING (DDT SKY TOWER) | STUDIO 3
17188 | *YU RESIDENCE | STUDIO 3
15169 | LATITUDE CORPORATE CENTER | STUDIO 3
13104 | STILES ENTERPRISE - EXTENSION OF CONSTRUCTION | STUDIO 3
15077 | THE GENTRY | STUDIO 3
13111 | PARK TRIANGLE CORP PLAZA NORTH | STUDIO 3
14066 | PARK TRIANGLE CORP PLAZA SOUTH | STUDIO 3
16094 | PROJECT THEODORE DATA CENTER (GLOBE ROOSEVELT) | STUDIO 3
18034 | AUREO PHASE 4 | STUDIO 3
16107 | 38 PARK AVENUE | STUDIO 3
17115 | ONE VERTIS PLAZA | STUDIO 1
18059 | SOUTHKEY HUB 2 (NORTHGATE ALABANG BPO 2) | STUDIO 3
14055 | HIGH PARK TOWER 2 | STUDIO 3
15069 | OREAN PLACE | STUDIO 3
16085 | 110 BENAVIDEZ CITADINES ID | STUDIO 3
14110 | KEYLAND BENAVIDEZ LEGASPI | STUDIO 3
16039J | ACI GATEWAY MALL 2 - CD TO CS | STUDIO 3
19281 | *GRAND WESTSIDE HOTEL - LANDSCAPE | STUDIO 3
19282 | *BAYSHORE RESIDENTIAL HOTEL - LANDSCAPE | STUDIO 3
17029 | DAVAO CENTRAL HOTEL | STUDIO 3
17223 | PATIO SUITES TOWER 2 LITE | STUDIO 3
18123 | PROJECT RUBY - DLR CIVIC & RETAIL | STUDIO 3
18060 | CITADINES/LYF SALCEDO (CITADINES SALCEDO) / CITADINES LEVISTE | STUDIO 3
19080 | VIBE TOWER 3 | STUDIO 3
19227 | CLI ABACA HOTEL | STUDIO 3
19180 | NORTHGATE B45L1 | STUDIO 3
18260 | PARKFORD SUITES | STUDIO 3
19065 | BAGUIO OFFICE BUILDING | STUDIO 3
19061 | 38 PARK PHASE 2 & 3 | STUDIO 3
19023 | DDTKI PARK MCKINLEY WEST | STUDIO 3
19068 | PROJECT GENESIS (ALP-HYUNDAI) | STUDIO 3
19099 | PROJECT AZUELA | STUDIO 3
14051 | WEST END SQUARE | STUDIO 3
13004 | MANGO TREE RESIDENCES | STUDIO 3
18232 | PROJECT RUBY - BPIDLR REDEVT. | STUDIO 3
18108 | OREAN TOWER 2 | STUDIO 3
19109 | Geo Estate Tower Roxas Blvd | STUDIO 3
1200406 | GARDEN TOWER T1: VARIATION ORDER - EXTENDED CONSTRUCTION STAGE | STUDIO 4
13029 | GARDEN TOWERS TOWER 2 | STUDIO 4
13063 | HIGH PARK TOWER 1 | STUDIO 3
14012 | GRAND TOWER CEBU | STUDIO 2
1401206 | GRAND LAND MIXED USE DEVT - EXTENSION OF CONSTRUCTION SERVICES | STUDIO 2
14032 | THE PADDINGTON PLACE | STUDIO 1
1405101 | WEST END SQUARE VARIATION ORDER NO. 01 | STUDIO 3
14087 | SOUTHKEY PLACE | STUDIO 3
14093 | UDENNA TOWER | STUDIO 3
15110 | HORIZON SOUND STAGE PHASE 1 | STUDIO 2
\N | AYALA NORTH EXCHANGE CITYGATE RESIDENTIAL COMMERCIAL RETAIL (AYALA NORTH EXCHANGE) FOR OFFICE/BPO- | undefined
\N | AYALA NORTH EXCHANGE CITYGATE RESIDENTIAL COMMERCIAL RETAIL (AYALA NORTH EXCHANGE)-FOR RETAIL | undefined
13107 | AYALA NORTH EXCHANGE | STUDIO 3
15118 | PROJECT SUPERSTAR | STUDIO 1
15040 | CAGAYAN SHRIMP PROCESSING PLANT | STUDIO 1
15146 | ETON CITY COMMERCIAL DEVELOPMENT | STUDIO 1
16002 | BLUE WATER MARIBAGO EXPANSION | STUDIO 5
16016 | SANTOR WAREHOUSE PHASE 2 | STUDIO 1
16017 | PROJECT CHEWEE | STUDIO 1
16019 | PARK TRIANGLE RESIDENCES | STUDIO 1
16028J | PAZ MADRIGAL PLAZA - DDTKI (DD CD CS PHASE ) | STUDIO 3
16037 | KASA LUNTIAN PHASE 2 | STUDIO 6
16044 | SUPERSTAR HOTEL | STUDIO 1
16045 | SUPERSTAR BPO | STUDIO 1
16052 | PHILAM VALERO COMMON AREAS RENOVATION | STUDIO 2
1605402 | SLMC QC VARIATION ORDER NO. 02 | STUDIO 5
16060 | WIDUS HOTEL CASINO AND HOTEL EXPANSION | STUDIO 1
16070 | PROJECT SEABREEZE PHASE 1 (ROBINSONS DUMAGUETE) | STUDIO 5
16073 | MANDANI BAY BLOCK 1A & 1B | STUDIO 5
1607301 | MANDANI BAY QUAY VO NO.1 | STUDIO 5
1607305 | MANDANI BAY QUAY VO NO.5 | STUDIO 5
16073A | MBQ T1 MARKETING REQUIREMENT | STUDIO 5
16073A1 | MBQ TOWER 2 MARKETING REQUIREMENTS | STUDIO 5
16073A2 | MBQ TOWER 4 MARKETING REQUIREMENTS | STUDIO 5
16077 | PNB MANILA BAY | STUDIO 5
16097 | DRUG REHAB CENTER REV-1 | STUDIO 1
16109 | ALG-CIT | STUDIO 1
16117 | LANDMARK BGC | STUDIO 5
16124 | MI CASA (PROJECT R8-R14) | STUDIO 5
16124E | MI CASA INTERIOR RENDERING | STUDIO 5
16135 | PROJECT AWAKENS | STUDIO 1
16148 | AMIGO TERRACES | STUDIO 2
16150 | ETON CITY SQUARE PHASE 2 | STUDIO 1
17027 | D&L INNOVATION & TECHNOLOGY CENTER | STUDIO 3
17027J | D&L INNOVATION & TECHNOLOGY CENTER -ID | STUDIO 3
17044 | AUREO APARTELLE BUILDING | STUDIO 3
17056 | UDENNA OFFICE INTERIORS | STUDIO 2
17090 | CENTRIS WALK EXTENSION CLUSTER 4 | STUDIO 1
17119 | MMC CITYGATE BRIDGEWAY | STUDIO 3
17124 | SLMC DAVAO | STUDIO 2
17131 | EMERALD INTEGRATED RESORT | STUDIO 4
17134 | CAVDEAL CATICLAN DORMITORY D&B | STUDIO 5
17163 | 3-BEDROOM ACCOMMODATION - SOLAIRE A&A ID | STUDIO 2
17168 | CASINO CEILING ID | STUDIO 2
17195 | ONE LE GRAND TOWER | STUDIO 5
17206 | BPI MSE OFFICE ID | STUDIO 2
17214 | 56 CENTRAL (ARCA SOUTH OFFICE BUILDING) | STUDIO 5
17224 | CEBU COURTYARD MARRIOTT | STUDIO 1
17230 | BACOOR RECLAMATION MASTERPLAN (FRABELLE FISHING CORP) | STUDIO 5
17230J | DEC BACOOR COASTAL RECLAMATION AND DEVELOPMENT PROJECT (DIAMOND EXPORT CORP) | STUDIO 5
18009 | WEST AEROPARK PHASE 2 CONSTRUCTION SERVICES | STUDIO 4
1800902 | WAP2 EXTENSION OF CONSTRUCTION | STUDIO 4
18015 | NEW CLARK CITY STADIUM | STUDIO 6
18035 | THE EMERALD PROJECT BOH ID | STUDIO 4
18050 | NEW CLARK CITY AQUATIC CENTER | STUDIO 6
18053 | MACTAN SEAGROVE HOTEL | STUDIO 5
18075 | PROJECT KAIZEN | STUDIO 1
18077 | SDC TORDESILLAS OFFICE | STUDIO 5
18078 | OREAN PLACE TOWER 2 | STUDIO 3
18080 | DAIICHI CORPORATE HQ INTERIORS | STUDIO 5
18091 | JADE PACIFIC SMH | STUDIO 1
18104 | DFNN OFFICE ID UDENNA SITE CLARK SITE | STUDIO 2
18124 | BLUEWATER HOTEL EXPANSION | STUDIO 5
18134 | SOLAIRE CLOAKROOM | STUDIO 2
18136 | MANULIFE OFFICE ID | STUDIO 2
18142 | PROJECT ISABEL - BPI HQ (PROJECT RUBY - DLR 1) | STUDIO 6
18149 | PULLMAN | STUDIO 4
18151 | PROJECT GARNET | STUDIO 1
18160 | SOLAIRE PRESIDENTIAL & CHAIRMAN'S SUITE | STUDIO 2
18170 | CITY OF DREAMS MANILA RENOVATION | STUDIO 2
18172 | NEW SENATE BUILDING (PROJECT VIZARD) | STUDIO 5
1817203 | NEW SENATE BUILDING - VO NO. 03 | STUDIO 5
18182 | ISOC SUCAT RESIDENTIAL | STUDIO 4
18182B | ISOC RESIDENCES SHOWROOM | STUDIO 4
18183 | ISOC ARNAIZ OFFICE | STUDIO 4
18192 | TGT REDEVELOPMENT | STUDIO 2
18204 | KEYLAND LEVADO | STUDIO 2
18223 | *TAJARA PANGLAO | STUDIO 5
18236 | PHILEXCEL ANNEX WAREHOUSE DEVELOPMENT | STUDIO 1
18249 | 18 AVENUE DE TROIMPHE | STUDIO 5
18256 | SOLAIRE L3 VIP WALL | STUDIO 2
18261 | THE PLAZA (FLI SSR TOWER 7) | STUDIO 5
18264 | GOOGLE E-BLOC DUE DILIGENCE | STUDIO 2
18265 | LUISITA BUILD TO SUIT OFFICE | STUDIO 1
18283 | *LAMASUTA RESIDENCE | STUDIO 2
18284 | *SANTOS RESIDENCE | STUDIO 2
19021 | DDTKI CLARK MASTERPLAN | STUDIO 3
19027 | TAGAYTAY RESIDENTIAL RESORT | STUDIO 4
19030 | SOLAIRE ARTWORK & DRAPERY | STUDIO 2
19032 | VERMOSA SPORTS HUB MASTERPLAN | STUDIO 6
19035 | RP ANTIPOLO MASTERPLAN | STUDIO 1
19052 | MANDANI BAY MASTERPLANNING | STUDIO 5
19058 | SOLAIRE BAY LEVEL 2 | STUDIO 2
19075 | CAGAYAN SHRIMP PROCESSING PLANT - ID | STUDIO 1
19077 | W OFFICE BGC | STUDIO 3
19085 | PROJECT AWAKENS BIM | STUDIO 1
19081 | SOLAIRE VILLA 1 REFURBISHMENT | STUDIO 2
19084 | QUASHA LAW OFFICE -ID | STUDIO 2
19101 | *WACK WACK GOLF LOUNGE | STUDIO 2
19112 | ARUP OFFICE FIT-OUT | STUDIO 2
16073A3 | MANDANI BAY MARKETING PLANS TOWER 3 | STUDIO 5
19176 | 917V INCUBATOR SPACE | STUDIO 2
19178 | CEDARSIDE HOTEL CITADINES CONNECT | STUDIO 5
19188 | TAGAYTAY RESIDENTIAL RESORT - DD TO CS - A&E | STUDIO 4
19190 | G-E ROXAS BLVD RESIDENTIAL BLDG_(previously 18187) | STUDIO 3
19198 | PROJECT ESPADA | STUDIO 5
19199 | UNIOIL OFFICE AND DORMITORY | STUDIO 4
19204 | BGC WESTGATE PARKING | STUDIO 1
19215 | GOOGLE VERTIS NORTH EXPANSION | STUDIO 2
19263 | PHILEXCEL BPO | STUDIO 4
17014 | SOUTHERN STAR | STUDIO 6
1701401 | SOUTHERN STAR- VARIATION ORDER NO.01 | STUDIO 6
18228 | ROBINSON LUISITA RESORT HOTEL | STUDIO 1
19070 | COURTYARD CEBU HOTEL | STUDIO 1
19238 | SOLAIRE WATERSIDE RESTOBAR | STUDIO 2
19253 | *VERGARA RESIDENCE | STUDIO 6
19160 | GRAMANS BPO | STUDIO 1
19177 | BPI DAVAO LANANG | STUDIO 2
19194 | TANAY RESIDENTIAL RESORT | STUDIO 4
19205 | BPI BUENDIA CENTER | STUDIO 2
19221 | BENCH HQ | STUDIO 4
19261 | PROJECT RADA | STUDIO 5
19270 | GRAMANS MIXED-USE MASTERPLAN | STUDIO 1
20002 | MANDANI BAY PHASE 3 | STUDIO 5
19232 | ARQ BEACH RESORT | STUDIO 1
19284 | PROJECT SRP 2 RENDERINGS | STUDIO 5
20001 | NESTLE ROCKWELL | STUDIO 2
20005 | FIRST TAAL | STUDIO 6
19158 | PARK TRIANGLE RETAIL PODIUM EXTERNAL LIGHTING | STUDIO 1
19260 | SAMAL RESIDENTIAL MP CONCEPT | STUDIO 5
20011 | BENCH DORM | STUDIO 4
20013 | P&G NET LIMA | STUDIO 2
20019 | ULTICON HARBOR CITY MP | STUDIO 5
19130 | LANGUIDINGAN AIRPORT | STUDIO 5
19154 | SEAGROVE MASTERPLANNING RENDERINGS | STUDIO 5
1920501 | BPI BUENDIA CENTER V.O NO.01 - COFFEE LOUNGE | STUDIO 7
19283 | (LEAD) SOLVIENTO PHASE 4 MASTERPLAN | STUDIO 1
20017 | CORON SALES PAVILLION | STUDIO 4
20028 | ISOC CLARK NEO MASTERPLAN | STUDIO 4
20029 | MANDALA PARK DEVELOPMENT | STUDIO 4
20033 | CL SALES LOUNGE (CITADINES LEVISTE SHOWROOM) | STUDIO 2
20038 | GARDEN TOWERS SUPPLEMENTARY SERVICES | STUDIO 4
20039 | PARK TERRACES SUPPLEMENTARY SERVICE | STUDIO 4
20048 | CABADBARAN SPORTS COMPLEX MP | STUDIO 1
16073A4 | MANDANI BAY MARKETING PLANS | STUDIO 5
1612408 | MICASA TOWER 2 & 3 REDESIGN | STUDIO 5
1713102 | THE EMERALD PROJECT VARIATION ORDER NO.02 | STUDIO 4
1713103 | THE EMERALD PROJECT VARIATION ORDER NO.03 | STUDIO 4
1812402 | BLUEWATER BOARDWALK | STUDIO 5
19150 | BTS LUISITA 3 | STUDIO 1
19159 | CHEVRON PILOT OFFIICE | STUDIO 2
19195 | BLUEWATER MASTERPLAN | STUDIO 5
19200 | BPI DAVAO ANNEX BLDG | STUDIO 2
20030 | TRANSASIA (OKADA) MASTERPLAN | STUDIO 1
20061 | BPI MSE EXTENSION | STUDIO 2
20072 | HT LAND MANDANI BAY PHASE 3B | STUDIO 5
19057 | NOVOTEL SUITES | STUDIO 5
19069 | NOVOTEL HOTEL | STUDIO 5
19095 | MC HOME DEPOT | STUDIO 5
19179 | URC MASTERPLANNING | STUDIO 4
20010 | CGC FOOD AND WELLNESS HUB | STUDIO 4
20022 | MANDAUE MIXED USE TEST FIT | STUDIO 4
20041 | MANDALUYONG CITY GYMNASIUM | STUDIO 6
20044 | SOLAIRE FOOD COURT RENOVATION | STUDIO 2
20052 | SHANG MAKATI TEST FIT | STUDIO 4
20078 | NEC PAMPANGA MP | STUDIO 6
20079 | BPI NORTH TOWER | STUDIO 6
20080 | BPI SOUTH TOWER | STUDIO 6
20082 | PROJECT AGE | STUDIO 4
19145 | *LLENADO CLINIC | STUDIO 2
20075 | AEON BLEU | STUDIO 5
20115 | MANULIFE LEV 7 RE-MEASUREMENT | STUDIO 2
1507525 | MANDANI BAY SUITES-2ND EXTENSION OF CONSTRUCTION | STUDIO 5
1926101 | PROJECT ELURIA - VARIATION ORDER NO.01 | STUDIO 5
20105 | DGT SE BLOCK RESIDENCES | STUDIO 4
20118 | MBS PODIUM RETAIL MARKETING | STUDIO 5
20119 | MBQ PODIUM RETAIL MARKETING | STUDIO 5
20120 | MBQ PODIUM HLURB | STUDIO 5
20128 | PROJECT GENESIS (BANYAN TREE) | STUDIO 1
20112 | PLANTATION HQ FACILITIES | STUDIO 1
20101 | BPI UPTOWN BGC ID | STUDIO 2
20085 | SYMRISE ID | STUDIO 2
20100 | DRAPER HOUSE INCUBATOR SPACE | STUDIO 2
19205001 | BPI CANTEEN BUENDIA | STUDIO 2
20124 | ISOC MIDLAND RESIDENCES | STUDIO 4
14107Z2 | NORTH BANK TOWER B | STUDIO 4
1302902 | GARDEN TOWER 2 - EXTENSION OF CONSTRCUTION | STUDIO 4
20088 | ISOC N DOMINGO RESIDENTIAL | STUDIO 4
20020 | MANDANI BAY QUAY - SIGNAGES | STUDIO 5
16073G | MANDANI BAY QUAY - BIM | STUDIO 5
18016 | UST GENSAN CAMPUS PHASE 1 | STUDIO 1
\N | 19122 | undefined
15075 | MANDANI BAY SUITES | STUDIO 5
15073 | PATIO SUITES TOWER 1 | STUDIO 4
15068 | CALLISTO TOWER 1 & 2 (TOWER 1) | STUDIO 4
15068/01 | CALLISTO TOWER 2 (FORMERLY CIRCUIT RESIDENTIAL TOWER 4)- USED IN THE SO OF TOWER 2 | STUDIO 4
14107Z1 | FOUNDRY MALL | STUDIO 4
1401801 | ANILAO BEACH RESORT - EXTENSION OF CONSTRUCTION | STUDIO 4
19125 | WHITE & CASE MANILA ATG | STUDIO 2
15057 | SEABREEZE VERANDA E | STUDIO 1
13095 | ONE & TWO PASEO (TOWER 1) | STUDIO 4
13102 | DOWELL TOWER | STUDIO 3
14018 | ANILAO BEACH RESORT | STUDIO 4
14107 | NORTHBANK MIXED USE DEV | STUDIO 4
14112J | THE BAY HOTEL | STUDIO 3
15037 | CITYGATE RETAIL COMMON AREAS (AYALA NORTH EXCHANGE) | STUDIO 3
18069 | GOOGLE VERTIS NORTH ID | STUDIO 2
19242 | ONE SIERRA | STUDIO 2
1506807 | CALLISTO TOWER 1 - EXTENSION OF CONSTRUCTION | STUDIO 4
1607303 | MANDANI BAY QUAY VO NO.3 | STUDIO 5
1806903 | GOOGLE VERTIS NORTH VARIATION ORDER NO.03 | STUDIO 2
20149 | PROJECT HOPE RESIDENTIAL MP | STUDIO 2
\N | Coron Sales Pavilion | undefined
20111 | FB SHELTER IN-PLACE | STUDIO 4
20138 | TRANS-ASIA OFFICE TOWERS | STUDIO 4
19218 | NCC MINT | STUDIO 4
18182A | I-LAND RESIDENCES RENDRED UNIT PLANS | STUDIO 4
20062 | IDESIA MODEL UNITS | STUDIO 2
1712403 | SLMC DAVAO VARIATION ORDER NO. 03 | STUDIO 2
2006201 | IDESIA - VARIATION ORDER NO. 01 | STUDIO 2
IP001 | PROJECT HRIS DEPLOYMENT | undefined
1716301 | SOLAIRE 3 BEDROOM SUITES VARIATION ORDER NO. 01 | STUDIO 2
20161 | CEBU OFFICE BUILDING | STUDIO 2
1410702 | NORTHBANK EXTENSION OF CONSTRUCTION | STUDIO 4
1507524 | MANDANI BAY SUITES - EXTENSION OF CONSTRUCTION | STUDIO 5
1817205 | NEW SENATE BUILDING - B1-B3 VER 1 | STUDIO 5
1817206 | NEW SENATE BUILDING - GROUND FLOOR | STUDIO 5
1817207 | NEW SENATE BUILDING - SECOND FLOOR | STUDIO 5
1713104 | THE EMERALD PROJECT VARIATION ORDER 04 | STUDIO 4
IP002 | TERRAVIVA DESIGN COMPETITION | undefined
1712408 | SLMC DAVAO VARIATION ORDER NO. 08 | STUDIO 2
2006101 | BPI MSE EXTENSION VO NO. 01 | STUDIO 2
20175 | PAZ CATALINA COLUMBARIUM ID | STUDIO 2
17131H | THE EMERALD HOTEL RESORT & CASINO- SITE ARCHITECTS | STUDIO 4
1310403 | THE STILES ENTERPRISE PLAZA - EXTENSION OF CONSTRUCTION | STUDIO 3
1705601 | UDENNA OFFICE INTERIORS VARIATION ORDER NO. 1 | STUDIO 2
1312105 | HSS VERVE 1 VARIATION ORDER | STUDIO 3
1305608 | THE VERANDA VARIATION ORDER | STUDIO 3
1701403 | SOUTHERN STAR - VARIATION ORDER NO. 03 | STUDIO 6
1713105 | EMERALD INTEGRATED RESORT- VARIATION ORDER NO. 05 | STUDIO 4
20180 | FULLWIN CLARK MIXED USE CONCEPT DESIGN | STUDIO 6
20185 | BEACON INTERNATIONAL SCHOOL | STUDIO 4
1800905 | WEST AEROPARK PHASE 2 CONSTRUCTION SERVICES - VO NO. 05 | STUDIO 4
1800906 | WEST AEROPARK PHASE 2 CONSTRUCTION SERVICES - VO NO. 06 | STUDIO 4
1806901 | GOOGLE VERTIS NORTH VARIATION ORDER NO.01 | STUDIO 2
21002 | PIK PROJECT KALINISAN | STUDIO 6
21006 | *ONE SIERRA - ID | STUDIO 2
1806904 | GOOGLE VERTIS NORTH VARIATION ORDER NO.04 | STUDIO 2
20174 | WIDUS EXPANSION PROJECT AOR CONSULTANCY SERVICES | STUDIO 1
21020 | *MANULIFE UP TECHNOHUB | STUDIO 2
21030 | IDESIA HEIGHTS MODEL UNITS ID | STUDIO 2
2017501 | PAZ CATALINA COLUMBARIUM - VARIATION ORDER NO. 01 | STUDIO 2
21017 | FPIP PROJECT DIAGON | STUDIO 4
12064 | CRIMSON BORACAY HOTEL | STUDIO 1
10011 | PARK TERRACES TOWER TWO | STUDIO 4
16061 | GARCIA WESTGROVE RESIDENCE | STUDIO 4
1106809 | SOLSTICE TOWER 1 - V.O. NO. 09 | STUDIO 4
17162 | POKER ROOM - SOLAIRE A&A | STUDIO 2
1410701 | THE NORTHBANK TOWERS A & B VARIATION ORDER NO. 1 | STUDIO 4
\N | Solaire Poker Room | STUDIO 2
14018Z | ANILAO STAFF HOUSE | STUDIO 4
13059 | PHILAMLIFE CENTER CEBU | STUDIO 2
10129 | ACC CORPORATE CENTER | STUDIO 2
13006 | KIDZANIA MANILA INTERIORS | STUDIO 2
21011 | SKY TOWER - BIM | STUDIO 3
19180J | NORTHGATE BLOCK 45 – DD to CS | STUDIO 3
1711501 | ONE VERTIS PLAZA VARIATION ORDER 01 | STUDIO 1
1711502 | ONE VERTIS PLAZA VARIATION ORDER 02 | STUDIO 1
16069 | .BAGUIO OFFICE BUILDING | STUDIO 3
1300804 | HSS VERVE TOWER 1 - VARIATION ORDER NO. 04 | STUDIO 3
1303801 | ABREEZA BPO 2 VARIATION ORDER NO. 1 | STUDIO 3
1303802 | ABREEZA BPO 2 VARIATION ORDER NO. 2 | STUDIO 3
1306301 | HIGH PARK TOWER 1 - VARIATION ORDER NO. 01 | STUDIO 3
1405502 | HIGH PARK TOWER 2 - VARIATION ORDER NO. 02 | STUDIO 3
1409301 | UDENNA TOWER PROJECT -VARIATION ORDER NO. 01 | STUDIO 3
1506903 | OREAN PLACE- VARIATION ORDER NO. 3 | STUDIO 3
1722301 | PATIO SUITES TOWER 2 VARIATION ORDER 1 | STUDIO 3
17013 | DMC MASTERPLAN | STUDIO 3
15024 | BROADWAY PROJECT | STUDIO 1
20126 | CLI ABACA HOTEL - ID AND EGD | STUDIO 7
21041 | BEACON INTERNATIONAL SCHOOL SITE 2 | STUDIO 4
1410703 | NORTHBANK TOWER A - EXTENSION OF CONSTRUCTION | STUDIO 4
20175D | PAZ CATALINA COLUMBARIUM ANIMATION | STUDIO 2
21005 | AMADEO MASTERPLANNING | STUDIO 4
1410704 | NORTHBANK MIXED USED DEVT - VARIATION ORDER NO, 04 | STUDIO 4
1817201 | NEW SENATE BUILDING - VO NO. 01 | STUDIO 5
1817202 | NEW SENATE BUILDING - VO NO. 02 | STUDIO 5
21048 | PALM RESIDENCES | STUDIO 5
21042 | PRI INDUSTRIAL PARK | STUDIO 4
21014 | *UA&P -DAVAO | STUDIO 4
1800907 | WAP PHASE 2 - 4TH EXTENSION OF CONSTRUCTION SERVICES | STUDIO 4
1800908 | WAP-VARIATION ORDER NO.08 | STUDIO 4
1818201 | ILAND RESIDENCES - VARIATION ORDER NO. 01 (TOWER 2 RE-DESIGN) | STUDIO 4
21028 | CWC ARNAIZ | STUDIO 2
20107 | CABADBARAN SPORTS COMPLEX | STUDIO 1
1713106 | EMERALD INTEGRATED RESORT - VARIATON ORDER NO. 06 | STUDIO 4
1701404 | SOUTHERN STAR - 2ND EXTENSION OF CONSTRUCTION | STUDIO 6
21058 | JTI GENEVA ID | STUDIO 7
1507526 | MANDANI BLOCK 2 - VARIATION ORDER NO. 26 | STUDIO 5
1817208 | NEW SENATE BUILDING - UTILITY TAPPING POINT RELOCATION & SDP | STUDIO 5
1507528 | MANDANI BAY SUITES VARIATION ORDER NO. 28 | STUDIO 5
21099 | RLC BUSAY MP | STUDIO 5
2101701 | PROJECT DIAGON - VARIATION ORDER NO. 01 | STUDIO 4
21007 | DISTRICT M | STUDIO 1
1302903 | GARDEN TOWERS T2- 2BD EXTENSION OF CONSTRUCTION | STUDIO 4
21074 | BT PROJECT GENESIS - ID & EGD | STUDIO 7
21100 | SRP MIXED-USE DEVELOPMENT | STUDIO 1
1506809 | CALLISTO TOWER 2 - EXTENSION OF CONSTRUCTION SERVICES | STUDIO 4
2017502 | PAZ COLUMBARIUM - VARIATION ORDER NO. 02 | STUDIO 2
13102J | DOWELL TOWER - SD TO CS | STUDIO 3
16039J01 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 01 | STUDIO 3
16039J02 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 02 | STUDIO 3
16039J03 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 03 | STUDIO 3
16039J04 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 04 | STUDIO 3
16039J06 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 06 | STUDIO 3
16039J07 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 07 | STUDIO 3
16039J09 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 09 | STUDIO 3
16039J10 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 10 | STUDIO 3
16039J11 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 11 | STUDIO 3
16039J12 | GATEWAY MALL & HOTEL VARIATION ORDER NO. 12 | STUDIO 3
1507304 | PATIO SUITES TOWER 1 VARIATION ORDER NO. 04 | STUDIO 4
2003901 | PARK TERRACES SUPPLEMENTARY SERVICES - VARIATION ORDER NO. 01 | STUDIO 4
2003902 | PARK TERRACES SUPPLEMENTARY SERVICES - VARIATION ORDER NO. 02 | STUDIO 4
2003903 | PARK TERRACES SUPPLEMENTARY SERVICES - VARIATION ORDER NO. 03 | STUDIO 4
20095 | MENARCO TOWER 2 | STUDIO 5
21078 | PROJECT MERGENT PHASE 2 | STUDIO 3
1410705 | NORTHBANK MIXED USE DEVT - VARIATION ORDER NO. 05 | STUDIO 4
16039 | ACI GATEWAY MALL & HOTEL: CD-CS | STUDIO 3
1819202 | TGT REDEVELOPMENT – VARIATION ORDER NO. 02 | STUDIO 2
20190 | WATCH TOWER - ADMIN BUILDING | STUDIO 3
1716302 | SOLAIRE 3 BEDROOM SUITES – VARIATION ORDER NO. 02 | STUDIO 2
1716802 | SOLAIRE CASINO CEILING WAYFINDING SCOPE | STUDIO 2
1825601 | SOLAIRE L3 VIP WALL – VARIATION ORDER NO. 01 | STUDIO 2
1923801 | SOLAIRE WATERSIDE RESTOBAR – VARIATION ORDER NO. 01 | STUDIO 2
1908103 | SOLAIRE VIP VILLA – VARIATION ORDER NO. 03 | STUDIO 2
1816001 | SOLAIRE PRESIDENTIAL AND CHAIRMAN SUITES - VARIATION ORDER NO. 01 | STUDIO 2
21111 | MSC CWC ARNAIZ OFFICE – DD TO CS | STUDIO 2
21124 | PROFRIENDS PROJECT HOPE FACADE REDEVELOPMENT | STUDIO 2
21096 | IDESIA SALES OFFICE | STUDIO 2
2017503 | PAZ CATALINA COLUMBARIUM – VARIATION ORDER NO. 03 | STUDIO 2
1507527 | MANDANI BAY SUITES - VARIATION ORDER NO. 27 | STUDIO 5
1507701 | THE GENTRY -VARIATION ORDER NO. 01 | STUDIO 3
1711503 | ONE VERTIS PLAZA – VARIATION ORDER NO. 03 | STUDIO 1
21128 | BEACON INTERNATIONAL SCHOOL SITE 3 – CONCEPT STUDIES | STUDIO 4
1506904 | OREAN PLACE - VARIATION ORDER NO. 04 | STUDIO 3
21125 | FIT DORM | STUDIO 3
11068 | SOLSTICE TOWER 1 | STUDIO 4
17068 | MGI DISTRIBUTION CENTER | STUDIO 4
1800909 | WAP PHASE 2 - 6TH EXTENSION OF CONSTRUCTION SERVICES. | STUDIO 4
21140 | CLI ABACA HOTEL F&B ID WORKS | STUDIO 7
21116 | *CATTLEYA PROJECT | STUDIO 2
21060 | FBDC PROJECT MACE | STUDIO 3
1410706 | NORTHBANK MIXED USE DEVELOPMENT - VARIATION ORDER NO. 06 | STUDIO 4
21130 | AQUARION SAMAL SHORES LA FAMILIA MP | STUDIO 5
21029 | PROJECT GENESIS BIM | STUDIO 1
21130J | POSEIDON SAMAL SHORES CHEMAS MP | STUDIO 5
21064 | PTCP SUPPLEMENTARY SERVICES | STUDIO 3
21063 | SEQUOIA SUPPLEMENTARY SERVICES | STUDIO 3
1608502 | 110 BENAVIDEZ CITADINES ID - VARIATION ORDER NO. 02 | STUDIO 3
1926102 | PROJECT ELURIA - VARIATION ORDER NO. 02 | STUDIO 5
1609401 | PROJECT THEODORE – EXTENSION OF CONSTRUCTION | STUDIO 3
21153 | *CCH PROJECT VISION | STUDIO 5
1818202 | ILAND RESIDENCES - VARIATION ORDER NO. 02 (TOWER 3 RE-DESIGN) | STUDIO 4
IP003 | AIDEA 32ND OFFICE EXPANSION FIT-OUT | undefined
1411003 | 110 BENAVIDEZ RSIDENCES-VARIATION ORDER NO. 03 | STUDIO 3
21087 | STELLO CENTRALE | STUDIO 1
1612412 | MI CASA - VARIATION ORDER NO. 12 | STUDIO 5
21093 | DISTRICT M DORMITEL LOD 350 | STUDIO 1
21094 | DISTRICT M RESIDENTIAL LOD 350 | STUDIO 1
1607309 | MANDANI BAY QUAY - VARIATION ORDER NO. 09 | STUDIO 5
21141 | IDA MNL1 DATA CENTER | STUDIO 6
16025Z | CRS-ITPII FACADE DESIGN CONSULTANCY | STUDIO 6
1602502 | CIVIL REGISTRY - IT PROJECT PHASE 2 VARIATION ORDER NO. 2 | STUDIO 6
1602504 | CIVIL REGISTRY - IT PROJECT PHASE 2 VARIATION ORDER NO. 4 | STUDIO 6
1805901 | NAB2 - VARIATION ORDER NO. 01 | STUDIO 3
1908101 | SOLAIRE VIP VILLA VARIATION ORDER NO. 01 BUTLER'S ROOM | STUDIO 2
1908102 | SOLAIRE VIP VILLA VARIATION ORDER NO. 02 SWITCHES AND RCU | STUDIO 2
1305605 | THE VERANDA-VARIATION ORDER NO. 05 | STUDIO 6
1701405 | SOUTHERN STAR PKS BOILER BUILDING | STUDIO 6
21150 | ALI PROJECT L | STUDIO 2
21168 | TAFT PROPERTIES PASONG TAMO TOWERS MP | STUDIO 4
1701407 | SOUTHERN STAR - 3RD EXTENSION OF CONSTRUCTION | STUDIO 6
21127 | SPI BAYORAN | STUDIO 1
21115 | MOLDEX MASTERPLANNING | STUDIO 1
21144 | HASKELL NCL CENTER OF EXCELLENCE MANILA | STUDIO 1
21147 | YONDU SOC ID | STUDIO 2
21175 | *FBDC PARK TRIANGLE RETAIL MALL REDESIGN | STUDIO 1
21088 | DDTKI MANDANI BAY PHASE 3A | STUDIO 5
21171 | PROJECT CALATAGAN MP | STUDIO 1
1601902 | PARK TRIANGLE RESIDENCES - VARIATION ORDER NO. 2 | STUDIO 1
21107 | ATPI PROJECT THOR | STUDIO 1
22004 | *TRANS ASIA ALABANG OFFICE ID | STUDIO 2
22009 | GLOBE ICONIC SOUTH WING ID | STUDIO 2
1506810 | CALLISTO TOWER 1 – 2ND EXTENSION OF CONSTRUCTION SERVICES | STUDIO 4
1506811 | CALLISTO TOWER 2 - 2ND EXTENSION OF CONSTRUCTION SERVICES | STUDIO 4
21135 | ABL SEAFRONT TOWN CENTER | STUDIO 4
1612413 | MI CASA - VARIATION ORDER NO. 13 | STUDIO 5
1800910 | WAP PHASE 2 - VARIATION ORDER NO. 10 | STUDIO 4
1612414 | MI CASA - VARIATION ORDER NO. 14 | STUDIO 5
1507529 | MANDANI BAY SUITES - VARIATION ORDER NO. 29 | STUDIO 5
21012 | ADB ID + BIM | STUDIO 7
21183 | BSP COMPLEX SEMI & NON-RESTRICTED ZONES | STUDIO 6
22005 | *NEW CORE MANILA POLO CLUB - F&B VERANDA | STUDIO 2
1819201 | TGT REFRESH - VARIATION ORDER NO. 01 | STUDIO 2
2017405 | WIDUS EXPANSION – SIGNAGE CS EXTENSION | STUDIO 1
1607310 | MANDANI BAY QUAY - VARIATION ORDER NO. 10 | STUDIO 5
22022 | BERIC COUNTRY CLUB GENEVA RENDERING | STUDIO 2
22026 | CWC SUBIC WATERFRONT MP | STUDIO 2
21129 | FPIP PROJECT ALPHA | STUDIO 4
21162 | FPIP PROJECT DIAGON SOUTH PARCEL DEVELOPMENT | STUDIO 4
2100201 | PROJECT KALINISAN - VARIATION ORDER NO.01 | STUDIO 6
2100202 | PROJECT KALINISAN - VARIATION ORDER NO.02 | STUDIO 6
2100203 | *PIK PROJECT KALINISAN - VARIATION ORDER NO. 03 | STUDIO 6
1410707 | NORTHBANK MIXED USE DEVELOPMENT - VARIATION ORDER NO. 07 | STUDIO 4
1800911 | WAP PHASE 2 - VARIATION ORDER NO. 11 | STUDIO 4
IP004 | 30F OFFICE EXPANSION 2022 | undefined
21134 | BENCH HQ ID & EGD | STUDIO 4
1902302 | PMW VARIATION ORDER NO. 02 | STUDIO 3
1711504 | ONE VERTIS PLAZA – VARIATION ORDER NO. 04 | STUDIO 1
21159 | ACI GM2 IBIS STYLES HOTEL BISTRO ID | STUDIO 3
1902303 | PARK MCKINLEY WEST - VARIATION ORDER NO. 03 | STUDIO 3
22027 | CLI CDO MIXED-USE MASTERPLAN | STUDIO 4
22006 | AMBERLAND EL PUEBLO OFFICE TOWER | STUDIO 4
22017 | FPIP PROJECT ALPHA ID | STUDIO 4
21154 | SEPI HABITAT 22 WELLNESS RESORT | STUDIO 4
1302904 | GARDEN TOWERS T2 - VARIATION ORDER NO. 04 | STUDIO 4
1507530 | MANDANI BAY SUITES - VARIATION ORDER NO. 30 | STUDIO 5
1923201 | ARQ BEACH RESORT VARIATION ORDER NO. 01 | STUDIO 1
1817214 | NEW SENATE BUILDING - FOURTH FLOOR | STUDIO 5
1817215 | NEW SENATE BUILDING - FIFTH FLOOR | STUDIO 5
1817216 | NEW SENATE BUILDING - SIXTH FLOOR | STUDIO 5
1817217 | NEW SENATE BUILDING - SEVENTH FLOOR | STUDIO 5
1817218 | NEW SENATE BUILDING - EIGHT FLOOR | STUDIO 5
1817219 | NEW SENATE BUILDING - NINTH FLOOR | STUDIO 5
1817220 | NEW SENATE BUILDING - TENTH FLOOR | STUDIO 5
1817221 | NEW SENATE BUILDING - ELEVENTH FLOOR | STUDIO 5
1817222 | NEW SENATE BUILDING - RENDER | STUDIO 5
1817209 | NEW SENATE BUILDING - BASEMENT 1 VER 2 | STUDIO 5
1817210 | NEW SENATE BUILDING - GROUND FLOOR VER 2 | STUDIO 5
1817211 | NEW SENATE BUILDING - GROUND FLOOR VER 3 | STUDIO 5
1817212 | NEW SENATE BUILDING - PAC TRELLIS | STUDIO 5
1817213 | NEW SENATE BUILDING - THIRD FLOOR | STUDIO 5
22025 | JECO CEBU PARK RESIDENCES MP | STUDIO 5
1817223 | NEW SENATE BUILDING - LOWER ROOF DECK | STUDIO 5
1817224 | NEW SENATE BUILDING - UPPER ROOF DECK | STUDIO 5
1817225 | NEW SENATE BUILDING - FACADE SCHEME 3 RE-DESIGN | STUDIO 5
1817226 | NEW SENATE BUILDING - MAIN CANOPY REDESIGN | STUDIO 5
1817227 | NEW SENATE BUILDING - SKYLIGHT REDESIGN | STUDIO 5
1924204 | ONE SIERRA - VARIATION ORDER NO. 04 | STUDIO 2
1924205 | ONE SIERRA - VARIATION ORDER NO. 05 | STUDIO 2
2111101 | MSC CWC ARNAIZ OFFICE – DD TO CS - VARIATION ORDER NO. 01 | STUDIO 2
2102801 | CWC ARNAIZ - VARIATION ORDER NO. 01 | STUDIO 2
2012601 | CLI ABACA HOTEL ID - VARIATION ORDER NO. 01H | STUDIO 7
22028 | APMC SHOWROOM GLORIETTA 2 | STUDIO 2
22059 | MRI OFFICE RENOVATION | STUDIO 2
22039 | PROFRIENDS AMENITY AND PARKING | STUDIO 2
22042 | ESTUDIO ARKIPELAGO ANZA | STUDIO 4
1701408 | SOUTHERN STAR AEROPACK - EXTENSION OF CONSTRUCTION | STUDIO 6
21012A | ADB OPC SPACE | STUDIO 7
22032 | *MAPLECREST LANDBANK PLANNING WORKSHOP | STUDIO 2
1305610 | THE VERANDA - 2ND EXTENSION OF CONSTRUCTION | STUDIO 6
22071 | BEACON SITE 3 MC | STUDIO 4
22076 | OLEO FATS OFFICE RENOVATION | STUDIO 2
22048 | PREMIUMLANDS BUNAWAN MIXED-USE MP | STUDIO 2
1806905 | GOOGLE VERTIS NORTH EXTENDED CA - CLOSE OUT | STUDIO 2
22055 | MOLDEX SILANG SOUTHRIDGE MEDIUM RISE COMMUNITY | STUDIO 1
22044 | GENVI MONTERRAZAS DE CEBU MP | STUDIO 1
22046 | WIDUS EXPANSION RETAIL DESIGN GUIDELINES | STUDIO 1
22023 | 947 SKY TOWER | STUDIO 3
22019 | BSP RESTRICTED ZONE | STUDIO 6
1701409 | SOUTHERN STAR - EXTENSION OF CONSTRUCTION FOR PREMIUM, NATURA AND AEROPACK | STUDIO 6
22060 | FHDC PHASE 6 AUREO | STUDIO 5
22081 | DMC TAGUIG MASTERPLAN | STUDIO 5
21043 | CGC CHAPEL | STUDIO 4
22043 | TRANSASIA BANYAN TREE DESIGN MANAGEMENT | STUDIO 1
1716801 | SOLAIRE CASINO CEILING ID VARIATION ORDER NO. 01 | STUDIO 2
1924203 | ONE SIERRA - VARIATION ORDER NO. 03 | STUDIO 2
1924202 | *ONE SIERRA - LANDSCAPE | STUDIO 2
22070 | PCFI RENDERING SERVICES | STUDIO 2
1701406 | SOUTHERN STAR – VARIATION ORDER NO. 06 | STUDIO 6
22051 | SOP CORON MP ZONE A | STUDIO 5
1506812 | CALLISTO TOWER 1 - 3RD EXTENSION OF CONSTRUCTION | STUDIO 4
1506813 | CALLISTO TOWER 2 - 3RD EXTENSION OF CONSTRUCTION | STUDIO 4
22011 | PRISTINA NORTH TOWN | STUDIO 4
22089 | P.A. PROPERTIES IDESIA CABUYAO ID | STUDIO 2
2017504 | PAZ CATALINA COLUMBARIUM – CD TO CS | STUDIO 2
22072 | JPMC MANILA IFC OFFICE ID | STUDIO 8
16039J13 | GATEWAY MALL & HOTEL - EXTENSION OF CONSTRUCTION | STUDIO 3
22086 | HSS VERVE TOWER 1 – SUPPLEMENTARY SERVICES | STUDIO 3
22087 | HSS VERVE TOWER 2 – SUPPLEMENTARY SERVICES | STUDIO 3
22088 | TWO MARIDIEN - SUPPLEMENTARY SERVICES | STUDIO 3
2114101 | VO NO. 01 - IDA DATA CENTER ID | STUDIO 6
1310402 | THE STILES ENTERPRISE PLAZA - VARIATION ORDER NO. 02 | STUDIO 3
2105801 | JTI GENEVA ID - VARIATION ORDER NO. 01 | STUDIO 7
2105802 | JTI GENEVA ID - VARIATION ORDER NO. 02 | STUDIO 7
1612415 | MI CASA - VARIATION ORDER NO. 15 | STUDIO 5
22045 | RLC MONTCLAIR PAMPANGA DSG | STUDIO 1
2111102 | MSC CWC ARNAIZ OFFICE DD TO CS - REDESIGN UPDATE | STUDIO 2
1906501 | BAGUIO OFFICE - EXTENSION OF CONSTRUCTION | STUDIO 3
22105 | BPI BFB HEAD OFFICE CODE REVIEW | STUDIO 3
2017506 | PAZ CATALINA COLUMBARIUM - VARIATION ORDER NO. 06 | STUDIO 2
2105803 | JTI GENEVA ID - PLOOM CAFE AND IMAGINARIUM REDESIGN | STUDIO 7
2017403 | WIDUS EXPANSION PROJECT AOR - VARIATION ORDER NO. 03 | STUDIO 1
2017404 | WIDUS EXPANSION PROJECT AOR - VARIATION ORDER NO. 04 | STUDIO 1
2105804 | JTI GENEVA ID - 6TH FLOOR MODELING AND EXCOM OFFICE REDESIGN | STUDIO 7
2019001 | WATCH TOWER - EXTENSION OF CONSTRUCTION | STUDIO 3
22098 | WEST GROVE RESORT EXPANSION | STUDIO 5
1612416 | MI CASA - 2ND EXTENSION OF CONSTRUCTION | STUDIO 5
1817228 | NEW SENATE BUILDING - VARIATION ORDER NO. 28 | STUDIO 5
22126 | CGC OFFICE TEST PLAN | STUDIO 4
1410708 | NORTHBANK FOUNDRY MALL - AR REVISIONS | STUDIO 4
1801601 | *UST GENSAN CAMPUS - EXTENSION OF CONSTRUCTION | STUDIO 1
22029 | BEACON INTERNATIONAL SCHOOL SITE 3 | STUDIO 4
1601701 | PROJECT CHEWEE - BPO CS EXTENSION | STUDIO 1
16039J14 | ACI GM2 CHURCH REVISION | STUDIO 3
16039J15 | ACI GM2 CINEMA ATRIUM | STUDIO 3
21022 | NAB3 BIM CSD | STUDIO 3
22131 | PENG LAI SITE REDEVELOPMENT | STUDIO 5
1902301 | PARK MCKINLEY WEST PHASE 2A | STUDIO 3
1701410 | SOUTHERN STAR - VARIATION ORDER NO. 10 | STUDIO 6
2100205 | PIK PROJECT KALINISAN - AR VO | STUDIO 6
2100206 | PIK PROJECT KALINISAN - ID VO | STUDIO 6
2100207 | PIK PROJECT KALINISAN - MEPF VO | STUDIO 6
20067 | ANVAYA COVE N10 | STUDIO 1
22113 | CLI MANRESA RESIDENTIAL | STUDIO 4
22129 | BT SALES LOUNGE & RESIDENTIAL SHOW UNIT | STUDIO 2
2204201 | ESTUDIO PROJECT ANZA - CFA INCREASE | STUDIO 4
2010501 | DGT SE BLOCK RESIDENCES - VARIATION ORDER NO. 01 | STUDIO 4
2105805 | JTI GENEVA ID - EGD | STUDIO 7
22127 | TGT REFRESH 2.0 | STUDIO 2
22128 | MYNT OFFICE FIT-OUT | STUDIO 7
1722401 | COURTYARD BY MARRIOTT CEBU VARIATION ORDER NO. 1 | STUDIO 1
22109 | GLOBE YONDU 7F OFFICE ID | STUDIO 7
21012B | ADB BPMSD SPACE | STUDIO 7
22136 | STT GDC OFFICE FIT-OUT | STUDIO 7
2207001 | PCFI RENDERING SERVICES – ADDITIONAL 4 LIFESTYLE SHOTS | STUDIO 2
1612417 | MI CASA - VARIATION ORDER NO. 17 | STUDIO 5
2116201 | PROJECT DIAGON SOUTH PARCEL DEVELOPMENT - INCREASE IN AREA | STUDIO 4
22140 | MOLDEX RESIDENTIAL CONDOMINIUM | STUDIO 3
2017406 | WIDUS EXPANSION PROJECT AOR – EXTENSION OF CONSTRUCTION | STUDIO 1
22135 | METROGATE SILANG CAVITE EXPANSION | STUDIO 3
1911201 | ARUP OFFICE FIT-OUT VARIATION ORDER NO. 01 | STUDIO 2
2115001 | ALI PROJECT L - VARIATION ORDER NO. 01 | STUDIO 2
2118301 | BSP SNR ZONES– VARIATION ORDER NO. 01 | STUDIO 6
2012801 | PROJECT GENESIS AR - RESIDENT ARCHITECT | STUDIO 1
22134 | URBAN HIVE MP | STUDIO 3
1923202 | ARQ BEACH RESORT - VARIATION ORDER NO. 02 | STUDIO 1
1817229 | NEW SENATE BUILDING - PHASE 1 EXTENSION OF CONSTRUCTION | STUDIO 5
22161 | FRIDAYS BORACAY MP | STUDIO 3
1800912 | WAP PHASE 2 - VARIATION ORDER NO. 12 | STUDIO 4
22150 | SATORI PROJECT ROCKET | STUDIO 6
22165 | PROJECT ROCKET DEMOLITION PACKAGE | STUDIO 6
22152 | BULIHAN CIRCLE* | STUDIO 5
22120 | ALP NUVALI MRB D&B | STUDIO 1
22167 | WAP B3 CONSTRUCTION SERVICES | STUDIO 4
22145 | AEON BLEU - TOWERS 4 AND 6 | STUDIO 5
1506814 | CALISTO TOWER 1 - 4TH CA EXTENSION | STUDIO 4
1506815 | CALISTO TOWER 2 - 4TH CA EXTENSION | STUDIO 4
1302905 | GARDEN TOWERS T2 - 4TH CA EXTENSION | STUDIO 4
22077 | SLMC ASEANA | STUDIO 2
22139 | 947 SKY TOWER AMENITY AREA ID | STUDIO 7
22163 | ARUP PROJECT LUNA | STUDIO 6
2112501 | *FIT DORM - EXTENSION OF CONSTRUCTION | STUDIO 3
22173 | ABACA RESORT SOGOD CEBU | STUDIO 3
22176 | SALESIAN MEMORIAL GARDEN COLUMBARIUM | STUDIO 3
1909901 | PROJECT AZUELA - VARIATION ORDER NO. 01 | STUDIO 3
1909902 | PROJECT AZUELA - VARIATION ORDER NO. 02 | STUDIO 3
1909903 | PROJECT AZUELA - VARIATION ORDER NO. 03 | STUDIO 3
1506905 | OREAN PLACE - VARIATION ORDER NO. 05 | STUDIO 3
23010 | CWC ARNAIZ ID | STUDIO 2
1807801 | OREAN PLACE TOWER 2 - VARIATION ORDER NO. 01 | STUDIO 3
1722303 | *PATIO SUITES TOWER 2 - FAÇADE REVISION | STUDIO 3
1722304 | *PATIO SUITES TOWER 2 - REVISED GF PER IRR | STUDIO 3
1908001 | VIBE TOWER 3 - VARIATION ORDER NO. 01 | STUDIO 3
1908002 | VIBE TOWER 3 - RESUBMISSION OF DD PLANS | STUDIO 3
1908003 | VIBE TOWER 3 - VARIATION ORDER NO. 03 | STUDIO 3
1908004 | VIBE TOWER 3 - CONSOLIDATED VOS | STUDIO 3
22118 | XU CAMPUS OF THE FUTURE | STUDIO 4
22054 | ABACA NUSTAR BAKING COMPANY | STUDIO 7
23008 | *CHEMPHIL TEST FIT | STUDIO 2
22175 | DON BOSCO NEW ZATTI HOUSE | STUDIO 3
1902304 | PMW PH2 ID - REVISED MATERIAL FINISHES OF COMMON AREA AND AMENITIES | STUDIO 3
23001 | *HOLY SPIRIT TAGAYTAY MP | STUDIO 3
2212701 | TGT REFRESH 2.0 - REDESIGN UPDATE | STUDIO 2
21032 | SAMAL SHORES AVP RENDERS | STUDIO 5
23009 | BALTIMORE OFFICE MP | STUDIO 4
23014 | GSIS CGC CONCEPT | STUDIO 4
2112901 | PROJECT ALPHA - RECONFIGURATION OF MP | STUDIO 4
1506816 | CALLISTO TOWER 1 – 4TH CA EXTENSION | STUDIO 4
1506817 | CALLISTO TOWER 2 - 4TH CS EXTENSION | STUDIO 4
1818207 | ILAND RESIDENCES - 1ST CA EXTENSION TOWER 1 | STUDIO 4
1302906 | GARDEN TOWERS T2 - 5TH CA EXTENSION | STUDIO 4
1817230 | NEW SENATE BUILDING - PHASE 2 | STUDIO 5
23017 | CALIRAYA MASTERPLAN | STUDIO 5
23036 | WAP THREE WEST RECEPTION ID | STUDIO 4
2112902 | PROJECT ALPHA - INCREASE IN CFA | STUDIO 4
23056 | CGIF TEST FIT | STUDIO 7
23007 | IRISH EMBASSY FIT-OUT | STUDIO 7
23039 | WORLD BALANCE FELIZ ID | STUDIO 2
1711508 | ONE VERTIS PLAZA - FOOD HALL LIGHTING DESIGN | STUDIO 1
23022 | ADB OAG CTL TD | STUDIO 7
2201701 | PROJECT ALPHA ID - INCREASE IN CFA | STUDIO 4
23038 | FLI BIÑAN VILLAGE CLUBHOUSE AND GUARDHOUSES | STUDIO 5
1608503 | 110 BENAVIDEZ CITADINES ID – 2ND EXTENSION OF CONSTRUCTION | STUDIO 3
23019 | DGT SE RESIDENCES ID | STUDIO 4
23041 | EPLDT VSR VISUALIZATION | STUDIO 6
16039J17 | ACI GM2 - A&E 2ND CS EXTENSION | STUDIO 3
1608501 | 110 BENAVIDEZ CITADINES ID VARIATION ORDER NO. 01 | STUDIO 3
23057 | ADB ACCESSIBILITY COMPLIANCE | STUDIO 3
1711507 | ONE VERTIS PLAZA - LPI CS EXTENSION | STUDIO 1
2106002 | PROJECT MACE - EXTERIOR VALUE ENGINEERING DESIGN | STUDIO 3
23042 | FRIDAYS BORACAY | STUDIO 3
1403206 | PADDINGTON PLACE - VARIATION ORDER NO. 06 | STUDIO 1
23072 | UPTOWN GLOBAL RESIDENCE | STUDIO 3
1906502 | *BAGUIO OFFICE - 2ND CA EXTENSION | STUDIO 3
23067 | ILOILO BUSINESS PARK RESIDENTIAL CONDO 7 | STUDIO 3
23046 | ONE WESTPARK RESIDENCES (MWC4 / PMW3) | STUDIO 3
23078 | MACTAN NEWTOWN RESIDENTIAL CONDOMINIUM 8 | STUDIO 3
23079 | MCKINLEY WEST RESIDENTIAL CONDOMINIUM 5 | STUDIO 4
23068 | MANHATTAN PLAZA ICON TOWER | STUDIO 2
2207201 | JPMC MANILA IFC OFFICE ID – ADDITIONAL LOBBY AREA | STUDIO 8
2207203 | JPMC OFFICE ID - LIGHTING | STUDIO 7
2207205 | JPMC OFFICE ID – LEVELS 19 - 20 | STUDIO 8
23086 | FROSCH IFC 17F | STUDIO 8
23087 | CXLOYALTY IFC 17F - 18F | STUDIO 8
23082 | ILOILO BUSINESS PARK RESIDENTIAL CONDO 7 – BIM | STUDIO 3
23044 | FPIP PROJECT DIAGON ANIMATION | STUDIO 4
22056 | DLI SKY TOWER RESIDENCES BIM | STUDIO 3
1507702 | THE GENTRY - 2ND EXTENSION OF CONSTRUCTION | STUDIO 3
2201101 | PRISTINA NORTH TOWN - PH1 REDESIGN | STUDIO 4
23118 | SLMC W 5TH OFFICE ID | STUDIO 7
1722305 | PATIO SUITES TOWER 2 - CA EXTENSION | STUDIO 3
16039J16 | ACI GM2 - ID CS EXTENSION | STUDIO 3
2106001 | FBDC PROJECT MACE - INCREASE IN CFA | STUDIO 3
1601702 | PROJECT CHEWEE - RETAIL CA EXTENSION | STUDIO 1
1601903 | PARK TRIANGLE RESIDENCES - 2ND CA EXTENSION | STUDIO 1
23112 | CHEMPHIL BUILDING RENOVATION | STUDIO 3
23100 | SONAK HQ | STUDIO 2
23092 | PHOENIX OFFICE FIT-OUT | STUDIO 7
1711506 | ONE VERTIS PLAZA – VARIATION ORDER NO. 06 | STUDIO 1
23052 | ALP PROJECT GENESIS | STUDIO 5
23122 | FNG LANCASTER ENCLAVE 2 - PACKAGE 1 | STUDIO 5
23123 | FNG LANCASTER ENCLAVE 2 - PACKAGE 2 | STUDIO 5
2213601 | STT GDC OFFICE FIT OUT - 3D VIDEO WALK-THRU | STUDIO 7
22153 | BULIHAN CIRCLE CONCEPT MP | STUDIO 5
22154 | MALVAR HOSPITAL | STUDIO 2
23018 | KEYLAND KATIPUNAN CONDO-DORM | STUDIO 3
23097 | AMANI TOWER | STUDIO 6
2110703 | PROJECT THOR – LEED | STUDIO 1
23129 | *FIRST BALFOUR HO REFRESH | STUDIO 7
1815101 | PROJECT GARNET - VARIATION ORDER NO. 01 | STUDIO 1
23128 | LANDMARK EXTENSION & SECONDARY BRIDGE – ID | STUDIO 7
23163 | *SLMC EXPANSION GROUP OFFICE ID | STUDIO 2
23101 | MCKINLEY WEST CONDO 4 (PARK MCKINLEY WEST PHASE 3) – ID | STUDIO 7
23140 | UNIQLO WAREHOUSE CODE REVIEW | STUDIO 2
23035 | AEON STUDIOS | STUDIO 5
23145 | UPTOWN GLOBAL RESIDENCE - RENDERING | STUDIO 3
23138 | MACTAN NEWTOWN RESIDENTIAL CONDOMINIUM 8 - ID | STUDIO 3
23108 | ONE WESTPARK RESIDENCES (MWC4 / PMW3) - RENDERING | STUDIO 3
23136 | MCKINLEY WEST RESIDENTIAL CONDOMINIUM 5 - ID | STUDIO 4
23144 | ILOILO BUSINESS PARK RESIDENTIAL CONDO 7 - RENDERING | STUDIO 3
23146 | MCKINLEY WEST RESIDENTIAL CONDOMINIUM 5 - RENDERING | STUDIO 4
23147 | MACTAN NEWTOWN RESIDENTIAL CONDOMINIUM 8 - RENDERING | STUDIO 3
23134 | ILOILO BUSINESS PARK RESIDENTIAL CONDO 7 - ID | STUDIO 3
23137 | MANHATTAN PLAZA ICON TOWER - ID | STUDIO 2
23135 | UPTOWN GLOBAL RESIDENCE - ID | STUDIO 3
2108701 | STELLO CENTRALE - DESIGN CHANGES | STUDIO 1
2208101 | DMC TAGUIG MASTERPLAN - VARIATION ORDER NO. 01 | STUDIO 5
23061 | CITY GARDEN NUVALI | STUDIO 1
23105 | TEAM BUILDING CAMP 2 MP | STUDIO 5
23161 | 947 SKY TOWER AVP | STUDIO 3
2204402 | GENVI MONTERRAZAS DE CEBU - INDIVIDUAL LOT PLANS AND SALEABLE LOTS | STUDIO 1
23184 | *PANGHULAN SUITE | STUDIO 5
2109601 | IDESIA SALES OFFICE - REDESIGN | STUDIO 2
23026 | MANRESA AMENITY AREAS ID | STUDIO 4
23154 | PRISTINA NORTH TOWN ID | STUDIO 4
1506818 | CALLISTO TOWER 1 - 5TH CA EXTENSION | STUDIO 4
1506819 | CALLISTO TOWER 2 - 5TH CA EXTENSION | STUDIO 4
16039J18 | ACI GM2 - ID 2ND CS EXTENSION | STUDIO 3
16039J19 | ACI GM2 - A&E 3RD CS EXTENSION | STUDIO 3
23170 | BPI ATG WEALTH FLOOR ID | STUDIO 7
23190 | HSSCP TOWERS 1 & 2 SUPPLEMENTARY SERVICES | STUDIO 4
1507501 | MANDANI BLOCK 2 - VARIATION ORDER NO. 01 | STUDIO 5
1507502 | MANDANI BLOCK 2 - VARIATION ORDER NO. 02 | STUDIO 5
1507503 | MANDANI BLOCK 2 - VARIATION ORDER NO. 03 | STUDIO 5
1507505 | MANDANI BLOCK 2 - VARIATION ORDER NO. 05 | STUDIO 5
23109 | NEW MARKET DUE DILIGENCE PH | STUDIO 6
23157 | ILOILO BUSINESS PARK RESIDENTIAL CONDO 7 - LANDSCAPE | STUDIO 3
23158 | UPTOWN GLOBAL RESIDENCE - LANDSCAPE | STUDIO 3
23080 | UPTOWN GLOBAL RESIDENCE - BIM | STUDIO 3
23083 | MCKINLEY WEST RESIDENTIAL CONDOMINIUM 5 - BIM | STUDIO 4
23159 | MCKINLEY WEST RESIDENTIAL CONDOMINIUM 5 - LANDSCAPE | STUDIO 4
23160 | MACTAN NEWTOWN RESIDENTIAL CONDOMINIUM 8 - LANDSCAPE | STUDIO 3
23211 | JPMC BANGALORE TEST FIT | STUDIO 7
1818203 | I-LAND RESIDENCES TOWER 4 REDESIGN | STUDIO 4
23192 | DPWH BUTUAN ID | STUDIO 7
23180 | BAYUGAN COMMUNITY HOSPITAL | STUDIO 2
23188 | AEON TOWER 3 ID | STUDIO 7
23194 | DGT T5 T6 RENDERING | STUDIO 4
1926105 | PROJECT ELURIA - VARIATION ORDER NO. 05 | STUDIO 5
23142 | CBRE TDD ID MUMBAI | STUDIO 7
1902305 | PARK MCKINLEY WEST – 1ST CA EXTENSION | STUDIO 3
1607312 | MANDANI BAY QUAY - 1ST CS EXTENSION | STUDIO 5
23116 | BPI BRANCHES FACADE DSG | STUDIO 2
1908005 | VIBE TOWER 3 - GF AND CURTAIN WALL REVISIONS | STUDIO 3
1908006 | VIBE TOWER 3 - APMC MAINTAINABILITY | STUDIO 3
1908007 | VIBE TOWER 3 - 3BDRM UNIT ADJUSTMENTS | STUDIO 3
1922702 | CLI ABACA HOTEL CS EXTENSION | STUDIO 3
1907702 | W OFFICE BGC - CD ADDITIONAL BASEMENT | STUDIO 3
2212802 | MYNT OFFICE - VARIATION ORDER NO. 2 | STUDIO 7
23214 | ADB CGIF | STUDIO 7
2012602 | CLI ABACA HOTEL ID - BOH REPLANNING 2 | STUDIO 7
2012603 | CLI ABACA HOTEL ID - FOH DESIGN REVISIONS | STUDIO 7
2012604 | CLI ABACA HOTEL ID - ADDITIONAL GUEST UNIT TYPES | STUDIO 7
2012605 | CLI ABACA HOTEL ID - DESIGN REVISIONS AND PATISSERIE DESIGN | STUDIO 7
2216302 | ARUP PROJECT LUNA - 3D VIDEO WALKTHROUGH | STUDIO 6
23186 | PROJECT PHOENIX MP | STUDIO 4
23203 | FNG LANCASTER ENCLAVE 2 - PACKAGE 3 | STUDIO 5
23195 | ADMU CENTRAL ADMIN BLDG. | STUDIO 2
2206001 | FERENZO PH 6 AUREO - ADJUSTED BUILDING HEIGHT | STUDIO 5
1817231 | NEW SENATE BUILDING - RDAED FOR 7TH TO 11TH FLOORS (PHASE 2) | STUDIO 5
23234 | FOUR WEST AND FIVE WEST AEROPARK | STUDIO 4
22110 | UST GENSAN SCIENCE BUILDING | STUDIO 1
23199 | CAPE CORAL CONCEPT | STUDIO 1
23243 | 38 PARK AVENUE PHASE 2 | STUDIO 3
23006 | AEON BLEU - TOWER 5 | STUDIO 5
1926104 | PROJECT ELURIA - INTERIOR DOCUMENTATION | STUDIO 5
1826001 | PARKFORD SUITES – 1ST CA EXTENSION | STUDIO 3
24008 | JPMC EMBASSY TOWER 1 TEST FIT | STUDIO 8
24009 | JPMC EMBASSY TOWER 3 TEST FIT | STUDIO 7
2212801 | MYNT OFFICE FIT OUT - BOARDROOM RENOVATION | STUDIO 7
24012 | OKADA MP MSRF0000 | STUDIO 6
24013 | ADB LEVEL 4 | STUDIO 7
23229 | CALUYA MUNICIPAL HALL ID | STUDIO 7
2309703 | AMANI TOWER - TIA | STUDIO 6
23155 | THE FORT REDEVELOPMENT MP | STUDIO 1
1909904 | PROJECT AZUELA - PODIUM RE-PLANNING | STUDIO 3
24001 | THE SERENE ALABANG | STUDIO 3
2107402 | BT PROJECT GENESIS ID & EGD - GUESTROOM TYPES DEV'T | STUDIO 7
2107403 | BT PROJECT GENESIS ID & EGD - RESIDENTIAL UNIT TYPES DEV'T | STUDIO 7
2107404 | BT PROJECT GENESIS ID & EGD - BI-LEVEL PENTHOUSE UNIT DEV'T | STUDIO 7
2107405 | BT PROJECT GENESIS ID & EGD - PREVIOUS ATRIUM FLOORS UNIT DEV'T | STUDIO 7
24021 | BANYAN TREE - GUESTROOM MOCK-UP | STUDIO 7
2309702 | AMANI TOWER – FAÇADE & BUILDING MAINTENANCE UNIT | STUDIO 6
2309704 | AMANI TOWER - SITE SURVEYING | STUDIO 6
1920401 | *BGC WESTGATE PARKING - TUNNEL DESIGN | STUDIO 1
23237 | LANDMARK MANILA BAY - ID | STUDIO 8
24016 | MYNT EGD | STUDIO 9
1926107 | PROJECT ELURIA - BIM ATTENDANCE | STUDIO 5
1926109 | PROJECT ELURIA - RESIDENTIAL FINISHES RENDER | STUDIO 5
2206002 | FHDC PH6 AUREO - ADDITIONAL DETAILED DESIGN PACKAGE | STUDIO 5
24024 | BULIHAN CIRCLE CENTRAL PARK | STUDIO 5
2309706 | AMANI TOWER - LIGHTING DESIGN | STUDIO 6
2309701 | AMANI TOWER - LANDSCAPE | STUDIO 6
1506820 | CALLISTO TOWER 1 - 6TH CA EXTENSION | STUDIO 4
1506821 | CALLISTO TOWER 2 - 6TH CA EXTENSION | STUDIO 4
22137 | PROJECT M | STUDIO 2
2309705 | AMANI TOWER - ACOUSTIC AND SECURITY DESIGN | STUDIO 6
23216 | BWDC RESIDENTIAL TOWER ID | STUDIO 8
2309707 | AMANI TOWER - WIND TUNNEL TESTING | STUDIO 6
1926106 | PROJECT ELURIA - GF, 2F, 9F, AND 10F LAYOUT REVISIONS | STUDIO 5
2308601 | FROSCH IFC - LIGHTING | STUDIO 8
23236 | BENCH HQ - ID BIM | STUDIO 4
1711511 | ONE VERTIS PLAZA - ARCHITECTURAL CA EXTENSION | STUDIO 1
24033 | W SIXTH CONVERSION TEST FIT | STUDIO 3
2213701 | PROJECT M - ADDITIONAL RENDERS | STUDIO 2
2309709 | AMANI TOWER - EDGE CONSULTANCY | STUDIO 6
1817232 | NEW SENATE BUILDING – SENATORS’ OFFICES ID | STUDIO 5

## stages
project_code | stage_name | description | date_start | date_close | is_onhold | U_CoreServices
13042 | Project Initiation | Mobilization | 2013-04-04 | 2013-04-04 | \N | S020
13042 | Schematic Design | Concept/Schematic | 2013-04-04 | 2013-05-31 | \N | S020
13042 | Design Development | \N | 2013-06-01 | 2013-08-31 | \N | S020
13042 | Contract Documentation | \N | 2013-09-01 | 2013-12-20 | \N | S020
13042 | Construction Administration | \N | 2014-01-01 | 2016-01-31 | \N | S020
13056 | Design Development | \N | 2014-06-09 | 2015-01-24 | \N | \N
13056 | Contract Documentation | \N | 2015-01-26 | 2016-07-18 | \N | \N
13056 | Construction Administration | \N | 2015-05-01 | 2018-08-31 | \N | \N
13056 | Project Initiation | \N | 2013-07-09 | 2013-07-09 | \N | \N
13056 | Schematic Design | \N | 2013-07-09 | 2014-06-06 | \N | \N
13058 | Project Initiation | \N | 2013-06-01 | 2013-06-01 | \N | \N
13058 | Schematic Design | \N | 2013-06-06 | 2013-08-30 | \N | \N
13058 | Design Development | \N | 2013-09-03 | 2013-12-16 | \N | \N
13058 | Contract Documentation | \N | 2014-01-10 | 2014-08-20 | \N | \N
13058 | Construction Administration | \N | 2014-08-29 | 2018-07-16 | \N | \N
13089 | Project Initiation | \N | 2013-08-30 | 2013-08-30 | \N | \N
13089 | Schematic Design | \N | 2013-10-15 | 2013-12-14 | \N | \N
13089 | Design Development | \N | 2013-12-15 | 2014-02-01 | \N | \N
13089 | Contract Documentation | \N | 2014-02-02 | 2014-04-02 | \N | \N
13089 | Construction Administration | \N | 2014-07-10 | 2016-01-09 | \N | \N
13113 | Project Initiation | \N | 2014-01-21 | \N | \N | \N
13113 | Planning and Programming | \N | 2014-01-22 | 2014-02-28 | \N | \N
13113 | Contract Documentation | \N | 2014-03-03 | 2017-01-09 | \N | \N
13121 | Design Development | \N | 2014-02-01 | 2014-04-30 | \N | S020
13121 | Contract Documentation | \N | 2014-05-01 | 2014-08-31 | \N | S020
13121 | Construction Administration | \N | 2016-12-01 | 2020-03-31 | \N | S020
13121 | Project Initiation | \N | 2013-12-02 | 2013-12-02 | \N | S020
13121 | Schematic Design | \N | 2014-01-01 | 2014-01-31 | \N | S020
14048 | Schematic Design | \N | 2015-05-30 | \N | \N | \N
14048 | Design Development | \N | 2016-01-01 | \N | \N | \N
14048 | Contract Documentation | \N | 2017-01-01 | \N | \N | \N
14048 | Construction Administration | \N | 2018-01-01 | \N | \N | \N
14048 | Project Initiation | \N | 2014-05-27 | 2014-05-27 | \N | \N
14048 | Final Masterplanning | \N | 2014-05-27 | 2015-05-30 | \N | \N
14098 | Project Initiation | Mobilization | 2016-03-30 | 2016-03-30 | N | S020
14098 | Schematic Design | Concept & Schematic | 2016-04-01 | 2016-08-31 | N | S020
14098 | Design Development | \N | 2016-09-01 | 2017-02-28 | N | S020
14098 | Contract Documentation | \N | 2017-03-01 | 2017-07-31 | N | S020
14098 | Construction Administration | \N | 2017-08-01 | 2018-04-30 | N | S020
14099 | Project Initiation | \N | 2014-10-01 | 2014-10-01 | N | S020
14099 | Conceptual Masterplanning | \N | 2014-10-01 | 2014-11-30 | Y | S020
14099 | Final Masterplanning | \N | 2014-12-01 | 2015-01-30 | N | S020
14101 | Project Initiation | \N | 2015-12-11 | 2015-12-11 | N | S010
14101 | Conceptual Masterplanning | \N | 2015-12-11 | 2016-01-15 | N | S010
14101 | Final Masterplanning | \N | 2016-01-18 | 2016-02-26 | N | S010
14112 | Project Initiation | \N | 2015-07-17 | 2015-07-17 | \N | \N
14112 | Schematic Design | \N | 2015-07-18 | 2015-10-18 | \N | \N
14112 | Design Development | \N | 2015-10-19 | 2015-12-18 | \N | \N
14112 | Contract Documentation | \N | 2015-12-19 | 2016-03-18 | \N | \N
14112 | Construction Administration | \N | 2016-04-01 | 2019-03-31 | \N | \N
15005 | Construction Administration | CA & Post CA | 2015-02-16 | 2017-05-31 | \N | \N
15005 | Design Development | DD & Permit | 2015-03-23 | 2015-06-17 | \N | \N
15005 | Contract Documentation | CD & Tender | 2015-02-17 | 2016-03-04 | \N | \N
15005 | Project Initiation | \N | 2015-02-16 | 2015-02-16 | \N | \N
15005 | Schematic Design | Prelim Design | 2015-02-06 | 2015-05-29 | \N | \N
15019 | Project Initiation | \N | 2012-10-12 | 2015-12-11 | N | S020
15019 | Schematic Design | \N | 2012-10-12 | 2014-07-07 | N | S020
15019 | Design Development | \N | 2013-02-22 | 2014-12-02 | N | S020
15019 | Contract Documentation | \N | 2013-01-28 | 2016-11-15 | N | S020
15019 | Construction Administration | \N | 2016-04-01 | 2018-09-30 | N | S020
15023 | Project Initiation | \N | 2016-11-01 | 2017-06-30 | N | S010
15023 | Conceptual Masterplanning | \N | 2017-07-01 | 2018-02-28 | N | S010
15041 | Data Collection and Analysis | \N | 2015-03-01 | \N | \N | \N
15041 | Project Initiation | \N | 2015-03-15 | 2015-03-15 | \N | S020
15041 | Schematic Design | \N | 2015-03-16 | 2015-05-30 | \N | S020
15041 | Design Development | \N | 2015-06-01 | 2015-11-14 | \N | S020
15041 | Contract Documentation | \N | 2015-11-15 | 2016-04-15 | \N | S020
15041 | Construction Administration | \N | 2016-04-01 | 2016-12-31 | \N | S020
15058 | Concept Design | \N | 2015-05-04 | 2016-03-08 | \N | \N
15058 | Schematic Design | \N | 2015-05-04 | 2016-03-08 | \N | \N
15058 | Design Development | \N | 2015-05-04 | 2016-03-08 | \N | \N
15058 | Contract Documentation | \N | 2015-06-04 | 2016-04-11 | \N | \N
15058 | Construction Administration | \N | 2016-04-01 | 2017-03-31 | \N | \N
15058 | Project Initiation | \N | 2015-05-04 | 2015-05-04 | \N | \N
15070 | Project Initiation | \N | 2015-05-21 | 2015-05-21 | \N | \N
15070 | Final Masterplanning | \N | 2015-05-21 | 2017-08-03 | \N | \N
15086 | Project Initiation | \N | 2015-07-06 | 2015-07-06 | \N | \N
15086 | Contract Documentation | \N | 2015-07-06 | 2016-01-18 | \N | \N
15086 | Construction Administration | \N | 2015-08-04 | 2016-02-29 | \N | \N
15094 | Project Initiation | \N | 2015-08-06 | 2015-08-06 | \N | \N
15094 | Concept Design | \N | 2015-08-06 | 2016-10-17 | \N | \N
15094 | Design Development | \N | 2015-08-17 | 2016-05-05 | \N | \N
15094 | Detailed Design | \N | 2015-08-13 | 2018-01-24 | \N | \N
15094 | Construction Administration | \N | 2016-01-29 | 2018-08-10 | \N | \N
15106 | Contract Documentation | \N | 2016-09-29 | 2017-12-14 | \N | S020
15106 | Project Initiation | \N | 2016-01-13 | 2016-01-13 | \N | S020
15106 | Schematic Design | \N | 2016-01-14 | 2016-09-26 | \N | S020
15106 | Design Development | \N | 2016-09-27 | 2016-09-28 | \N | S020
15106 | Construction Administration | \N | 2017-12-16 | 2018-12-31 | \N | S020
15130 | Others | \N | 2016-04-18 | 2018-04-30 | \N | \N
15130 | Project Initiation | \N | 2016-04-18 | 2016-04-18 | \N | \N
15130 | Schematic Design | Pre-Design/Programming/ Concept/ | 2016-04-18 | 2016-07-15 | \N | \N
15130 | Contract Documentation | Design Development/ Contract Documentation | 2016-07-19 | 2016-12-16 | \N | \N
15130 | Construction Administration | \N | 2017-01-01 | 2018-04-30 | \N | \N
15166 | Project Initiation | \N | 2015-08-12 | 2015-08-12 | \N | \N
15166 | Conceptual Masterplanning | \N | 2015-08-12 | 2015-09-11 | \N | \N
15166 | Final Masterplanning | \N | 2015-10-12 | 2015-11-11 | \N | \N
15173 | Project Initiation | \N | 2016-04-01 | 2016-04-01 | \N | \N
15173 | Contract Documentation | \N | 2016-04-01 | 2016-07-20 | \N | \N
15173 | Construction Administration | \N | 2016-03-31 | 2016-12-05 | \N | \N
16025 | Project Initiation | Stage 2: Milestone 1 | 2016-03-01 | 2016-03-01 | \N | \N
16025 | Concept Design | Stage 1 | 2016-03-01 | 2016-08-31 | \N | \N
16025 | Preliminary Architecture and Engineering Design | Stage 2: MIlestone 2 | 2016-09-01 | 2016-10-31 | \N | \N
16025 | Detailed Architecture and Engineering Design | Stage 2: Milestone 3 | 2016-11-01 | 2016-11-30 | \N | \N
16025 | Detailed Architecture and Engineering Design | Stage 2: Milestone 4 | 2016-12-01 | 2016-12-31 | \N | \N
16025 | For Construction Drawings | Stage 2: MIlestone 5 | 2017-01-01 | 2017-03-31 | \N | \N
16025 | Construction Administration | \N | 2017-04-01 | 2019-03-31 | \N | \N
16030 | Project Initiation | \N | 2016-03-04 | 2016-03-04 | \N | \N
16030 | Contract Documentation | \N | 2016-03-04 | 2016-06-30 | \N | \N
16031 | Project Initiation | \N | 2016-05-31 | 2016-05-31 | \N | \N
16031 | Schematic Design | \N | 2016-05-31 | 2017-05-11 | \N | \N
16031 | Construction Administration | \N | 2016-08-02 | 2018-03-08 | \N | \N
16105 | Project Initiation | Mobilization | 2017-07-21 | 2017-07-21 | \N | S020
16105 | Schematic Design | Concept/ Schematic | 2017-07-24 | 2017-12-20 | \N | S020
16105 | Detailed Design | DD / CD | 2018-01-01 | 2018-02-28 | \N | S020
16105 | Construction Administration | Construction | 2018-03-01 | 2019-02-28 | \N | S020
16137 | Project Initiation | \N | 2017-01-25 | 2017-01-25 | \N | \N
16137 | Detailed Design | \N | 2017-01-25 | 2017-11-20 | \N | \N
16137 | Construction Administration | \N | 2017-04-27 | 2017-11-21 | \N | \N
17022 | Project Initiation | \N | 2017-02-21 | 2017-02-21 | \N | \N
17022 | Schematic Design | Preliminary Design | 2017-02-21 | 2020-02-12 | \N | \N
17022 | Detailed Design | \N | 2017-02-21 | 2020-02-12 | \N | \N
17047 | Construction Administration | \N | 2018-05-01 | 2019-01-31 | \N | \N
17047 | Project Initiation | \N | 2017-02-24 | 2017-02-24 | \N | \N
17047 | Schematic Design | \N | 2017-02-24 | 2017-08-31 | \N | \N
17047 | Contract Documentation | \N | 2017-09-01 | 2018-04-30 | \N | \N
17122 | Conceptual Masterplanning | \N | 2017-05-29 | 2017-07-04 | \N | S010
17122 | Detailed Masterplanning | \N | 2017-09-18 | 2018-09-04 | \N | S010
17122 | Final Masterplanning | \N | 2018-08-08 | 2018-12-15 | \N | S010
17122 | Urban Design Guidelines | \N | 2019-01-06 | 2021-01-31 | \N | S010
17122 | Project Initiation | \N | 2018-04-11 | 2018-04-11 | \N | S010
17126 | Project Initiation | \N | 2017-08-17 | 2017-08-17 | \N | S020
17126 | Schematic Design | \N | 2017-09-01 | 2017-11-30 | \N | S020
17126 | Contract Documentation | 50% | 2017-12-01 | 2018-01-31 | \N | S020
17126 | Contract Documentation | 100% | 2018-02-01 | 2018-04-30 | \N | S020
17126 | Construction Administration | \N | 2018-05-01 | 2019-05-31 | \N | S020
17150 | Construction Administration | \N | 2017-12-21 | \N | Y | \N
17150 | Project Initiation | For Masterplanning | 2017-07-18 | 2017-07-18 | Y | \N
17150 | Schematic Design | For Architecture | 2017-07-18 | 2018-03-08 | Y | \N
17150 | Concept Design | For Masterplanning | 2017-07-18 | 2018-03-08 | Y | \N
17150 | Design Development | For Architecture | 2017-07-18 | \N | Y | \N
17150 | Contract Documentation | For Architecture | 2017-07-18 | \N | Y | \N
17150 | Project Initiation | For Architecture | 2017-07-18 | \N | Y | \N
17153 | Schematic Design | Scope Aborted | 2017-11-17 | 2017-11-17 | Y | \N
17153 | Project Initiation | \N | 2017-11-17 | 2017-11-17 | Y | \N
17153 | Contract Documentation | Scope Aborted | 2017-11-17 | 2017-11-17 | Y | \N
17153 | Construction Administration | Scope Aborted | 2017-11-17 | 2017-11-17 | Y | \N
18068 | Others | \N | 2018-03-13 | 2018-06-22 | \N | \N
18068 | Project Initiation | \N | 2018-03-13 | 2018-03-13 | \N | \N
18068 | Detailed Design | \N | 2018-03-13 | 2018-06-22 | \N | \N
18148 | Project Initiation | \N | 2018-11-19 | 2018-11-19 | \N | S020
18148 | Design Development | \N | 2018-12-01 | 2019-01-31 | N | S020
18148 | Contract Documentation | \N | 2019-02-01 | 2019-03-31 | N | S020
18148 | Schematic Design | from 18148J | 2019-01-01 | 2019-02-28 | N | S020
18148 | Project Initiation | from 18148J | 2019-01-01 | 2019-01-01 | \N | S020
18165 | Project Initiation | \N | 2018-08-09 | 2018-08-09 | \N | \N
18165 | Code Review | \N | 2018-08-09 | 2018-10-22 | \N | \N
18171 | Architecture Test-Fit | \N | 2018-03-08 | 2018-03-08 | Y | \N
18171 | Project Initiation | not in S.O. | 2018-03-08 | 2018-03-08 | Y | \N
18213 | Project Initiation | \N | 2018-10-01 | 2018-10-01 | Y | \N
18213 | Others | \N | 2018-10-01 | 2018-10-01 | Y | \N
18216 | Project Initiation | \N | 2018-10-22 | 2018-10-22 | \N | \N
18216 | Concept Design | schematic design | 2018-10-22 | 2018-10-31 | \N | \N
18216 | Construction Administration | \N | 2018-11-05 | 2018-12-07 | \N | \N
18217 | Test-Fit | \N | 2018-01-01 | 2018-01-01 | Y | \N
18217 | Project Initiation | \N | 2018-01-01 | 2018-01-01 | Y | \N
18229 | Project Initiation | \N | 2018-10-24 | 2018-10-24 | Y | \N
18229 | Schematic Design | \N | 2018-10-24 | 2018-10-24 | Y | \N
18229 | Design Development | \N | 2018-10-24 | 2018-10-24 | Y | \N
18229 | Contract Documentation | \N | 2018-10-24 | 2018-10-24 | Y | \N
18229 | Construction Administration | \N | 2018-10-24 | 2018-10-24 | Y | \N
18235 | Project Initiation | \N | 2018-10-24 | 2018-10-24 | \N | \N
18235 | Final Renderings | \N | 2018-10-24 | 2018-12-19 | \N | \N
18262 | Others | \N | 2019-01-04 | 2019-01-04 | Y | \N
18262 | Project Initiation | \N | 2019-01-04 | 2019-01-04 | Y | \N
18262 | Schematic Design | \N | 2019-01-04 | 2019-01-04 | Y | \N
18262 | Contract Documentation | \N | 2019-01-04 | 2019-01-04 | Y | \N
19040 | Project Initiation | \N | 2019-02-20 | 2019-02-20 | Y | \N
19040 | Schematic Design | \N | 2019-02-20 | 2019-02-20 | Y | \N
19059 | Project Initiation | \N | 2019-01-31 | 2019-01-31 | Y | \N
19087 | Final Renderings | \N | 2019-05-14 | 2019-05-28 | \N | \N
19087 | Project Initiation | \N | 2019-05-14 | 2019-05-14 | \N | \N
19111 | Others | \N | 2019-05-22 | 2019-05-22 | Y | \N
19111 | Project Initiation | \N | 2019-05-22 | 2019-05-22 | Y | \N
19111 | Schematic Design | \N | 2019-05-22 | 2019-05-22 | Y | \N
19111 | Construction Administration | \N | 2019-05-22 | 2019-05-22 | Y | \N
19128 | Final Renderings | \N | 2019-08-01 | 2019-10-07 | \N | \N
19128 | Project Initiation | \N | 2019-07-05 | 2019-07-05 | \N | \N
19128 | Preliminary Renderings | \N | 2019-07-05 | 2019-07-30 | \N | \N
19163 | Preliminary Design | Aborted | 2019-08-01 | 2019-08-01 | Y | \N
19163 | Project Initiation | \N | 2019-08-01 | 2019-08-01 | Y | \N
19174 | Concept Design | \N | 2019-10-14 | 2019-10-14 | Y | \N
19174 | Schematic Design | \N | 2019-10-14 | 2019-10-14 | Y | \N
19174 | Design Development | \N | 2019-10-14 | 2019-10-14 | Y | \N
19174 | Contract Documentation | \N | 2019-10-14 | 2019-10-14 | Y | \N
19174 | Construction Administration | \N | 2019-10-14 | 2019-10-14 | Y | \N
19174 | Project Initiation | \N | 2019-10-14 | 2019-10-14 | Y | \N
19186 | Final Renderings | \N | 2019-08-14 | 2019-08-20 | \N | \N
19186 | Project Initiation | \N | 2019-08-14 | 2019-08-14 | \N | \N
19226 | Final Renderings | \N | 2019-10-14 | 2019-10-24 | \N | \N
19226 | Project Initiation | \N | 2019-07-01 | 2019-07-01 | \N | \N
19226 | Preliminary Renderings | \N | 2019-09-25 | 2019-10-11 | \N | \N
19252 | Preliminary Design | \N | 2020-02-14 | 2020-03-31 | \N | \N
19252 | Project Initiation | \N | 2020-02-14 | 2020-02-14 | \N | \N
19265 | Preliminary Architecture and Engineering Design | architecture only | 2019-12-01 | 2021-08-31 | Y | \N
19265 | Project Initiation | XXX | 2019-12-01 | 2019-12-01 | Y | \N
20004 | Project Initiation | \N | 2020-03-06 | 2020-03-06 | Y | \N
20006 | Project Initiation | \N | 2020-01-09 | 2020-01-09 | Y | \N
20007 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20016 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20016 | Design Development | \N | 2020-01-02 | 2020-01-01 | Y | \N
20018 | Data Collection and Analysis | no time charges | 2020-02-22 | 2020-03-31 | \N | \N
20018 | Contract Documentation | Other Stages - Advance Copy | 2020-03-31 | 2020-06-30 | \N | \N
20018 | Contract Documentation | Other Stages - Printing for OBO | 2021-01-01 | 2021-01-31 | \N | \N
20018 | Others | Other Stages | 2020-02-22 | 2021-01-31 | \N | \N
20018 | Project Initiation | Mobilization | 2020-02-22 | 2020-02-22 | \N | \N
20027 | Nothing Follows | \N | 2020-01-01 | 2020-01-01 | Y | \N
20046 | Development Permit Alteration Plans | \N | 2020-01-01 | 2020-01-01 | Y | \N
20046 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20049 | Concept Design | \N | 2020-01-06 | 2020-01-06 | Y | S020
20049 | Schematic Design | \N | 2020-01-07 | 2020-03-06 | Y | S020
20049 | Design Development | \N | 2020-01-06 | 2020-01-06 | Y | \N
20049 | Contract Documentation | \N | 2020-01-06 | 2020-01-06 | Y | \N
20049 | Construction Administration | \N | 2020-01-06 | 2020-01-06 | Y | \N
20049 | Project Initiation | \N | 2020-01-06 | 2020-01-06 | Y | \N
20050 | Concept Design | \N | 2020-01-01 | 2020-01-01 | Y | S020
20050 | Schematic Design | \N | 2020-01-07 | 2020-01-01 | Y | S020
20050 | Design Development | \N | 2020-01-01 | 2020-01-01 | Y | \N
20050 | Contract Documentation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20050 | Construction Administration | \N | 2020-01-01 | 2020-01-01 | Y | \N
20050 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20051 | Final Renderings | \N | 2020-02-26 | 2020-04-24 | \N | \N
20051 | Project Initiation | \N | 2020-02-26 | 2020-02-26 | \N | \N
20057 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20058 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20063 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20064 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
1309502 | Contract Documentation | Plan Revisions | 2020-03-01 | 2020-03-31 | \N | S020
1309502 | Project Initiation | for deletion | 2020-03-01 | 2020-03-01 | \N | S020
1310203 | Design Development | \N | 2019-05-01 | \N | \N | \N
1310203 | Contract Documentation | \N | 2019-05-01 | \N | \N | \N
1310203 | Construction Administration | \N | 2019-05-01 | 2021-01-31 | \N | \N
1405102 | Project Initiation | \N | 2018-03-21 | 2018-03-21 | \N | \N
1405102 | Contract Documentation | \N | 2018-03-21 | 2018-06-30 | \N | \N
1405102 | Construction Administration | \N | 2018-07-01 | 2021-12-06 | \N | \N
1504101 | Project Initiation | \N | 2015-03-15 | 2015-03-15 | \N | S020
1504101 | Schematic Design | \N | 2015-03-16 | 2015-05-30 | \N | S020
1504101 | Design Development | \N | 2015-06-01 | 2015-11-14 | \N | S020
1504101 | Contract Documentation | \N | 2015-11-15 | 2016-04-15 | \N | S020
1504101 | Construction Administration | \N | 2016-04-01 | 2016-12-31 | Y | S020
1506802 | Construction Administration | ATC for CD | 2018-08-01 | 2019-05-31 | \N | S020
1506802 | Project Initiation | XX | 2018-10-01 | 2018-10-01 | \N | \N
1506802 | Contract Documentation | xx | 2018-08-09 | 2019-05-08 | \N | \N
1506803 | Contract Documentation | XX | 2018-08-13 | 2018-10-02 | \N | \N
1506803 | Project Initiation | XX | 2018-01-10 | 2018-01-10 | \N | \N
1506803 | Construction Administration | ATC FOR CD | 2018-08-01 | 2018-10-31 | \N | S020
1506804 | Contract Documentation | \N | 2018-06-28 | 2018-06-28 | \N | S020
1506804 | Project Initiation | XX | 2019-02-01 | \N | \N | \N
1607302 | Contract Documentation | \N | 2018-03-23 | 2018-05-01 | \N | \N
1607304 | Contract Documentation | \N | 2018-02-12 | 2018-03-26 | \N | \N
1702901 | Design Development | XXX | 2021-01-01 | 2021-01-01 | Y | S020
1702901 | Schematic Design | \N | 2018-01-02 | 2018-04-16 | N | S020
1702901 | Contract Documentation | 100% Combined DD/CD | 2021-08-12 | 2023-03-31 | Y | S020
1702901 | Construction Administration | \N | 2024-05-01 | 2027-04-30 | Y | S020
1702901 | Project Initiation | \N | 2018-01-01 | 2018-01-01 | N | S020
1704401 | Project Initiation | \N | 2018-02-19 | 2018-02-19 | \N | \N
1704401 | Contract Documentation | \N | 2018-02-20 | 2018-03-19 | \N | \N
1705602 | Project Initiation | \N | 2018-04-19 | 2018-04-19 | \N | \N
1705602 | Contract Documentation | \N | 2018-08-01 | 2018-12-05 | \N | \N
1705602 | Construction Administration | \N | 2019-01-04 | 2019-05-22 | \N | \N
1706801 | Contract Documentation | CFA Adjustment | 2018-10-01 | 2018-12-01 | \N | S020
1706801 | Project Initiation | XX | 2018-10-01 | 2018-10-01 | \N | \N
1706801 | Miscellaneous | XX | 2018-10-01 | 2018-12-01 | \N | \N
1706801 | Concept Design | XX | 2018-10-01 | 2018-12-01 | \N | \N
1712201 | Final Masterplanning | \N | 2018-12-17 | 2019-01-30 | \N | S010
1712201 | Project Initiation | \N | 2018-12-17 | 2018-12-17 | \N | S010
1712201 | Construction Administration | NA | 2018-12-06 | 2018-12-06 | \N | \N
1712401 | Schematic Design | \N | 2018-03-13 | 2018-05-15 | \N | \N
1712401 | Project Initiation | \N | 2018-03-13 | 2018-03-13 | \N | \N
1712401 | Design Development | \N | 2018-05-16 | 2018-06-30 | \N | \N
1712402 | Schematic Design | \N | 2018-07-03 | 2019-09-10 | \N | \N
1712402 | Project Initiation | \N | 2018-07-03 | 2018-07-03 | \N | \N
1712405 | Schematic Design | \N | 2018-08-13 | 2018-10-11 | \N | \N
1712405 | Project Initiation | \N | 2018-08-13 | 2018-08-13 | \N | \N
1712406 | Schematic Design | \N | 2019-01-03 | 2019-07-15 | \N | S020
1712406 | Project Initiation | \N | 2019-01-03 | 2019-01-03 | \N | S020
1712406 | Concept Design | \N | 2019-01-03 | 2019-07-15 | \N | S020
1712407 | Schematic Design | \N | 2019-01-05 | 2019-02-05 | \N | \N
1712407 | Design Development | \N | 2019-02-05 | 2020-01-31 | \N | \N
1712407 | Project Initiation | \N | 2019-01-05 | 2019-01-05 | \N | \N
1713101 | Contract Documentation | L Project, MH to 1713105 | 2018-11-01 | 2018-11-01 | \N | \N
1713101 | Project Initiation | L Project, MH to 1713105 | 2018-11-01 | 2018-11-01 | \N | \N
1713101 | Construction Administration | L Project, MH to 1713105 | 2018-11-01 | 2018-11-01 | \N | \N
1720101 | Construction Administration | \N | 2017-01-01 | 2017-01-01 | Y | \N
1720101 | Project Initiation | \N | 2017-01-01 | 2017-01-01 | Y | \N
1722302 | Contract Documentation | \N | 2019-05-26 | 2019-07-25 | N | \N
1800903 | Contract Documentation | \N | 2018-06-19 | 2018-09-14 | \N | S020
1800904 | Construction Administration | \N | 2020-02-01 | 2020-07-31 | \N | S020
1800904 | Project Initiation | XXX | 2020-02-01 | \N | \N | \N
1806902 | Contract Documentation | \N | 2020-01-29 | 2020-12-31 | \N | \N
1806902 | Project Initiation | \N | 2020-01-29 | 2020-01-29 | \N | \N
1813601 | Project Initiation | \N | 2018-11-16 | 2018-11-16 | \N | \N
1813601 | Contract Documentation | \N | 2018-11-16 | 2019-01-23 | \N | \N
1813602 | Project Initiation | \N | 2019-01-23 | 2019-01-23 | \N | \N
1813602 | Others | \N | 2019-01-17 | 2019-06-10 | \N | \N
1912501 | Contract Documentation | \N | 2019-01-01 | 2019-01-01 | Y | \N
1912501 | Construction Administration | \N | 2019-01-01 | 2019-01-01 | Y | \N
1922701 | Schematic Design | \N | 2020-05-27 | 2020-05-27 | Y | \N
1922701 | Project Initiation | \N | 2020-05-27 | 2020-05-27 | Y | \N
1924201 | Design Development | not in scope | 2019-11-20 | \N | \N | \N
1924201 | Contract Documentation | not in scope | 2019-11-20 | \N | \N | \N
1924201 | Construction Administration | not in scope | 2019-11-20 | \N | \N | \N
1924201 | BIM LOD 300 Architecture and Structural Modelling | not in scope | 2019-11-20 | \N | \N | \N
1924201 | BIM LOD 300 MEPF Modelling | not in scope | 2019-11-20 | \N | \N | \N
1924201 | Schematic Design | Only Scope is SD | 2019-11-20 | 2020-02-11 | \N | \N
1924201 | Project Initiation | \N | 2019-11-20 | 2019-11-20 | \N | \N
15057G | BIM LOD 300 Architecture and Structural Modelling | \N | 2018-02-01 | 2018-02-28 | \N | \N
15057G | BIM LOD 300 MEPF Modelling | \N | 2018-03-01 | 2018-04-30 | \N | \N
15057G | Clash Detection and Resolution | \N | 2018-05-01 | 2018-05-31 | \N | \N
15057G | 2D Combined Services Drawings | \N | 2018-06-01 | 2018-07-31 | \N | \N
16010 | Project Initiation | \N | 2016-01-04 | 2016-01-04 | \N | \N
16010 | Schematic Design | \N | 2016-01-04 | 2016-04-15 | \N | \N
16010 | Contract Documentation | \N | 2016-04-18 | 2016-08-19 | \N | \N
16010 | Construction Administration | \N | 2016-08-22 | 2017-07-21 | \N | \N
17131H01 | Construction Administration | \N | 2020-06-01 | 2020-12-31 | \N | S020
17131H01 | Project Initiation | XXX | 2020-06-01 | 2020-06-01 | \N | \N
17145 | Final Masterplanning | \N | 2017-12-12 | \N | \N | \N
17145 | Project Initiation | \N | 2017-12-12 | 2017-12-12 | \N | \N
17145 | Conceptual Masterplanning | \N | 2017-12-12 | \N | \N | \N
17185 | Project Initiation | not is S.O. | 2017-08-25 | 2017-08-25 | \N | S010
17185 | Visioning and Options Generation | \N | 2017-08-25 | 2017-12-22 | \N | S010
17185 | Conceptual Masterplanning | \N | 2018-01-01 | 2018-12-22 | \N | S010
17185 | Final Masterplanning | \N | 2019-01-01 | 2019-09-30 | \N | S010
17212 | Schematic Design | \N | 2019-02-12 | \N | \N | \N
17212 | Project Initiation | \N | 2019-02-12 | 2019-02-12 | \N | \N
17212 | Concept Design | \N | 2019-02-12 | \N | \N | \N
18016J | Design Development | \N | 2019-09-18 | 2019-09-18 | Y | \N
18016J | Project Initiation | \N | 2019-09-18 | 2019-09-18 | Y | \N
18051 | Data Collection and Analysis | \N | 2019-02-26 | 2019-02-26 | Y | \N
18051 | Visioning and Options Generation | \N | 2019-02-26 | 2019-02-26 | Y | \N
18051 | Conceptual Masterplanning | \N | 2019-02-26 | 2019-02-26 | Y | \N
18051 | Final Masterplanning | \N | 2019-02-26 | 2019-02-26 | Y | \N
18051 | Marketing Collaterals | \N | 2019-02-26 | 2019-02-26 | Y | \N
18051 | Others | \N | 2019-02-26 | 2019-02-26 | Y | \N
18051 | Project Initiation | \N | 2019-02-26 | 2019-02-26 | Y | \N
18152 | Project Initiation | Mobi | 2018-07-31 | 2018-07-31 | \N | S010
18152 | Conceptual Masterplanning | Concept MP | 2018-08-01 | 2018-09-30 | \N | S010
18152 | Final Masterplanning | Final MP | 2018-10-01 | 2018-10-31 | \N | S010
18163 | Final Masterplanning | \N | 2018-08-01 | 2018-09-30 | \N | \N
18163 | Others | POST PROJECT | 2018-08-01 | \N | \N | \N
18163 | Project Initiation | \N | 2018-08-01 | 2018-08-01 | \N | S010
18163 | Conceptual Masterplanning | \N | 2018-07-23 | 2018-09-30 | \N | S010
19088 | Preliminary Design | Project Aborted | 2018-08-01 | 2018-08-01 | Y | \N
19088 | Project Initiation | \N | 2018-08-01 | 2018-08-01 | Y | \N
19088 | Detailed Design | \N | 2018-08-01 | 2018-08-01 | Y | \N
19088 | Construction Administration | \N | 2018-08-01 | 2018-08-01 | Y | \N
19144 | Schematic Design | \N | 2019-08-05 | 2019-10-01 | \N | S020
19144 | Project Initiation | \N | 2019-08-05 | \N | \N | S020
19166 | Project Initiation | \N | 2019-07-29 | 2019-07-29 | Y | \N
19198J | Project Initiation | \N | 2019-11-26 | 2019-11-26 | Y | \N
19198J | Preliminary Architecture and Engineering Design | \N | 2019-11-26 | 2019-11-26 | Y | \N
19198J | Detailed Architecture and Engineering Design | \N | 2019-11-26 | 2019-11-26 | Y | \N
19198J | Construction Administration | \N | 2019-11-26 | 2019-11-26 | Y | \N
19265J | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | S030
20096 | Concept Design | \N | 2020-01-01 | 2020-01-01 | Y | \N
20096 | Schematic Design | \N | 2020-01-01 | 2020-01-01 | Y | \N
20096 | Design Development | \N | 2020-01-01 | 2020-01-01 | Y | \N
20096 | Contract Documentation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20096 | Construction Administration | \N | 2020-01-01 | 2020-01-01 | Y | \N
20096 | Others | \N | 2020-01-01 | 2020-01-01 | Y | \N
20096 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
18138 | Design Development | 50% DD/CD | 2018-11-16 | 2019-02-15 | \N | S020
18138 | Contract Documentation | 100% DD/CD | 2019-02-16 | 2019-05-15 | N | S020
18138 | Construction Administration | Tower1 | 2024-01-01 | 2026-12-31 | Y | S020
18138 | Schematic Design | \N | 2018-08-16 | 2018-11-15 | \N | S020
18138 | Construction Administration | Tower2 | 2025-01-01 | 2026-12-31 | Y | S020
18138 | Others | N/A | 2018-08-15 | 2018-08-15 | \N | S020
18138 | Project Initiation | \N | 2018-08-15 | 2018-08-15 | \N | S020
18188 | Contract Documentation | \N | 2019-06-15 | 2019-10-14 | \N | \N
18188 | Construction Administration | \N | 2020-07-01 | 2021-06-30 | \N | \N
18188 | Design Development | \N | 2019-03-15 | 2019-06-14 | \N | \N
18188 | Schematic Design | \N | 2019-01-15 | 2019-03-14 | \N | \N
18188 | Project Initiation | \N | 2019-01-07 | 2019-01-07 | \N | \N
14119 | Contract Documentation | \N | 2017-08-16 | 2017-12-15 | \N | \N
14119 | Construction Administration | \N | 2017-12-16 | 2019-04-30 | \N | \N
14119 | Project Initiation | \N | 2017-04-09 | 2017-04-09 | \N | \N
14119 | Schematic Design | \N | 2017-04-10 | 2017-06-15 | \N | \N
14119 | Design Development | \N | 2017-06-16 | 2017-08-15 | \N | \N
16028 | Contract Documentation | \N | 2018-05-01 | 2018-05-31 | \N | S020
16028 | Construction Administration | \N | 2018-10-01 | 2018-10-01 | \N | S020
16028 | Project Initiation | \N | 2016-02-24 | 2016-02-24 | \N | S020
16028 | Design Development | \N | 2018-04-01 | 2018-04-30 | \N | S020
16028 | Schematic Design | \N | 2016-02-25 | 2016-03-24 | \N | S020
17201 | Contract Documentation | \N | 2017-11-01 | 2018-02-28 | N | \N
17201 | Construction Administration | \N | 2018-03-01 | 2020-02-29 | \N | \N
17201 | Design Development | Incorporated with SD | 2017-10-01 | 2017-10-31 | \N | \N
17201 | Schematic Design | SD/DD | 2017-10-01 | 2017-10-31 | \N | \N
17201 | Project Initiation | \N | 2017-10-01 | 2017-10-01 | \N | \N
16035 | Design Development | \N | 2016-05-16 | 2016-07-15 | \N | S030
16035 | Contract Documentation | \N | 2016-07-16 | 2016-10-15 | \N | S030
16035 | Construction Administration | Start of CS (1)EGD (6 months)ID, LA, Spl Lighting. (12 months)Facade (24 months | 2019-07-01 | 2021-06-30 | \N | S070
16035 | Project Initiation | \N | 2016-01-09 | 2016-01-09 | \N | S030
16035 | Detailed Design | \N | 2018-11-28 | 2018-11-28 | \N | \N
16035 | Schematic Design | \N | 2016-03-16 | 2016-05-15 | \N | S030
16035 | Construction Administration | N/A | 2021-06-30 | 2021-06-30 | \N | \N
16035 | Construction Administration | N/A | 2019-07-01 | 2019-07-01 | \N | \N
16035 | Construction Administration | N/A | 2019-07-01 | 2019-07-01 | \N | \N
18103 | Design Development | \N | 2018-09-10 | 2019-01-09 | \N | S020
18103 | Contract Documentation | \N | 2019-01-10 | 2019-06-09 | \N | S020
18103 | Construction Administration | \N | 2019-09-01 | 2021-08-31 | Y | S020
18103 | Schematic Design | \N | 2018-06-10 | 2018-09-09 | \N | S020
18103 | Project Initiation | \N | 2018-06-09 | 2018-06-09 | \N | S020
17188 | Contract Documentation | N/A | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Construction Administration | AR | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Design Development | N/A | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Project Initiation | N/A | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Schematic Design | N/A | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Preliminary Design | AR | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Detailed Design | AR | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Preliminary Design | ID | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Detailed Design | ID | 2017-09-04 | 2017-09-04 | Y | \N
17188 | Construction Administration | ID | 2017-09-04 | 2017-09-04 | Y | \N
15169 | Contract Documentation | \N | 2017-05-01 | 2017-08-31 | \N | S020
15169 | Construction Administration | \N | 2018-02-01 | 2020-01-31 | \N | S020
15169 | Project Initiation | \N | 2016-01-10 | 2016-01-10 | \N | S020
15169 | Schematic Design | \N | 2017-02-01 | 2017-04-30 | \N | S020
13104 | Contract Documentation | \N | 2015-03-01 | 2015-07-01 | \N | \N
13104 | Construction Administration | \N | 2015-01-01 | 2018-05-31 | \N | \N
13104 | Project Initiation | \N | 2014-08-01 | 2014-08-01 | \N | \N
13104 | Schematic Design | \N | 2014-08-15 | 2014-11-15 | \N | \N
13104 | Design Development | \N | 2014-11-16 | 2015-02-16 | \N | \N
15077 | Contract Documentation | \N | 2016-04-19 | 2016-09-18 | \N | S020
15077 | Construction Administration | \N | 2018-04-01 | 2021-03-31 | \N | S020
15077 | Design Development | \N | 2015-12-19 | 2016-04-18 | \N | S020
15077 | Schematic Design | \N | 2015-08-19 | 2015-11-18 | \N | S020
15077 | Others | \N | 2015-08-18 | 2015-08-18 | \N | S020
15077 | Project Initiation | \N | 2015-08-18 | 2015-08-18 | \N | S020
13111 | Contract Documentation | \N | 2014-06-21 | 2014-10-21 | \N | \N
13111 | Construction Administration | \N | 2016-12-31 | 2019-06-30 | \N | \N
13111 | Project Initiation | \N | 2013-12-04 | 2013-12-04 | \N | \N
13111 | Schematic Design | \N | 2014-01-16 | 2014-03-15 | \N | \N
13111 | Design Development | \N | 2014-03-20 | 2014-06-20 | \N | \N
13111 | Concept Design | \N | 2014-01-15 | 2014-01-15 | \N | \N
14066 | Contract Documentation | \N | 2014-10-09 | 2015-02-09 | \N | \N
14066 | Construction Administration | \N | 2017-09-01 | 2020-02-29 | \N | \N
14066 | Design Development | \N | 2014-03-09 | 2014-06-09 | \N | \N
14066 | Schematic Design | \N | 2014-01-08 | 2014-03-08 | \N | \N
14066 | Project Initiation | \N | 2014-01-07 | 2014-01-07 | \N | \N
16094 | Contract Documentation | N/A | 2018-04-03 | 2018-04-03 | \N | \N
16094 | Construction Administration | Upon Testing and Commissioning Support | 2018-05-23 | 2018-12-22 | \N | \N
16094 | Project Initiation | \N | 2016-10-24 | 2016-10-24 | \N | \N
16094 | Design Development | N/A | 2017-10-06 | 2017-10-06 | \N | \N
16094 | Schematic Design | N/A | 2016-10-24 | 2016-10-24 | \N | \N
16094 | Detailed Design | Upon Completion of Detailed Design & BOQ submission | 2017-10-06 | 2017-12-06 | \N | \N
16094 | Detailed Design | Upon Submittal of Technical Evaluation | 2017-10-06 | 2017-12-06 | \N | \N
16094 | Construction Administration | Upon Project Close-out | 2018-05-23 | 2018-12-22 | \N | \N
16094 | Post Construction Phase | Upon Final Billing and Final Acceptance | 2018-12-31 | 2019-12-01 | \N | \N
16094 | Project Initiation | SMEPF - Upon Signing of Letter of Award/ Notice to Proceed | 2016-10-24 | 2016-10-24 | \N | \N
16094 | Detailed Design | SMEPF - Upon Completion of Detailed Design & BOQ submission | 2017-10-06 | 2017-12-06 | \N | \N
16094 | Detailed Design | SMEPF - Upon Submittal of Technical Evaluation | 2017-10-06 | 2017-12-06 | \N | \N
16094 | Construction Administration | SMEPF - Upon Testing and Commissioning Support | 2018-05-23 | 2018-12-22 | \N | \N
16094 | Construction Administration | SMEPF - Upon Project Close-out | 2018-05-23 | 2018-12-22 | \N | \N
16094 | Post Construction Phase | SMEPF - Upon Final Billing and Final Acceptance | 2018-12-31 | 2019-12-01 | \N | \N
16094 | Project Initiation | QS - Upon Signing of Letter of Award/ Notice to Proceed | 2016-10-24 | 2016-10-24 | \N | \N
16094 | Detailed Design | QS - Upon Completion of Detailed Design & BOQ submission | 2017-10-06 | 2017-10-06 | \N | \N
16094 | Detailed Design | QS - Upon Submittal of Technical Evaluation | 2017-10-06 | 2017-10-06 | \N | \N
16094 | Construction Administration | QS - Upon Testing and Commissioning Support | 2018-05-23 | 2018-12-22 | \N | \N
16094 | Construction Administration | QS - Upon Project Close-out | 2018-05-23 | 2018-12-22 | \N | \N
16094 | Post Construction Phase | QS - Upon Final Billing and Final Acceptance | 2018-12-31 | 2019-12-01 | \N | \N
18034 | Contract Documentation | \N | 2018-10-01 | 2019-02-06 | \N | S020
18034 | Construction Administration | \N | 2019-01-01 | 2020-06-30 | \N | S020
18034 | Design Development | \N | 2018-06-28 | 2018-09-27 | \N | S020
18034 | Schematic Design | \N | 2018-02-28 | 2018-06-27 | \N | S020
18034 | Project Initiation | \N | 2018-01-02 | 2018-01-02 | \N | S020
16107 | Contract Documentation | 100% DD/CD | 2016-04-04 | 2016-09-03 | \N | S020
16107 | Construction Administration | \N | 2018-02-01 | 2020-01-31 | \N | S020
16107 | Design Development | \N | 2016-01-04 | 2016-01-04 | \N | S020
16107 | Schematic Design | \N | 2016-01-04 | 2016-04-03 | \N | S020
16107 | Project Initiation | \N | 2016-01-04 | 2016-01-04 | \N | S020
17115 | Contract Documentation | \N | 2017-08-07 | 2018-01-06 | N | S020
17115 | Construction Administration | \N | 2019-02-01 | 2022-01-31 | N | S020
17115 | Design Development | \N | 2017-04-07 | 2017-08-06 | N | S020
17115 | Schematic Design | \N | 2017-01-07 | 2017-04-06 | N | S020
18059 | Contract Documentation | \N | 2018-08-02 | 2019-01-16 | \N | S020
18059 | Construction Administration | \N | 2019-07-01 | 2020-12-31 | \N | S020
18059 | Design Development | \N | 2018-06-05 | 2018-08-01 | \N | S020
18059 | Schematic Design | \N | 2018-04-05 | 2018-06-04 | \N | S020
18059 | Project Initiation | \N | 2018-04-04 | 2018-04-04 | \N | S020
14055 | Design Development | \N | 2014-06-04 | 2014-10-03 | \N | \N
14055 | Contract Documentation | \N | 2014-10-04 | 2015-03-03 | \N | \N
14055 | Construction Administration | \N | 2016-01-01 | 2018-12-31 | \N | \N
14055 | Project Initiation | \N | 2014-01-11 | 2014-01-11 | \N | \N
14055 | Schematic Design | \N | 2014-02-01 | 2014-05-31 | \N | \N
15069 | Design Development | \N | 2016-05-16 | 2016-10-15 | \N | S020
15069 | Contract Documentation | \N | 2016-10-16 | 2017-03-15 | \N | S020
15069 | Construction Administration | \N | 2018-01-01 | 2020-12-31 | \N | S020
15069 | Schematic Design | \N | 2016-01-31 | 2016-05-15 | \N | S020
15069 | Others | \N | 2020-12-31 | 2020-12-31 | \N | S020
15069 | Project Initiation | \N | 2016-01-03 | 2016-01-03 | \N | S020
16085 | Detailed Design | \N | 2017-08-15 | 2018-01-11 | \N | \N
16085 | Contract Documentation | \N | 2017-04-30 | 2017-04-30 | \N | \N
16085 | Construction Administration | \N | 2019-08-01 | 2020-09-30 | \N | \N
16085 | Schematic Design | \N | 2017-05-15 | 2017-07-14 | \N | \N
16085 | Others | \N | 2017-04-30 | 2017-04-30 | \N | \N
16085 | Project Initiation | \N | 2017-04-30 | 2017-04-30 | \N | \N
14110 | Design Development | \N | 2015-05-01 | 2015-07-31 | \N | \N
14110 | Contract Documentation | \N | 2015-08-01 | 2015-11-30 | \N | \N
14110 | Construction Administration | \N | 2017-09-01 | 2020-10-31 | \N | \N
14110 | Schematic Design | \N | 2015-03-01 | 2015-04-30 | \N | \N
14110 | Project Initiation | \N | 2015-01-07 | 2015-01-07 | \N | \N
16039J | Design Development | \N | 2017-12-31 | 2017-12-31 | \N | S020
16039J | Contract Documentation | Transferred to main project number 16039 | 2018-01-01 | 2018-01-01 | \N | S020
16039J | Construction Administration | Architectural | 2018-05-01 | 2020-08-31 | \N | S020
16039J | Project Initiation | \N | 2017-12-31 | 2017-12-31 | \N | S020
16039J | Schematic Design | \N | 2017-12-31 | 2017-12-31 | \N | S020
19281 | Design Development | N/A | 2019-12-12 | 2019-12-12 | Y | \N
19281 | Contract Documentation | \N | 2019-12-12 | 2019-12-12 | Y | \N
19281 | Construction Administration | N/A | 2019-12-12 | 2020-02-01 | Y | \N
19281 | Project Initiation | N/A | 2019-12-12 | 2019-12-12 | Y | \N
19282 | Design Development | N/A | 2019-12-12 | 2019-12-12 | Y | \N
19282 | Contract Documentation | \N | 2019-12-12 | 2019-12-12 | Y | \N
19282 | Construction Administration | N/A | 2019-12-12 | 2020-02-12 | Y | \N
19282 | Project Initiation | N/A | 2019-12-12 | 2019-12-12 | Y | \N
17029 | Schematic Design | N/A | 2017-01-05 | 2017-01-05 | \N | S020
17029 | Design Development | \N | 2021-01-01 | 2021-03-31 | \N | S020
17029 | Contract Documentation | ABORTED | 2017-01-05 | 2017-01-05 | \N | S020
17029 | Construction Administration | ABORTED | 2017-01-05 | 2017-01-05 | \N | S020
17029 | Others | ABORTED | 2017-01-05 | 2017-01-05 | \N | S020
17029 | Project Initiation | \N | 2017-01-01 | 2017-01-01 | \N | S020
17223 | Design Development | \N | 2017-04-04 | 2018-01-03 | N | S020
17223 | Contract Documentation | \N | 2018-01-04 | 2018-06-03 | N | S020
17223 | Construction Administration | \N | 2020-06-01 | 2023-05-31 | N | S020
17223 | Schematic Design | \N | 2017-01-04 | 2017-04-03 | N | S020
17223 | Project Initiation | \N | 2017-01-03 | 2017-01-03 | \N | S020
18123 | Schematic Design | \N | 2018-10-01 | 2019-04-30 | N | \N
18123 | Design Development | \N | 2023-01-01 | 2023-04-30 | Y | \N
18123 | Contract Documentation | \N | 2023-05-01 | 2023-09-30 | Y | \N
18123 | Construction Administration | \N | 2023-10-01 | 2028-09-30 | Y | \N
18123 | Concept Design | \N | 2018-09-13 | 2018-09-13 | N | \N
18123 | Project Initiation | \N | 2018-09-13 | 2018-09-13 | \N | \N
18060 | Design Development | \N | 2018-10-01 | 2018-11-30 | \N | S020
18060 | Contract Documentation | \N | 2018-12-01 | 2019-10-31 | N | S020
18060 | Construction Administration | \N | 2024-05-01 | 2027-04-30 | Y | S020
18060 | Schematic Design | \N | 2018-08-01 | 2018-09-30 | \N | S020
18060 | Project Initiation | \N | 2018-01-08 | 2018-01-08 | \N | S020
19080 | Schematic Design | \N | 2019-11-01 | 2020-01-31 | N | S020
19080 | Design Development | \N | 2020-09-01 | 2021-02-28 | N | S020
19080 | Contract Documentation | \N | 2021-05-11 | 2024-04-15 | N | S020
19080 | Construction Administration | \N | 2024-05-01 | 2027-04-30 | N | S020
19080 | Project Initiation | \N | 2019-10-31 | 2019-10-31 | N | S020
19227 | Schematic Design | \N | 2019-12-15 | 2020-02-14 | N | S020
19227 | Design Development | \N | 2020-09-01 | 2020-11-30 | N | S020
19227 | Contract Documentation | \N | 2020-12-01 | 2021-02-28 | N | S020
19227 | Construction Administration | \N | 2021-11-01 | 2023-10-31 | N | S020
19227 | Concept Design | N/A | 2019-12-14 | 2019-12-14 | Y | \N
19227 | Project Initiation | \N | 2019-10-14 | 2019-10-14 | N | S020
19227 | Project Initiation | BIM | 2019-10-14 | 2019-10-14 | N | S060
19227 | Schematic Design | BIM | 2021-10-01 | 2021-10-31 | N | S060
19227 | Design Development | BIM | 2021-11-01 | 2021-11-30 | N | S060
19227 | Contract Documentation | BIM | 2021-12-01 | 2023-09-30 | N | S060
19180 | Schematic Design | \N | 2019-07-11 | 2020-11-15 | \N | S020
19180 | Design Development | Not Part of Contract | 2021-04-01 | 2021-04-01 | \N | S020
19180 | Contract Documentation | Not Part of Contract | 2021-04-01 | 2021-04-01 | \N | S020
19180 | Construction Administration | Not Part of Contract | 2021-04-01 | 2021-04-01 | \N | S020
19180 | Project Initiation | \N | 2019-07-11 | 2019-07-11 | \N | S020
18260 | Contract Documentation | \N | 2019-09-06 | 2020-01-05 | N | S020
18260 | Construction Administration | \N | 2021-01-01 | 2023-12-31 | N | S020
18260 | Design Development | \N | 2019-05-06 | 2019-09-05 | N | S020
18260 | Schematic Design | \N | 2019-01-06 | 2019-05-05 | N | S020
18260 | Project Initiation | \N | 2019-01-05 | 2019-01-05 | N | S020
19065 | Contract Documentation | \N | 2019-09-02 | 2019-11-01 | \N | S020
19065 | Construction Administration | \N | 2021-06-01 | 2022-05-31 | \N | S020
19065 | Design Development | \N | 2019-07-02 | 2019-09-01 | \N | S020
19065 | Schematic Design | \N | 2019-05-02 | 2019-07-01 | \N | S020
19065 | Project Initiation | \N | 2019-05-01 | 2019-05-01 | \N | S020
19061 | Schematic Design | \N | 2019-10-01 | 2022-09-30 | Y | \N
19061 | Design Development | \N | 2022-10-01 | 2022-12-31 | Y | \N
19061 | Contract Documentation | \N | 2023-01-01 | 2023-04-30 | Y | \N
19061 | Construction Administration | \N | 2023-09-01 | 2026-08-31 | Y | \N
19061 | Project Initiation | \N | 2019-07-03 | 2019-07-03 | N | \N
19061 | Project Initiation | \N | 2019-07-03 | 2019-07-03 | N | \N
19061 | Schematic Design | \N | 2019-10-01 | 2022-09-30 | Y | \N
19061 | Design Development | \N | 2022-10-01 | 2022-12-31 | Y | \N
19061 | Contract Documentation | \N | 2023-01-01 | 2023-04-30 | Y | \N
19061 | Construction Administration | \N | 2023-09-01 | 2026-08-31 | Y | \N
19061 | Project Initiation | \N | 2019-07-03 | 2019-07-03 | N | \N
19061 | Schematic Design | \N | 2019-10-01 | 2022-09-30 | Y | \N
19061 | Others | \N | 2019-07-03 | 2019-08-02 | N | \N
19061 | Project Initiation | \N | 2019-07-03 | 2019-07-03 | N | \N
19061 | Final Renderings | \N | 2019-07-03 | 2019-07-03 | N | \N
19061 | Final Renderings | \N | 2019-07-03 | 2019-07-03 | N | \N
19061 | Final Renderings | \N | 2019-07-03 | 2019-07-03 | N | \N
19061 | Animation | \N | 2019-07-03 | 2019-07-03 | N | \N
19023 | Design Development | \N | 2019-06-15 | 2019-10-14 | N | S020
19023 | Contract Documentation | \N | 2019-10-15 | 2020-02-14 | N | S020
19023 | Construction Administration | \N | 2019-10-01 | 2023-09-30 | N | S020
19023 | Project Initiation | \N | 2019-06-03 | 2019-06-03 | N | S020
19068 | Schematic Design | Concept/ SD | 2019-07-31 | 2020-02-28 | N | \N
19068 | Design Development | \N | 2023-01-01 | 2023-05-31 | N | \N
19068 | Contract Documentation | \N | 2023-06-01 | 2023-11-30 | N | \N
19068 | Construction Administration | \N | 2024-01-01 | 2026-12-31 | N | \N
19068 | Concept Design | N/A | 2019-07-31 | 2019-07-31 | \N | \N
19068 | Project Initiation | N/A | 2019-07-30 | 2019-07-30 | \N | \N
19099 | Schematic Design | \N | 2019-07-25 | 2019-10-24 | N | S020
19099 | Design Development | \N | 2020-09-17 | 2021-02-16 | N | S020
19099 | Contract Documentation | ON HOLD | 2021-07-03 | 2024-03-31 | Y | S020
19099 | Construction Administration | ON HOLD | 2024-05-01 | 2027-04-30 | Y | S020
19099 | Project Initiation | \N | 2019-07-24 | 2019-07-24 | N | S020
14051 | Construction Administration | \N | 2016-07-01 | 2019-10-31 | \N | \N
14051 | Project Initiation | \N | 2014-06-11 | 2014-06-11 | \N | \N
14051 | Contract Documentation | \N | 2016-01-15 | 2016-05-14 | \N | \N
14051 | Design Development | \N | 2015-04-15 | 2015-07-14 | \N | \N
14051 | Schematic Design | \N | 2014-06-15 | 2014-08-14 | \N | \N
13004 | Contract Documentation | \N | 2013-12-01 | 2014-07-31 | N | S020
13004 | Construction Administration | \N | 2018-10-01 | 2024-09-30 | N | S020
13004 | Design Development | \N | 2013-08-01 | 2013-11-30 | N | S020
13004 | Schematic Design | \N | 2013-02-01 | 2013-07-31 | N | S020
13004 | Others | \N | 2017-08-01 | 2018-02-28 | N | S020
13004 | Project Initiation | \N | 2013-01-08 | 2013-01-08 | N | S020
18232 | Schematic Design | \N | 2020-08-31 | 2020-08-31 | Y | \N
18232 | Design Development | \N | 2020-08-31 | 2020-08-31 | Y | \N
18232 | Contract Documentation | \N | 2020-08-31 | 2020-08-31 | Y | \N
18232 | Construction Administration | \N | 2020-08-31 | 2020-08-31 | Y | \N
18108 | Design Development | \N | 2018-04-01 | 2018-04-01 | Y | \N
18108 | Contract Documentation | \N | 2018-04-01 | 2018-04-01 | Y | \N
18108 | Construction Administration | \N | 2018-04-01 | 2018-04-01 | Y | \N
18108 | Contract Documentation | \N | 2018-04-01 | 2018-04-01 | Y | \N
19109 | Schematic Design | \N | 2020-08-31 | 2020-08-31 | Y | \N
19109 | Design Development | \N | 2020-08-31 | 2020-08-31 | Y | \N
19109 | Contract Documentation | \N | 2020-08-31 | 2020-08-31 | Y | \N
19109 | Construction Administration | \N | 2020-08-31 | 2020-08-31 | Y | \N
1200406 | Construction Administration | \N | 2017-02-01 | 2019-03-31 | \N | \N
1200406 | Project Initiation | XX | 2017-02-01 | 2017-02-01 | \N | \N
1200406 | Contract Documentation | XX | 2017-02-01 | 2017-02-01 | \N | \N
13029 | Construction Administration | \N | 2016-06-01 | 2020-05-31 | N | S020
13029 | Contract Documentation | \N | 2013-12-01 | 2015-12-31 | N | S020
13029 | Design Development | \N | 2013-09-01 | 2013-11-30 | N | S020
13029 | Schematic Design | \N | 2013-03-01 | 2013-08-31 | N | S020
13029 | Others | Post Project | 2013-03-01 | 2020-03-31 | Y | S020
13029 | Project Initiation | \N | 2013-03-01 | 2013-03-01 | N | S020
13063 | Construction Administration | \N | 2015-05-01 | 2018-08-31 | \N | \N
13063 | Project Initiation | \N | 2013-07-04 | 2013-07-04 | \N | \N
13063 | Schematic Design | \N | 2013-07-04 | 2013-10-03 | \N | \N
13063 | Design Development | \N | 2013-10-04 | 2014-02-03 | \N | \N
13063 | Contract Documentation | \N | 2014-02-04 | 2014-07-03 | \N | \N
14012 | Construction Administration | \N | 2015-02-17 | 2019-11-20 | \N | S020
14012 | Project Initiation | \N | 2014-02-13 | 2014-02-13 | \N | S020
14012 | Concept Design | \N | 2014-02-13 | 2016-01-26 | \N | S020
14012 | Schematic Design | \N | 2014-02-13 | 2016-01-26 | \N | S020
14012 | Design Development | \N | 2014-10-27 | 2017-02-02 | \N | S020
14012 | Contract Documentation | \N | 2014-10-23 | 2019-01-07 | \N | S020
1401206 | Construction Administration | \N | 2019-06-03 | 2019-11-29 | \N | \N
1401206 | Project Initiation | \N | 2019-06-03 | 2019-06-03 | \N | \N
14032 | Construction Administration | RETAIL & TOWER 1 | 2020-01-01 | 2024-05-31 | N | S020
14032 | BIM LOD 300 Architecture and Structural Modelling | ON HOLD: A/R MEPFS (TOWER 3 TYPICAL FLOOR BIM) | 2020-10-22 | 2022-12-31 | Y | S020
14032 | BIM LOD 300 MEPF Modelling | AR/MEPFS ( RETAIL BIM) - REFER TO VO -06 | 2018-01-01 | 2020-10-22 | N | S020
14032 | 2D Combined Services Drawings | not in S.O. | 2018-01-01 | \N | N | S020
14032 | Others | not in S.O. | 2014-01-01 | \N | \N | S020
14032 | Concept Design | not in S.O. | 2014-01-01 | \N | \N | S020
14032 | Schematic Design | \N | 2015-01-01 | 2016-01-04 | N | S020
14032 | Design Development | not in S.O. | 2015-01-01 | \N | \N | S020
14032 | Contract Documentation | \N | 2015-01-01 | 2021-01-02 | N | S020
14032 | Tender | not in S.O. | 2019-01-01 | \N | \N | S020
14032 | Project Initiation | \N | 2014-06-25 | 2014-06-25 | N | S020
14032 | Construction Administration | TOWERS 2 & 4 | 2020-01-01 | 2022-12-31 | N | S020
14032 | Construction Administration | TOWER 3 | 2020-01-01 | 2022-12-31 | N | S020
1405101 | Construction Administration | \N | 2018-01-19 | 2018-01-19 | \N | S020
1405101 | Project Initiation | \N | 2018-01-19 | 2018-01-19 | \N | S020
1405101 | Contract Documentation | \N | 2018-01-19 | 2019-06-01 | \N | S020
1405101 | Design Development | \N | 2018-01-19 | 2018-01-19 | \N | S020
14087 | Construction Administration | \N | 2017-01-01 | 2018-06-30 | \N | \N
14087 | Project Initiation | \N | 2014-07-21 | 2014-07-21 | \N | \N
14087 | Contract Documentation | \N | 2015-09-03 | 2016-02-15 | \N | \N
14087 | Design Development | \N | 2014-10-24 | 2015-09-02 | \N | \N
14087 | Schematic Design | \N | 2014-07-21 | 2014-10-03 | \N | \N
14093 | Construction Administration | \N | 2016-09-01 | 2018-08-31 | \N | \N
14093 | Project Initiation | \N | 2014-08-07 | 2014-08-07 | \N | \N
14093 | Contract Documentation | \N | 2015-01-08 | 2015-05-07 | \N | \N
14093 | Design Development | \N | 2014-10-08 | 2015-01-07 | \N | \N
14093 | Schematic Design | \N | 2014-08-08 | 2014-10-07 | \N | \N
15110 | Construction Administration | \N | 2017-08-01 | 2019-11-29 | \N | \N
15110 | Schematic Design | \N | 2015-05-14 | 2016-07-25 | \N | \N
15110 | Contract Documentation | \N | 2015-04-21 | 2018-06-22 | \N | \N
15110 | Project Initiation | \N | 2015-04-20 | 2015-04-20 | \N | \N
\N | Construction Administration | \N | 2015-03-01 | \N | \N | \N
\N | Construction Administration | \N | 2015-03-01 | \N | \N | \N
13107 | Construction Administration | \N | 2015-08-01 | 2019-08-01 | \N | \N
13107 | Project Initiation | \N | 2013-07-09 | 2013-07-09 | \N | \N
13107 | Schematic Design | \N | 2013-07-10 | 2013-09-30 | \N | \N
13107 | Design Development | \N | 2014-02-24 | 2014-08-31 | \N | \N
13107 | Contract Documentation | \N | 2014-09-01 | 2015-01-15 | \N | \N
13107 | Construction Administration | \N | 2015-08-01 | 2015-08-01 | \N | \N
15118 | Design Development | MALL Phase 1&2 | 2016-01-01 | 2018-03-31 | N | S020
15118 | Contract Documentation | MALL Phase 1&2 | 2017-01-01 | 2022-01-31 | Y | S020
15118 | Construction Administration | MALL Phase 1 | 2017-01-01 | 2019-12-31 | N | S020
15118 | Conceptual Masterplanning | - - don't link - - | 2015-12-16 | 2015-12-16 | \N | \N
15118 | Concept Design | - - don't link - - | 2015-12-16 | 2015-12-16 | \N | \N
15118 | Schematic Design | MALL Phase 1,2 & 3 | 2016-04-01 | 2016-05-31 | \N | S020
15118 | Post Construction Phase | not linked (retention tagged to CA Stage Mall) | 2022-12-16 | 2022-12-16 | Y | \N
15118 | Design Development | - - don't link - - | 2015-12-16 | 2015-12-16 | N | \N
15118 | Contract Documentation | - - don't link - - | 2015-12-16 | 2015-12-16 | N | \N
15118 | Construction Administration | MALL Phase 2 | 2023-01-01 | 2023-12-31 | Y | S020
15118 | Design Development | MALL Phase 3 | 2018-01-01 | 2022-03-31 | Y | S020
15118 | Contract Documentation | MALL Phase 3 | 2018-04-01 | 2022-06-30 | Y | S020
15118 | Construction Administration | - - don't link - - Mall Ph3 wrong charging | 2015-12-16 | 2015-12-16 | N | \N
15118 | Project Initiation | MALL Phase 1,2 & 3 | 2015-12-16 | 2015-12-16 | \N | S020
15118 | Project Initiation | BPO | 2015-12-16 | 2015-12-16 | \N | S020
15118 | Schematic Design | BPO | 2016-06-01 | 2016-07-31 | \N | S020
15118 | Design Development | BPO | 2018-04-01 | 2022-07-31 | Y | S020
15118 | Contract Documentation | BPO | 2019-02-01 | 2022-06-30 | Y | S020
15118 | Construction Administration | BPO including retention | 2023-01-01 | 2024-08-31 | Y | S020
15118 | Post Construction Phase | not linked (retention tagged to CA stage BPO) | 2024-09-01 | 2024-09-01 | Y | \N
15118 | Project Initiation | Hotel | 2015-12-16 | 2015-12-16 | \N | S020
15118 | Schematic Design | Hotel | 2016-08-01 | 2016-09-30 | \N | S020
15118 | Design Development | Hotel | 2018-06-01 | 2022-09-30 | Y | S020
15118 | Contract Documentation | Hotel | 2019-07-01 | 2022-11-30 | Y | S020
15118 | Construction Administration | - - don't link - - Hotel wrong charging | 2015-12-16 | 2015-12-16 | Y | \N
15118 | Post Construction Phase | not linked (retention tagged to CA stage Hotel) | 2025-12-01 | 2025-12-01 | Y | \N
15118 | Construction Administration | Mall Phase 3 including retention for Mall | 2023-01-01 | 2023-12-31 | Y | S020
15118 | Construction Administration | Hotel including retention | 2024-09-01 | 2025-11-30 | Y | S020
15040 | Construction Administration | \N | 2018-08-01 | 2018-12-31 | N | S020
15040 | Project Initiation | Mobilization | 2015-07-01 | 2015-07-01 | N | S020
15040 | Schematic Design | Schematic & Conceptual MasterPlanning / | 2015-07-01 | 2016-07-31 | N | S020
15040 | Contract Documentation | Design Development & Contract Documantation | 2016-08-01 | 2018-07-31 | N | S020
15146 | Construction Administration | \N | 2020-07-01 | 2020-12-31 | \N | \N
15146 | Concept Design | \N | 2016-09-01 | 2016-09-01 | \N | \N
15146 | Schematic Design | \N | 2016-09-01 | 2017-02-28 | \N | \N
15146 | Design Development | \N | 2017-03-01 | 2017-08-31 | \N | \N
15146 | Contract Documentation | \N | 2017-09-01 | 2018-02-28 | \N | \N
15146 | Others | \N | 2016-09-01 | 2016-09-01 | \N | \N
15146 | Project Initiation | \N | 2016-09-01 | 2016-09-01 | \N | \N
16002 | Concept Design | \N | 2016-05-03 | 2018-11-15 | \N | \N
16002 | Project Initiation | \N | 2016-05-02 | \N | \N | \N
16002 | Concept Design | Architectural Pre-Design Phase | 2016-01-04 | 2016-05-19 | \N | \N
16016 | Concept Design | Schematic Design | 2017-07-01 | 2017-08-15 | \N | S020
16016 | Project Initiation | Mobilization | 2017-07-01 | 2017-07-01 | \N | S020
16016 | Contract Documentation | Contract Documentation | 2017-08-16 | 2017-09-30 | \N | S020
16016 | Construction Administration | Construction Administration | 2017-10-01 | 2018-02-14 | \N | S020
16017 | Construction Administration | Parking and Office Tower | 2020-06-01 | 2021-05-31 | N | S020
16017 | Construction Administration | Chewee Retail (partial 22) | 2018-08-01 | 2020-05-31 | N | S020
16017 | Construction Administration | Chewee ID | 2024-01-01 | 2024-03-31 | N | S030
16017 | Tender | not included XXXX | 2016-01-01 | 2016-01-01 | Y | S020
16017 | BIM LOD 300 MEPF Modelling | not included XXXXX | 2016-01-01 | 2016-01-01 | Y | S020
16017 | Contract Documentation | Contract Documents | 2016-01-01 | 2017-01-15 | N | S020
16017 | Project Initiation | Mobilization | 2016-01-01 | 2016-01-01 | Y | S020
16017 | Construction Administration | Chewee Retail (remaining 2 months) | 2023-06-01 | 2023-07-31 | N | S020
16019 | Construction Administration | \N | 2016-07-01 | 2021-02-28 | N | S020
16019 | Design Development | not in S.O. | 2016-01-10 | 2016-01-10 | Y | S020
16019 | Contract Documentation | \N | 2016-01-02 | 2019-01-07 | N | S020
16019 | Tender | not in S.O. | 2016-01-10 | 2016-01-10 | Y | S020
16019 | BIM LOD 300 MEPF Modelling | not in S.O. | 2016-01-10 | 2016-01-10 | Y | S020
16019 | Project Initiation | not in S.O. | 2016-01-10 | 2016-01-10 | Y | S020
16019 | Construction Administration | \N | 2023-06-01 | 2023-10-31 | N | S030
16028J | Construction Administration | \N | 2018-10-01 | 2020-03-31 | \N | S020
16028J | Schematic Design | N/A | 2018-03-31 | 2018-03-31 | \N | S020
16028J | Design Development | N/A | 2018-03-31 | 2018-03-31 | \N | S020
16028J | Contract Documentation | \N | 2018-04-01 | 2018-05-31 | \N | S020
16028J | Project Initiation | \N | 2018-03-30 | 2018-03-30 | \N | S020
16037 | Schematic Design | \N | 2016-04-01 | 2016-07-29 | \N | \N
16037 | Design Development | \N | 2016-08-01 | 2016-10-31 | \N | \N
16037 | Contract Documentation | \N | 2016-11-01 | 2018-01-08 | \N | \N
16037 | Construction Administration | \N | 2019-08-01 | 2020-07-31 | \N | \N
16044 | Construction Administration | \N | 2017-08-01 | 2017-08-01 | Y | \N
16044 | Project Initiation | \N | 2017-08-01 | 2017-08-01 | Y | \N
16045 | Construction Administration | \N | 2016-10-01 | 2016-10-01 | Y | \N
16045 | Project Initiation | \N | 2016-10-01 | 2016-10-01 | Y | \N
16052 | Project Initiation | \N | 2016-04-05 | 2016-04-05 | \N | \N
16052 | Detailed Design | \N | 2016-09-02 | 2018-10-25 | \N | \N
16052 | Concept Design | \N | 2016-04-29 | 2017-08-14 | \N | \N
16052 | Construction Administration | \N | 2016-12-05 | 2019-07-24 | \N | \N
1605402 | Project Initiation | \N | 2018-04-24 | \N | \N | \N
1605402 | Test-Fit | \N | 2018-04-24 | 2018-06-15 | \N | \N
16060 | Construction Administration | \N | 2018-10-01 | 2020-09-30 | \N | S020
16060 | Others | \N | 2017-12-01 | 2021-03-23 | \N | S020
16060 | Concept Design | \N | 2017-12-01 | 2017-12-31 | \N | S020
16060 | Schematic Design | \N | 2018-01-01 | 2018-03-31 | \N | S020
16060 | Design Development | \N | 2018-04-01 | 2018-06-30 | \N | S020
16060 | Contract Documentation | \N | 2018-07-01 | 2018-09-30 | \N | S020
16060 | Project Initiation | Mobilization | 2017-12-01 | 2017-12-01 | \N | S020
16070 | Construction Administration | \N | 2019-08-01 | 2020-07-31 | \N | \N
16070 | Contract Documentation | CD: Upon completion of Bidding Plans | 2018-06-25 | 2018-08-23 | \N | \N
16070 | Design Development | \N | 2018-06-25 | 2018-09-20 | \N | \N
16070 | Schematic Design | \N | 2016-06-30 | 2018-06-25 | \N | \N
16070 | Project Initiation | \N | 2016-06-30 | 2016-06-30 | \N | \N
16070 | Contract Documentation | CD: Upon completion of Contract Documents Drawings | 2018-08-23 | 2018-08-23 | \N | \N
16070 | Contract Documentation | CD: After awarding of Contracts | 2019-06-03 | 2019-06-03 | \N | \N
16070 | Others | Retention | 2022-12-15 | 2022-12-15 | \N | \N
16073 | Construction Administration | \N | 2019-03-01 | 2023-10-31 | N | S020
16073 | Schematic Design | \N | 2017-01-01 | 2017-05-12 | N | S020
16073 | Design Development | \N | 2017-05-13 | 2018-02-07 | N | S020
16073 | Contract Documentation | \N | 2018-02-08 | 2018-08-28 | N | S020
16073 | Project Initiation | \N | 2017-01-01 | 2017-01-01 | N | S020
1607301 | Contract Documentation | \N | 2018-01-18 | 2018-08-01 | \N | \N
1607305 | Contract Documentation | \N | 2018-04-02 | 2018-05-15 | \N | \N
16073A | Concept Design | Upon completion of Marketing Plans + CTS Plans | 2017-04-01 | \N | N | \N
16073A | Project Initiation | \N | 2017-04-01 | \N | N | \N
16073A1 | Concept Design | \N | 2017-04-01 | \N | \N | \N
16073A1 | Project Initiation | \N | 2017-04-01 | 2017-04-01 | \N | \N
16073A1 | Design Development | Upon Completion of CTS Plans | 2018-09-07 | 2020-05-04 | \N | \N
16073A1 | Design Development | Upon Completion of Marketing Plans | 2018-03-15 | 2018-05-02 | \N | \N
16073A2 | Design Development | Upon Completion of Marketing Plans | 2019-01-01 | 2019-06-06 | \N | \N
16073A2 | Design Development | Upon Completion of CTS Plans | 2019-01-01 | 2019-06-06 | \N | \N
16073A2 | Project Initiation | \N | 2019-01-01 | 2019-01-01 | \N | \N
16077 | Project Initiation | \N | 2016-06-21 | 2016-06-21 | \N | \N
16077 | Concept Design | Preliminary Conceptual Masterplan | 2016-06-21 | 2016-08-05 | \N | \N
16097 | Construction Administration | \N | 2018-07-01 | 2018-07-01 | \N | S020
16097 | Project Initiation | \N | 2017-10-01 | 2017-10-01 | \N | S020
16097 | Schematic Design | Concept & Schematic / Conceptual Masterplanning | 2017-10-01 | 2017-12-31 | \N | S020
16097 | Design Development | \N | 2018-01-01 | 2018-03-31 | \N | S020
16097 | Contract Documentation | \N | 2018-04-01 | 2018-06-30 | \N | S020
16109 | Construction Administration | \N | 2017-09-01 | 2018-06-30 | \N | S020
16109 | Project Initiation | \N | 2016-09-01 | 2016-09-01 | \N | S020
16109 | Conceptual Masterplanning | not in S.O | 2016-09-01 | 2016-12-20 | \N | S020
16109 | Schematic Design | \N | 2017-01-01 | 2017-03-31 | \N | S020
16109 | Design Development | \N | 2017-04-01 | 2017-06-30 | \N | S020
16109 | Contract Documentation | \N | 2017-07-01 | 2017-08-30 | \N | S020
16117 | Design Development | \N | 2017-02-01 | 2017-09-29 | N | \N
16117 | Project Initiation | \N | 2016-09-27 | 2016-09-27 | \N | \N
16117 | Schematic Design | \N | 2016-09-27 | 2017-01-31 | \N | \N
16117 | Contract Documentation | \N | 2016-11-01 | \N | N | \N
16117 | Construction Administration | \N | 2016-11-01 | \N | N | \N
16124 | Construction Administration | Phase 1 | 2019-09-01 | 2021-12-31 | N | S020
16124 | BIM LOD 300 MEPF Modelling | 100% MEPF Modeling Phase 1 | 2018-09-04 | 2019-04-01 | N | S060
16124 | Schematic Design | Phase 1 | 2016-12-01 | 2017-10-03 | \N | S020
16124 | Contract Documentation | 50% CD Phase 1 | 2017-10-04 | 2018-09-03 | \N | S020
16124 | Contract Documentation | 100% CD Phase 1 | 2018-09-04 | 2018-12-07 | \N | \N
16124 | Project Initiation | Phase 1 | 2016-12-01 | 2016-12-01 | \N | S020
16124 | Project Initiation | Phase 2 | 2016-12-01 | 2016-12-01 | \N | S020
16124 | Schematic Design | Phase 2 | 2016-12-01 | 2017-10-03 | \N | \N
16124 | Contract Documentation | 50% CD Phase 2 | 2017-10-04 | 2018-09-03 | \N | \N
16124 | Contract Documentation | 100% CD Phase 2 | 2018-09-04 | 2018-12-07 | \N | \N
16124 | Construction Administration | Phase 2 | 2025-01-01 | 2025-12-31 | Y | S020
16124 | BIM LOD 300 MEPF Modelling | 100% MEPF Modeling Phase 2 | 2018-08-27 | 2019-04-01 | N | \N
16124 | BIM LOD 300 Architecture and Structural Modelling | 50% MEPF Modeling Phase 1 | 2017-10-19 | 2019-04-01 | \N | \N
16124 | BIM LOD 300 Architecture and Structural Modelling | 50% MEPF Modeling Phase 2 | 2017-10-19 | 2019-04-01 | \N | \N
16124 | Clash Detection and Resolution | Phase 1 | 2018-09-06 | 2019-04-01 | \N | \N
16124 | Clash Detection and Resolution | Phase 2 | 2018-09-06 | 2019-04-01 | \N | \N
16124 | 2D Combined Services Drawings | Phase 1 | 2019-09-19 | 2020-08-01 | N | \N
16124 | 2D Combined Services Drawings | Phase 2 | 2022-02-01 | 2023-01-04 | N | S060
16124E | Final Renderings | \N | 2019-03-01 | 2019-06-15 | \N | \N
16124E | Project Initiation | \N | 2019-03-01 | 2019-03-01 | \N | \N
16135 | Others | not in SO | 2018-10-01 | 2018-10-01 | \N | S020
16135 | Concept Design | not in SO | 2018-10-01 | 2018-10-01 | \N | S020
16135 | Schematic Design | \N | 2018-10-01 | 2018-12-22 | \N | S020
16135 | Design Development | \N | 2019-01-01 | 2019-12-22 | \N | S020
16135 | Contract Documentation | \N | 2020-01-01 | 2020-03-31 | Y | S020
16135 | Construction Administration | \N | 2023-03-01 | 2028-04-30 | Y | S020
16135 | Project Initiation | not in SO | 2018-10-01 | 2018-10-01 | \N | S020
16148 | Construction Administration | \N | 2018-09-01 | 2019-08-31 | \N | \N
16148 | Project Initiation | \N | 2016-12-14 | 2016-12-14 | \N | \N
16148 | Schematic Design | \N | 2017-07-03 | 2017-09-29 | \N | \N
16148 | Design Development | \N | 2017-10-02 | 2017-11-29 | \N | \N
16148 | Contract Documentation | \N | 2017-11-17 | 2018-03-28 | \N | \N
16148 | Concept Design | no link to SO minimal tc | 2016-12-14 | 2017-06-30 | \N | \N
16150 | Concept Design | \N | 2018-03-01 | 2018-03-01 | Y | \N
16150 | Schematic Design | \N | 2018-03-01 | 2018-03-01 | Y | \N
16150 | Others | \N | 2018-03-01 | 2018-03-01 | Y | \N
16150 | Project Initiation | \N | 2018-03-01 | 2018-03-01 | Y | \N
17027 | Contract Documentation | \N | 2018-10-30 | 2018-10-30 | \N | S020
17027 | Project Initiation | \N | 2017-01-24 | 2017-01-24 | \N | S020
17027 | Design Development | \N | 2018-07-31 | 2018-10-30 | \N | S020
17027 | Schematic Design | \N | 2018-01-01 | 2018-02-28 | \N | S020
17027J | Schematic Design | \N | 2017-01-01 | 2017-01-01 | Y | \N
17027J | Project Initiation | \N | 2017-01-01 | 2017-01-01 | Y | \N
17044 | Construction Administration | \N | 2018-02-01 | 2019-01-31 | \N | \N
17044 | Project Initiation | \N | 2017-03-01 | 2017-03-01 | \N | \N
17044 | Schematic Design | \N | 2017-03-02 | 2017-05-01 | \N | \N
17044 | Design Development | \N | 2017-06-22 | 2017-09-21 | \N | \N
17044 | Contract Documentation | \N | 2017-10-01 | 2018-01-31 | \N | \N
17056 | Construction Administration | \N | 2018-04-30 | 2019-11-08 | \N | \N
17056 | Project Initiation | \N | 2017-04-10 | 2017-04-10 | \N | \N
17056 | Concept Design | \N | 2017-04-10 | 2018-01-31 | \N | \N
17056 | Detailed Design | \N | 2018-01-15 | 2018-09-04 | \N | \N
17056 | Miscellaneous | Concept stage | 2017-04-17 | 2017-04-17 | \N | \N
17090 | Construction Administration | \N | 2024-01-01 | 2024-06-30 | Y | S020
17090 | Project Initiation | \N | 2017-04-26 | 2017-04-26 | \N | S020
17090 | Schematic Design | \N | 2017-04-26 | 2017-08-25 | \N | S020
17090 | Contract Documentation | \N | 2017-07-20 | 2017-09-27 | \N | S020
17119 | Construction Administration | \N | 2018-07-01 | 2018-08-31 | N | \N
17119 | Project Initiation | \N | 2017-05-01 | 2017-05-01 | \N | \N
17119 | Contract Documentation | \N | 2017-11-07 | 2017-11-28 | \N | \N
17119 | Design Development | N/A | 2017-11-07 | 2017-11-28 | \N | \N
17119 | Schematic Design | N/A | 2017-05-02 | 2017-05-17 | \N | \N
17124 | Contract Documentation | \N | 2020-09-01 | \N | Y | \N
17124 | Construction Administration | \N | 2020-09-01 | \N | Y | \N
17124 | BIM LOD 300 MEPF Modelling | \N | 2020-09-01 | \N | Y | \N
17124 | Planning and Programming | \N | 2017-10-02 | 2018-01-30 | \N | \N
17124 | Concept Design | \N | 2018-02-01 | 2018-12-31 | \N | \N
17124 | Schematic Design | \N | 2019-01-03 | 2019-12-19 | \N | \N
17124 | Design Development | \N | 2019-01-04 | 2019-10-02 | \N | \N
17124 | Project Initiation | \N | 2017-10-02 | 2017-10-02 | \N | \N
17124 | Post Construction Phase | \N | 2020-09-01 | \N | Y | \N
17131 | Conceptual Masterplanning | PAGCOR | 2016-12-01 | 2016-12-31 | Y | S010
17131 | Final Masterplanning | SOM | 2017-01-01 | 2017-04-30 | N | S010
17131 | Schematic Design | \N | 2017-09-30 | 2017-12-20 | N | S020
17131 | Design Development | \N | 2018-01-08 | 2018-08-06 | N | S020
17131 | Contract Documentation | \N | 2018-08-07 | 2019-01-07 | N | S020
17131 | Construction Administration | \N | 2018-03-01 | 2021-02-28 | N | S020
17131 | BIM LOD 300 MEPF Modelling | \N | 2018-08-07 | 2020-06-01 | Y | S060
17131 | Conceptual Masterplanning | STEELMAN | 2017-05-01 | 2017-09-30 | Y | S010
17131 | Project Initiation | \N | 2016-12-01 | \N | N | S020
17134 | Construction Administration | \N | 2018-05-11 | 2019-10-28 | \N | \N
17134 | Project Initiation | \N | 2017-06-14 | 2017-06-14 | \N | \N
17134 | Contract Documentation | \N | 2018-05-21 | 2018-12-05 | \N | \N
17134 | Design Development | Part of preliminary | 2018-04-19 | 2018-07-10 | \N | \N
17134 | Schematic Design | Part of preliminary | 2017-06-14 | 2018-05-16 | \N | \N
17163 | Construction Administration | \N | 2018-07-01 | 2018-12-31 | \N | \N
17163 | Design Development | \N | 2017-10-09 | 2018-01-31 | \N | \N
17163 | Contract Documentation | \N | 2018-02-01 | 2018-03-15 | \N | \N
17163 | Others | \N | 2019-01-01 | 2020-12-31 | \N | \N
17163 | Project Initiation | \N | 2017-08-14 | 2017-08-14 | \N | \N
17168 | Construction Administration | \N | 2018-07-01 | 2018-12-31 | \N | \N
17168 | Design Development | \N | 2017-08-10 | 2017-12-31 | \N | \N
17168 | Contract Documentation | \N | 2018-01-01 | 2018-04-30 | \N | \N
17168 | Others | \N | 2019-01-01 | 2020-12-30 | \N | \N
17168 | Project Initiation | \N | 2017-08-10 | 2017-08-10 | \N | \N
17195 | Construction Administration | \N | 2018-07-09 | 2019-10-18 | \N | \N
17195 | Project Initiation | \N | 2017-09-08 | 2017-09-08 | \N | \N
17195 | Design Development | \N | 2017-09-29 | 2018-06-29 | \N | \N
17195 | Preliminary Design | \N | 2017-10-06 | 2018-02-05 | \N | \N
17195 | Schematic Design | \N | 2017-09-08 | 2017-10-05 | \N | \N
17206 | Construction Administration | CA | 2019-09-01 | 2019-12-31 | \N | \N
17206 | Concept Design | Schematic | 2018-01-09 | 2018-06-29 | \N | \N
17206 | Schematic Design | No TC | 2018-01-09 | 2018-06-29 | \N | \N
17206 | Design Development | No TC | 2018-07-02 | 2018-11-29 | \N | \N
17206 | Construction Administration | No TC | 2018-12-03 | 2019-12-07 | \N | \N
17206 | Project Initiation | \N | 2018-01-09 | 2018-01-09 | \N | \N
17206 | Contract Documentation | CD | 2018-07-02 | 2018-11-29 | \N | \N
17214 | Contract Documentation | \N | 2018-05-07 | 2019-01-06 | \N | \N
17214 | Construction Administration | \N | 2025-01-01 | 2027-12-31 | Y | \N
17214 | Schematic Design | \N | 2018-01-22 | 2018-03-27 | \N | \N
17214 | Design Development | \N | 2018-03-28 | 2018-04-07 | \N | \N
17214 | Tender | Under Construction Admin | 2020-09-01 | 2024-12-31 | Y | \N
17214 | Project Initiation | \N | 2018-01-22 | \N | \N | \N
17224 | Contract Documentation | DD/CD -ABORTED SCOPE | 2018-04-01 | 2018-08-30 | \N | S020
17224 | Project Initiation | \N | 2017-11-01 | 2017-11-01 | \N | S020
17224 | Schematic Design | \N | 2017-12-01 | 2018-03-31 | \N | S020
17224 | Construction Administration | ABORTED SCOPE | 2018-09-01 | 2019-12-30 | \N | S020
17224 | Schematic Design | removed line - combined to line 3 | 2017-12-01 | 2018-12-30 | \N | S020
17230 | Concept Design | Redundant | 2018-05-01 | 2018-05-01 | \N | \N
17230 | Project Initiation | \N | 2018-02-27 | 2018-02-27 | \N | \N
17230 | Conceptual Masterplanning | Preliminary Conceptual Masterplan Stage & Project Appreciation and Baseline review Stage | 2018-02-27 | 2018-09-07 | \N | \N
17230 | Conceptual Masterplanning | XX | 2018-02-27 | 2018-09-07 | \N | \N
17230 | Final Masterplanning | \N | 2018-07-17 | 2019-02-20 | \N | \N
17230J | Concept Design | Redundant | 2018-05-01 | 2019-02-20 | \N | \N
17230J | Project Initiation | \N | 2018-02-27 | 2018-02-27 | \N | \N
17230J | Conceptual Masterplanning | Preliminary Conceptual Masterplan Stage | 2018-05-11 | 2018-09-07 | \N | \N
17230J | Conceptual Masterplanning | Project Appreciation and Baseline review Stage | 2018-02-27 | 2018-04-19 | \N | \N
17230J | Final Masterplanning | \N | 2018-07-17 | 2019-02-20 | \N | \N
18009 | Construction Administration | \N | 2018-02-01 | 2019-03-31 | N | \N
18009 | Project Initiation | \N | 2018-02-01 | 2018-02-01 | N | \N
18009 | Contract Documentation | NA | 2018-02-17 | 2018-03-06 | \N | \N
18009 | Miscellaneous | NA | 2018-07-12 | 2018-07-20 | \N | \N
1800902 | Construction Administration | \N | 2019-04-01 | 2020-01-31 | \N | S020
1800902 | Project Initiation | XX | 2019-04-01 | 2019-04-01 | \N | \N
18015 | Construction Administration | \N | 2018-09-01 | 2019-09-30 | \N | \N
18015 | Project Initiation | \N | 2018-02-01 | 2018-02-01 | \N | \N
18015 | Schematic Design | \N | 2018-02-01 | 2018-03-31 | \N | \N
18015 | Design Development | \N | 2018-04-01 | 2018-05-31 | \N | \N
18015 | Contract Documentation | \N | 2018-06-01 | 2018-08-31 | \N | \N
18035 | Schematic Design | \N | 2018-02-01 | 2018-05-01 | N | S030
18035 | Detailed Design | \N | 2018-05-02 | 2018-09-04 | N | S030
18035 | Construction Administration | \N | 2019-07-01 | 2020-06-30 | N | S030
18035 | Project Initiation | \N | 2018-02-01 | 2018-02-01 | N | S030
18050 | Construction Administration | \N | 2018-12-01 | 2019-11-30 | \N | \N
18050 | Project Initiation | \N | 2018-02-28 | 2018-02-28 | \N | \N
18050 | Schematic Design | \N | 2018-03-01 | 2018-05-31 | \N | \N
18050 | Design Development | \N | 2018-06-01 | 2018-07-31 | \N | \N
18050 | Contract Documentation | \N | 2018-08-01 | 2018-11-30 | \N | \N
18053 | Design Development | \N | 2019-03-01 | 2022-06-30 | N | \N
18053 | Schematic Design | \N | 2018-09-01 | 2019-02-28 | \N | \N
18053 | Project Initiation | \N | 2018-09-01 | \N | \N | \N
18075 | Schematic Design | On hold June 2020 with some activity in 2021 | 2020-01-01 | 2020-06-30 | Y | S020
18075 | Concept Design | \N | 2019-01-02 | 2020-01-06 | N | S020
18075 | Others | not in S.O. | 2018-01-08 | 2018-01-29 | Y | S020
18075 | Contract Documentation | \N | 2023-01-01 | 2023-04-30 | Y | S020
18075 | Tender | not in S.O. | 2023-05-01 | 2023-05-31 | Y | S020
18075 | Construction Administration | \N | 2024-05-01 | 2025-12-31 | Y | S020
18075 | Project Initiation | \N | 2018-03-28 | 2018-03-28 | \N | S020
18077 | Contract Documentation | \N | 2019-12-13 | 2020-11-27 | \N | \N
18077 | Construction Administration | \N | 2025-01-01 | 2026-12-31 | Y | \N
18077 | Schematic Design | \N | 2019-04-02 | 2019-04-30 | \N | \N
18077 | Design Development | \N | 2019-05-01 | 2019-12-12 | \N | \N
18077 | Others | Redundant | 2020-08-31 | 2020-10-20 | \N | \N
18077 | Tender | Part of Construction Admin | 2020-12-01 | 2024-12-31 | Y | \N
18077 | Project Initiation | \N | 2019-04-02 | \N | \N | \N
18078 | Contract Documentation | \N | 2020-09-01 | 2021-04-30 | N | S020
18078 | Design Development | \N | 2018-04-02 | 2018-07-01 | N | S020
18078 | Project Initiation | \N | 2018-04-01 | 2018-04-01 | N | S020
18078 | Construction Administration | \N | 2022-02-01 | 2025-01-31 | N | S020
18080 | Construction Administration | \N | 2019-04-01 | 2019-10-31 | \N | \N
18080 | Project Initiation | \N | 2018-07-01 | 2018-07-01 | \N | \N
18080 | Contract Documentation | \N | 2018-04-24 | 2019-03-31 | \N | \N
18091 | Construction Administration | Aborted stage: 30 months including BIM | 2024-01-01 | 2026-06-30 | Y | S020
18091 | BIM LOD 300 Architecture and Structural Modelling | not in SO | 2018-10-10 | 2018-10-10 | Y | \N
18091 | BIM LOD 300 MEPF Modelling | Contract Documentation | 2019-01-09 | 2020-12-31 | N | S060
18091 | 2D Combined Services Drawings | not in SO | 2018-10-10 | 2018-10-10 | Y | \N
18091 | Others | not in SO | 2018-10-10 | 2018-10-10 | Y | \N
18091 | Schematic Design | including BIM | 2018-10-10 | 2020-10-23 | N | S020
18091 | Contract Documentation | \N | 2019-01-09 | 2020-12-31 | N | S020
18091 | Project Initiation | Including BIM | 2018-10-10 | 2018-10-10 | \N | S020
18104 | Construction Administration | \N | 2018-05-01 | 2018-05-01 | Y | \N
18104 | Schematic Design | \N | 2018-05-01 | 2018-05-01 | Y | \N
18104 | Contract Documentation | \N | 2018-05-01 | 2018-05-01 | Y | \N
18104 | Project Initiation | \N | 2018-05-01 | 2018-05-01 | Y | \N
18124 | Construction Administration | \N | 2019-04-01 | 2020-03-31 | Y | \N
18124 | Schematic Design | \N | 2018-06-01 | \N | \N | \N
18124 | Design Development | \N | 2018-12-01 | \N | \N | \N
18124 | Contract Documentation | \N | 2019-03-16 | \N | \N | \N
18124 | Project Initiation | \N | 2018-06-01 | \N | \N | \N
18134 | Construction Administration | \N | 2018-12-15 | 2019-05-23 | \N | \N
18134 | Design Development | \N | 2018-07-09 | 2018-08-09 | \N | \N
18134 | Contract Documentation | \N | 2018-08-31 | 2018-12-14 | \N | \N
18134 | Project Initiation | \N | 2018-07-09 | 2018-07-09 | \N | \N
18136 | Construction Administration | \N | 2018-12-03 | 2019-06-11 | \N | \N
18136 | Planning and Programming | Concept Design | 2018-06-27 | 2018-08-30 | \N | \N
18136 | Schematic Design | \N | 2018-08-07 | 2018-08-31 | \N | \N
18136 | Design Development | \N | 2018-09-01 | 2018-09-28 | \N | \N
18136 | Contract Documentation | \N | 2018-10-01 | 2018-11-29 | \N | \N
18136 | Others | \N | 2019-06-12 | 2019-12-30 | \N | \N
18136 | Project Initiation | \N | 2018-06-27 | 2018-06-27 | \N | \N
18136 | Concept Design | \N | 2018-06-27 | 2018-08-30 | \N | \N
18142 | Schematic Design | \N | 2019-01-01 | 2019-07-31 | N | S020
18142 | Concept Design | \N | 2018-10-01 | 2018-10-01 | N | S020
18142 | Design Development | \N | 2020-12-17 | 2023-02-28 | N | S020
18142 | Contract Documentation | \N | 2022-11-01 | 2024-02-29 | N | S020
18142 | Construction Administration | \N | 2024-03-01 | 2029-02-28 | N | S020
18142 | Project Initiation | \N | 2018-10-01 | 2018-10-01 | N | S020
18149 | Detailed Design | Scope Aborted | 2019-02-01 | 2020-02-29 | N | S020
18149 | Preliminary Design | \N | 2018-12-01 | 2019-02-28 | N | S020
18149 | Miscellaneous | Post Project | 2020-02-01 | 2021-05-03 | Y | S020
18149 | Project Initiation | \N | 2018-12-01 | 2018-12-01 | N | S020
18149 | Construction Administration | CANCELLED | 2020-03-01 | 2023-02-28 | Y | S020
18151 | Concept Design | not in SO | 2019-05-06 | 2019-09-30 | N | S020
18151 | Schematic Design | \N | 2019-10-01 | 2019-12-31 | N | S020
18151 | Design Development | 5 months | 2024-05-01 | 2024-09-30 | N | S020
18151 | Contract Documentation | 6 months | 2024-10-01 | 2025-03-31 | N | S020
18151 | Tender | not in SO | 2025-04-01 | 2025-04-30 | N | S020
18151 | Construction Administration | 96 months | 2025-05-01 | 2033-04-30 | N | S020
18151 | Others | not in SO | 2019-05-06 | 2019-05-06 | N | S020
18151 | Project Initiation | \N | 2019-05-06 | 2019-05-06 | N | S020
18160 | Construction Administration | \N | 2020-04-01 | 2021-03-31 | \N | \N
18160 | Contract Documentation | \N | 2018-08-13 | 2019-11-30 | \N | \N
18160 | Project Initiation | \N | 2018-07-19 | 2018-07-19 | \N | \N
18170 | Construction Administration | \N | 2018-11-27 | 2019-09-09 | \N | \N
18170 | Design Development | \N | 2018-10-02 | 2019-04-02 | \N | \N
18170 | Contract Documentation | \N | 2019-01-29 | 2019-07-02 | \N | \N
18170 | Tender | \N | 2019-01-29 | 2019-07-02 | \N | \N
18170 | Project Initiation | \N | 2018-10-02 | 2018-10-02 | \N | \N
18172 | Construction Administration | \N | 2019-11-01 | 2022-10-31 | \N | \N
18172 | Preliminary Architecture and Engineering Design | \N | 2019-01-08 | 2019-06-01 | \N | \N
18172 | Detailed Architecture and Engineering Design | Contract Documentation | 2019-06-02 | 2019-10-31 | \N | \N
18172 | Project Initiation | \N | 2019-03-25 | 2019-03-25 | \N | \N
1817203 | Construction Administration | \N | 2019-11-01 | 2022-10-31 | \N | \N
1817203 | Preliminary Architecture and Engineering Design | \N | 2019-01-08 | 2019-06-01 | \N | \N
1817203 | Detailed Architecture and Engineering Design | \N | 2019-06-02 | 2019-10-31 | \N | \N
18182 | Conceptual Masterplanning | \N | 2018-11-01 | 2019-05-31 | N | S010
18182 | Final Masterplanning | \N | 2018-11-01 | 2019-05-31 | N | S010
18182 | Preliminary Design | AR: TOWERS 1 TO 6 | 2019-05-01 | 2019-06-30 | N | S020
18182 | Detailed Design | A&E: PH-1 FEB 2020 ¦ ON-GOING Towers 4 - 6 | 2019-06-30 | 2019-12-31 | N | S020
18182 | Construction Administration | A&E: Tower 1 CS 5 mo | 2020-06-01 | 2020-10-31 | N | S020
18182 | Tender | XX | 2020-08-31 | 2021-06-29 | Y | \N
18182 | Others | \N | 2018-11-01 | 2018-11-01 | Y | \N
18182 | Project Initiation | AR: TOWERS 1 TO 6 | 2018-11-01 | 2018-11-01 | N | S020
18182 | Detailed Design | Tower 2 | 2019-06-30 | 2019-12-31 | Y | \N
18182 | Detailed Design | Tower 3 | 2019-06-30 | 2019-12-31 | Y | \N
18182 | Detailed Design | A&E: Tower 4 | 2021-01-01 | 2021-12-31 | N | S020
18182 | Detailed Design | A&E: Tower 5 | 2021-01-01 | 2021-12-31 | N | S020
18182 | Detailed Design | A&E: Tower 6 | 2021-01-01 | 2021-12-31 | N | S020
18182 | Construction Administration | AIDEA Tower 2 | 2023-08-01 | 2024-10-31 | N | S020
18182 | Construction Administration | AIDEA Tower 3 | 2024-01-01 | 2025-03-31 | N | S020
18182 | Construction Administration | AIDEA Tower 4 | 2024-01-01 | 2025-03-31 | N | S020
18182 | Construction Administration | AIDEA Tower 5 | 2024-01-01 | 2025-03-31 | N | S020
18182 | Construction Administration | AIDEA Tower 6 | 2024-01-01 | 2025-03-31 | N | S020
18182 | Construction Administration | A&E: Tower 1 CS 15 mo | 2021-06-01 | 2022-08-31 | N | S020
18182 | Construction Administration | LA Tower 2 | 2023-08-01 | 2024-10-31 | N | S070
18182 | Construction Administration | LA Tower 3 | 2024-01-01 | 2025-03-31 | N | S070
18182 | Construction Administration | LA Tower 4 | 2024-01-01 | 2025-03-31 | N | S070
18182 | Construction Administration | LA Tower 5 | 2024-01-01 | 2025-03-31 | N | S070
18182 | Construction Administration | LA Tower 6 | 2024-01-01 | 2025-03-31 | N | S070
18182B | Preliminary Design | Schematic Design in SO | 2019-07-01 | 2019-08-20 | \N | S030
18182B | Detailed Design | Contract Documentation in SO | 2019-08-20 | 2020-04-30 | \N | S030
18182B | Construction Administration | \N | 2020-06-01 | 2020-11-30 | \N | S030
18182B | Project Initiation | \N | 2019-07-01 | 2019-07-01 | \N | S030
18183 | Preliminary Design | \N | 2018-09-26 | 2019-01-31 | \N | S020
18183 | Detailed Design | \N | 2019-01-31 | 2020-08-31 | \N | S020
18183 | Construction Administration | CANCELLED | 2021-03-01 | 2022-08-31 | N | S020
18183 | Construction Administration | Tender | 2021-03-01 | 2021-03-01 | \N | S020
18183 | Project Initiation | Mobilization | 2018-09-26 | 2018-09-26 | \N | S020
18192 | Contract Documentation | N/A | 2019-05-02 | 2019-09-30 | \N | \N
18192 | Construction Administration | \N | 2019-10-01 | 2020-05-31 | \N | \N
18192 | Concept Design | Schematic Design | 2019-03-01 | 2019-04-30 | \N | \N
18192 | Design Development | Contract Documentation | 2019-05-02 | 2019-09-30 | \N | \N
18192 | Project Initiation | \N | 2019-03-01 | 2019-03-01 | \N | \N
18204 | Schematic Design | \N | 2019-04-01 | 2019-05-31 | \N | S030
18204 | Contract Documentation | \N | 2019-05-30 | 2020-11-13 | \N | S030
18204 | Construction Administration | \N | 2023-01-01 | 2025-12-31 | Y | S030
18204 | Concept Design | \N | 2019-03-01 | 2019-03-29 | \N | S030
18204 | Design Development | \N | 2019-06-03 | 2020-11-13 | \N | S030
18204 | Project Initiation | \N | 2019-03-01 | 2019-03-01 | \N | S030
18223 | Contract Documentation | \N | 2018-08-12 | 2018-08-12 | Y | \N
18223 | Construction Administration | \N | 2018-08-12 | 2018-08-12 | Y | \N
18223 | Schematic Design | \N | 2018-08-12 | 2018-08-12 | Y | \N
18223 | Design Development | \N | 2018-08-12 | 2018-08-12 | Y | \N
18223 | Project Initiation | \N | 2018-08-12 | 2018-08-12 | Y | \N
18223 | Concept Design | \N | 2018-08-12 | 2018-08-12 | Y | \N
18236 | Construction Administration | Not in SO | 2019-02-11 | 2019-12-31 | \N | \N
18236 | Project Initiation | \N | 2019-02-11 | 2019-02-11 | \N | \N
18236 | Schematic Design | \N | 2019-02-11 | 2019-03-15 | \N | \N
18249 | Construction Administration | Abortive June 2022 onwards | 2020-02-01 | 2022-05-31 | N | S020
18249 | Schematic Design | \N | 2019-05-30 | 2019-08-31 | \N | S020
18249 | Design Development | \N | 2019-09-01 | 2019-11-30 | \N | S020
18249 | Contract Documentation | \N | 2019-12-01 | 2020-02-14 | \N | S020
18249 | Project Initiation | \N | 2019-05-30 | 2019-05-30 | \N | S020
18256 | Construction Administration | \N | 2019-08-01 | 2019-10-16 | \N | \N
18256 | Design Development | \N | 2019-02-06 | 2019-05-15 | \N | \N
18256 | Contract Documentation | \N | 2019-05-16 | 2019-07-30 | \N | \N
18256 | Project Initiation | \N | 2019-01-09 | 2019-01-09 | \N | \N
18261 | Schematic Design | Concept & Schematic Design | 2019-03-20 | 2023-03-07 | N | S020
18261 | Design Development | Cancelled Scope | 2019-03-20 | 2019-03-20 | Y | S020
18261 | Contract Documentation | Cancelled Scope | 2019-03-20 | 2019-03-20 | Y | S020
18261 | Construction Administration | Cancelled Scope | 2019-03-20 | 2019-03-20 | Y | S020
18261 | Project Initiation | \N | 2019-03-20 | 2019-03-20 | N | S020
18261 | Schematic Design | SUBCON | 2019-03-20 | 2023-03-07 | N | S070
18264 | Schematic Design | Building Audit | 2019-01-14 | 2019-05-27 | \N | \N
18264 | Project Initiation | \N | 2019-01-14 | 2019-01-14 | \N | \N
18264 | Building Audit | \N | 2019-01-14 | 2019-05-27 | \N | \N
18265 | Construction Administration | \N | 2019-04-01 | 2020-10-06 | \N | \N
18265 | Project Initiation | \N | 2019-01-01 | 2019-01-01 | \N | \N
18265 | Preliminary Architectural Design | \N | 2019-01-01 | 2019-01-31 | \N | \N
18265 | Contract Documentation | \N | 2019-02-01 | 2019-03-31 | \N | \N
18283 | Construction Administration | \N | 2019-01-04 | 2019-01-04 | Y | \N
18283 | Project Initiation | \N | 2019-01-04 | 2019-01-04 | Y | \N
18283 | Schematic Design | \N | 2019-01-04 | 2019-01-04 | Y | \N
18283 | Contract Documentation | \N | 2019-01-04 | 2019-01-04 | Y | \N
18284 | Construction Administration | \N | 2019-04-01 | 2019-04-01 | Y | \N
18284 | Project Initiation | \N | 2019-04-01 | 2019-04-01 | Y | \N
18284 | Schematic Design | \N | 2019-04-01 | 2019-04-01 | Y | \N
18284 | Contract Documentation | \N | 2019-04-01 | 2019-04-01 | Y | \N
19021 | Conceptual Masterplanning | \N | 2019-10-01 | 2020-08-31 | \N | \N
19021 | Final Masterplanning | N/A | 2020-08-31 | 2020-08-31 | \N | \N
19021 | Project Initiation | \N | 2019-06-28 | 2019-06-28 | \N | \N
19027 | Concept Design | \N | 2019-03-04 | 2020-05-26 | \N | S020
19027 | Project Initiation | \N | 2019-02-27 | 2019-02-27 | \N | S020
19030 | Concept Design | \N | 2019-02-15 | 2019-02-15 | Y | \N
19030 | Project Initiation | \N | 2019-02-15 | 2019-02-15 | Y | \N
19030 | Contract Documentation | \N | 2019-02-15 | 2019-02-15 | Y | \N
19032 | Project Initiation | \N | 2019-02-01 | 2019-02-01 | \N | \N
19032 | Conceptual Masterplanning | \N | 2019-02-01 | 2019-05-31 | \N | \N
19032 | Schematic Design | \N | 2019-06-01 | 2019-10-31 | \N | \N
19035 | Data Collection and Analysis | NIC | 2019-05-31 | 2019-05-31 | \N | \N
19035 | Visioning and Options Generation | NIC | 2019-05-31 | 2019-05-31 | \N | \N
19035 | Conceptual Masterplanning | \N | 2023-01-01 | 2023-02-28 | Y | \N
19035 | Final Masterplanning | \N | 2023-03-01 | 2023-04-30 | Y | \N
19035 | Others | NIC | 2019-05-31 | 2019-05-31 | N | \N
19035 | Project Initiation | \N | 2019-05-31 | 2019-05-31 | \N | \N
19052 | Final Masterplanning | \N | 2019-03-15 | 2023-12-31 | N | S010
19058 | Construction Administration | line 5 other stages | 2019-10-01 | 2020-05-31 | \N | \N
19058 | Schematic Design | line 2 dd | 2019-06-19 | 2019-08-31 | \N | \N
19058 | Design Development | line 3 cd | 2019-06-19 | 2019-08-31 | \N | \N
19058 | Contract Documentation | line 4 CA | 2019-09-01 | 2019-09-30 | \N | \N
19058 | Project Initiation | line 1 other stages | 2019-06-19 | 2019-06-19 | \N | \N
19075 | Project Initiation | \N | 2019-04-08 | 2019-04-08 | \N | \N
19075 | Schematic Design | \N | 2019-04-08 | 2019-05-30 | \N | \N
19075 | Detailed Design | \N | 2019-06-01 | 2019-08-09 | \N | \N
19077 | Design Development | \N | 2020-02-20 | 2020-06-22 | N | S020
19077 | Contract Documentation | \N | 2020-09-02 | 2021-12-31 | N | S020
19077 | Construction Administration | JAN TO FEB 2024 | 2024-01-01 | 2024-02-29 | N | S020
19077 | Schematic Design | \N | 2019-08-05 | 2020-02-19 | N | S020
19077 | Project Initiation | Mobilization | 2019-08-05 | 2019-08-05 | N | S020
19077 | Construction Administration | 2023 | 2023-09-01 | 2023-09-30 | N | S020
19077 | Construction Administration | ON HOLD: MARCH 2024 ONWARDS | 2024-03-01 | 2026-07-31 | Y | S020
19085 | Design Development | Not part of SO | 2019-10-23 | 2019-10-23 | \N | S060
19085 | Project Initiation | Mobilization | 2019-10-23 | 2019-10-23 | \N | S060
19085 | BIM LOD 300 Architecture and Structural Modelling | move all time charges to to this stage | 2019-10-23 | 2023-06-22 | Y | S060
19081 | Construction Administration | CA & Handover | 2020-01-01 | 2020-06-30 | \N | \N
19081 | Schematic Design | \N | 2019-07-30 | 2019-08-31 | \N | \N
19081 | Design Development | \N | 2019-09-01 | 2019-09-30 | \N | \N
19081 | Contract Documentation | \N | 2019-10-01 | 2019-12-31 | \N | \N
19081 | Project Initiation | \N | 2019-07-30 | 2019-07-30 | \N | \N
19084 | Design Development | \N | 2019-04-26 | 2019-04-26 | Y | \N
19084 | Project Initiation | \N | 2019-04-26 | 2019-04-26 | Y | \N
19101 | Construction Administration | \N | 2019-04-30 | 2019-04-30 | Y | \N
19101 | Schematic Design | \N | 2019-04-30 | 2019-04-30 | Y | \N
19101 | Design Development | \N | 2019-04-30 | 2019-04-30 | Y | \N
19101 | Contract Documentation | \N | 2019-04-30 | 2019-04-30 | Y | \N
19101 | Project Initiation | \N | 2019-04-30 | 2019-04-30 | Y | \N
19112 | Construction Administration | \N | 2020-01-01 | 2020-03-31 | \N | \N
19112 | Concept Design | \N | 2019-06-18 | 2019-08-26 | \N | \N
19112 | Project Initiation | Mobilization | 2019-06-18 | 2019-06-18 | \N | \N
16073A3 | Design Development | Upon Completion of Marketing Plans | 2019-09-01 | 2020-06-09 | N | \N
16073A3 | Project Initiation | \N | 2019-09-01 | 2019-09-01 | N | \N
16073A3 | Design Development | Upon Completion of CTS Plans | 2019-09-01 | 2020-06-09 | Y | \N
19176 | Contract Documentation | \N | 2019-11-01 | 2019-11-30 | \N | \N
19176 | Construction Administration | \N | 2019-12-01 | 2020-03-31 | \N | \N
19176 | Concept Design | \N | 2019-08-01 | 2019-10-31 | \N | \N
19176 | Project Initiation | \N | 2019-08-01 | 2019-08-01 | \N | \N
19178 | Schematic Design | \N | 2019-06-01 | 2023-03-31 | Y | S020
19178 | Project Initiation | \N | 2019-05-31 | 2019-05-31 | \N | S020
19178 | Design Development | \N | 2023-04-01 | 2023-05-31 | Y | S020
19178 | Contract Documentation | \N | 2023-06-01 | 2023-08-31 | Y | S020
19178 | Tender | BIdding and Netiation stage | 2023-09-01 | 2024-12-31 | Y | S020
19178 | Construction Administration | \N | 2025-01-01 | 2027-12-31 | Y | S020
19188 | Preliminary Design | Schematic Design in SO | 2019-10-01 | 2020-03-31 | \N | S020
19188 | Detailed Design | Contract Doc in SO | 2020-04-01 | 2020-11-30 | \N | S020
19188 | Construction Administration | ABORTED STAGE | 2023-03-01 | 2023-03-01 | N | S020
19188 | Project Initiation | \N | 2019-10-01 | 2019-10-01 | \N | S020
19190 | Concept Design | N/A | 2019-08-24 | 2019-08-24 | Y | \N
19190 | Schematic Design | \N | 2019-10-24 | 2020-09-15 | N | \N
19190 | Project Initiation | \N | 2019-08-24 | 2019-08-24 | N | \N
19198 | Preliminary Architecture and Engineering Design | \N | 2023-01-01 | 2023-12-31 | Y | S070
19198 | Project Initiation | \N | 2019-09-01 | 2019-09-01 | N | S070
19198 | Detailed Architecture and Engineering Design | \N | 2024-01-01 | 2024-06-30 | Y | S070
19198 | Construction Administration | \N | 2025-01-01 | 2027-07-31 | Y | S070
19199 | Schematic Design | \N | 2019-09-09 | 2020-12-18 | \N | S020
19199 | Design Development | \N | 2020-01-06 | 2020-04-06 | \N | S020
19199 | Contract Documentation | \N | 2021-01-04 | 2021-06-07 | Y | S020
19199 | Construction Administration | \N | 2021-08-01 | 2024-07-31 | Y | S020
19199 | BIM LOD 300 MEPF Modelling | \N | 2021-01-04 | 2021-06-07 | Y | S060
19199 | Project Initiation | Architecture | 2019-09-09 | 2019-09-09 | N | S020
19199 | BIM LOD 300 Architecture and Structural Modelling | \N | 2021-01-04 | 2021-06-07 | Y | S060
19199 | Clash Detection and Resolution | \N | 2021-01-04 | 2021-06-07 | Y | S060
19199 | 2D Combined Services Drawings | \N | 2021-01-04 | 2021-06-07 | Y | S060
19199 | Project Initiation | BIM LOD300 | 2019-09-09 | 2019-09-09 | N | S060
19204 | Concept Design | ABORTED SCOPE: NIC | 2019-10-02 | 2019-10-02 | \N | S020
19204 | Schematic Design | ABORTED SCOPE: Submitted SD Report (waiting for approval) | 2019-10-02 | 2019-10-02 | Y | S020
19204 | Design Development | ABORTED SCOPE | 2019-10-02 | 2019-10-02 | Y | S020
19204 | Contract Documentation | ABORTED SCOPE | 2019-10-02 | 2019-10-02 | Y | S020
19204 | Construction Administration | ABORTED SCOPE: 18 months | 2019-10-02 | 2019-10-02 | Y | S020
19204 | Project Initiation | \N | 2019-10-02 | 2019-10-02 | \N | S020
19215 | Project Initiation | \N | 2020-01-07 | 2020-01-07 | Y | \N
19263 | Data Collection and Analysis | \N | 2019-11-01 | 2019-12-20 | \N | S010
19263 | Conceptual Masterplanning | \N | 2020-01-06 | 2020-02-28 | \N | S010
19263 | Final Masterplanning | \N | 2020-03-03 | 2020-04-30 | \N | S010
19263 | Project Initiation | \N | 2019-11-01 | 2019-11-01 | \N | S010
17014 | Final Masterplanning | \N | 2017-05-01 | 2017-07-31 | \N | \N
17014 | Concept Design | \N | 2017-08-01 | 2017-08-31 | \N | \N
17014 | Schematic Design | \N | 2017-08-01 | 2017-08-31 | \N | \N
17014 | Detailed Design | \N | 2017-09-01 | 2021-01-31 | \N | \N
17014 | Construction Administration | \N | 2019-06-01 | 2020-09-30 | \N | \N
17014 | Project Initiation | \N | 2017-05-01 | 2017-05-01 | \N | \N
1701401 | Schematic Design | \N | 2017-08-01 | 2018-01-31 | \N | \N
1701401 | Detailed Design | Design Development in SO | 2018-02-01 | 2021-04-30 | \N | \N
1701401 | Construction Administration | \N | 2020-11-01 | 2022-02-28 | \N | \N
1701401 | Project Initiation | \N | 2017-08-01 | 2017-08-01 | \N | \N
18228 | Concept Design | Schematic Design | 2019-10-24 | 2019-11-23 | \N | S020
18228 | Project Initiation | \N | 2019-10-24 | 2019-10-24 | \N | S020
18228 | Design Development | \N | 2019-11-24 | 2019-12-23 | \N | S020
18228 | Contract Documentation | \N | 2019-12-24 | 2020-01-23 | \N | S020
18228 | Construction Administration | \N | 2020-01-24 | 2020-07-23 | \N | S020
19070 | Concept Design | not in S.O. | 2019-09-17 | 2019-12-21 | N | S020
19070 | Schematic Design | \N | 2020-01-06 | 2020-06-13 | N | S020
19070 | Design Development | \N | 2020-06-15 | 2020-11-15 | N | S020
19070 | Contract Documentation | \N | 2021-03-01 | 2022-07-31 | N | S020
19070 | Construction Administration | ABORTED | 2022-07-08 | 2022-07-08 | Y | S020
19070 | Project Initiation | \N | 2019-09-17 | 2019-09-17 | \N | S020
19238 | Construction Administration | \N | 2020-04-01 | 2020-09-30 | \N | \N
19238 | Design Development | Schematic Design in SO | 2019-11-19 | 2020-01-15 | \N | \N
19238 | Contract Documentation | \N | 2020-01-16 | 2020-03-31 | \N | \N
19238 | Project Initiation | \N | 2019-11-19 | 2019-11-19 | \N | \N
19253 | Concept Design | \N | 2019-11-08 | 2019-11-08 | Y | \N
19253 | Project Initiation | \N | 2019-11-08 | 2019-11-08 | Y | \N
19160 | Schematic Design | ON HOLD STARTING APRIL 2020 | 2019-12-18 | 2023-02-28 | Y | S020
19160 | Design Development | \N | 2023-03-01 | 2023-04-30 | Y | S020
19160 | Contract Documentation | \N | 2023-05-01 | 2023-07-31 | Y | S020
19160 | Construction Administration | \N | 2023-08-01 | 2024-01-31 | Y | S020
19160 | Project Initiation | \N | 2019-12-18 | 2019-12-18 | \N | S020
19177 | Construction Administration | \N | 2021-04-01 | 2021-06-30 | \N | \N
19177 | Schematic Design | \N | 2019-08-10 | 2020-03-31 | \N | \N
19177 | Design Development | Contract Documentation | 2020-01-01 | 2020-09-30 | \N | \N
19177 | Project Initiation | \N | 2019-08-09 | 2019-08-09 | \N | \N
19194 | Conceptual Masterplanning | XX | 2020-01-07 | 2020-02-07 | N | S010
19194 | Concept Design | \N | 2020-02-11 | 2020-04-14 | Y | S010
19194 | Final Masterplanning | \N | 2020-08-31 | 2020-10-31 | Y | S010
19194 | Project Initiation | \N | 2020-01-07 | 2020-01-07 | \N | S010
19205 | Design Development | Contract Documentation | 2020-03-17 | 2020-06-30 | N | S030
19205 | Construction Administration | ABORTED STAGE | 2020-12-01 | 2020-12-01 | Y | \N
19205 | Schematic Design | \N | 2019-10-07 | 2020-03-16 | \N | S030
19205 | Project Initiation | \N | 2019-10-07 | 2019-10-07 | \N | S030
19221 | Schematic Design | AR | 2020-02-01 | 2021-08-31 | N | S020
19221 | Design Development | AR | 2021-08-31 | 2022-02-28 | N | S020
19221 | Contract Documentation | AR | 2022-02-28 | 2024-04-30 | N | S020
19221 | Tender | XX | 2021-02-01 | 2021-02-01 | Y | S020
19221 | Construction Administration | AR | 2024-05-01 | 2027-04-30 | N | S020
19221 | Project Initiation | AR | 2020-02-01 | 2020-02-01 | N | S020
19261 | Design Development | \N | 2020-06-26 | 2021-02-12 | \N | S020
19261 | Contract Documentation | \N | 2021-02-15 | 2021-07-15 | \N | S020
19261 | Construction Administration | Actual CS | 2023-02-01 | 2026-01-31 | N | S020
19261 | Schematic Design | \N | 2020-01-01 | 2020-06-30 | \N | S020
19261 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | \N | S020
19261 | Construction Administration | Tender / Bidding Phase | 2021-07-16 | 2023-01-31 | N | S020
19270 | Conceptual Masterplanning | \N | 2020-01-06 | 2021-06-14 | N | \N
19270 | Final Masterplanning | \N | 2021-02-19 | 2021-06-14 | N | \N
19270 | Preliminary Architectural Design | \N | 2021-06-03 | 2021-06-14 | N | \N
19270 | Project Initiation | \N | 2020-01-06 | 2020-01-06 | N | \N
20002 | Concept Design | \N | 2019-12-01 | \N | \N | S020
20002 | Schematic Design | \N | 2019-12-01 | 2021-07-31 | \N | S020
20002 | Project Initiation | \N | 2019-12-01 | \N | \N | S020
19232 | Construction Administration | 7 months contract | 2020-07-01 | 2021-01-31 | \N | \N
19232 | Schematic Design | \N | 2019-11-12 | 2020-02-28 | \N | \N
19232 | Contract Documentation | \N | 2020-03-01 | 2020-06-30 | \N | \N
19232 | Project Initiation | \N | 2019-11-12 | 2019-11-12 | \N | \N
19284 | Final Renderings | \N | 2019-12-19 | 2020-01-31 | \N | S050
19284 | Project Initiation | \N | 2019-12-19 | 2019-12-19 | \N | \N
20001 | Schematic Design | \N | 2020-01-06 | 2020-11-30 | \N | \N
20001 | Project Initiation | \N | 2020-01-06 | 2020-01-06 | \N | \N
20005 | Concept Design | \N | 2020-01-10 | 2020-01-10 | Y | \N
20005 | Project Initiation | \N | 2020-01-10 | 2020-01-10 | Y | \N
19158 | Concept Design | Mobilization | 2019-11-12 | 2020-01-31 | \N | \N
19158 | Schematic Design | Schematic | 2020-02-03 | 2020-03-31 | \N | \N
19158 | Design Development | Design Development | 2020-04-01 | 2020-05-31 | \N | \N
19158 | Contract Documentation | Contract Documentation | 2020-06-01 | 2020-08-31 | \N | \N
19158 | Construction Administration | Construction Administration | 2021-01-01 | 2021-06-30 | \N | \N
19158 | Project Initiation | Mobilization | 2019-11-12 | 2019-11-12 | \N | \N
19260 | Final Masterplanning | SO Line 3 | 2020-09-01 | 2020-11-15 | \N | S010
19260 | Conceptual Masterplanning | SO Line 2 | 2020-03-01 | 2020-10-20 | \N | S010
19260 | Project Initiation | SO Line 1 | 2020-03-01 | 2020-03-01 | \N | S010
20011 | Schematic Design | \N | 2020-01-01 | 2020-01-01 | Y | \N
20011 | Design Development | \N | 2020-01-01 | 2020-01-01 | Y | \N
20011 | Contract Documentation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20011 | Construction Administration | \N | 2020-01-01 | 2020-01-01 | Y | \N
20011 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20013 | Preliminary Design | \N | 2020-02-14 | 2020-09-30 | \N | \N
20013 | Project Initiation | \N | 2020-02-14 | 2020-02-14 | \N | \N
20019 | Detailed Masterplanning | review of Detailed Masterplanning | 2020-07-02 | 2022-01-31 | N | S010
20019 | Final Masterplanning | Permit Plans | 2021-08-01 | 2024-12-31 | N | S010
20019 | Urban Design Guidelines | \N | 2021-02-15 | 2021-12-15 | \N | S010
20019 | Conceptual Masterplanning | review of Conceptual Masterplanning | 2020-02-03 | 2020-07-01 | \N | S010
20019 | Project Initiation | \N | 2020-02-03 | 2020-02-03 | \N | S010
19130 | Concept Design | 25% Conceptual | 2020-04-02 | 2020-08-31 | N | S020
19130 | Concept Design | 15% Conceptual | 2020-03-01 | 2020-05-05 | Y | S020
19130 | Code Review | Validation of existing concept | 2020-03-01 | 2020-04-01 | Y | S020
19130 | Project Initiation | \N | 2020-03-01 | 2020-03-01 | \N | S020
19154 | Final Renderings | SO Line 1 | 2019-01-07 | \N | \N | S080
1920501 | Concept Design | Detailed Design | 2020-05-08 | 2020-06-30 | N | S030
1920501 | Project Initiation | \N | 2020-05-08 | 2020-05-08 | Y | \N
1920501 | Contract Documentation | Not in contract | 2020-05-08 | 2020-05-08 | Y | \N
19283 | Conceptual Masterplanning | \N | 2020-01-06 | 2020-01-06 | Y | \N
19283 | Final Masterplanning | \N | 2020-01-06 | 2020-01-06 | Y | \N
19283 | Project Initiation | Mobilization | 2020-01-06 | 2020-01-06 | Y | \N
20017 | Concept Design | \N | 2020-03-30 | 2021-08-31 | \N | S020
20017 | Schematic Design | Client cancelled this service | 2020-03-30 | 2020-09-29 | Y | \N
20017 | Design Development | Client cancelled this service | 2020-03-30 | 2020-09-29 | Y | \N
20017 | Contract Documentation | Client cancelled this service | 2020-03-30 | 2020-09-29 | Y | \N
20017 | Construction Administration | Client cancelled this service | 2020-03-30 | 2020-09-29 | Y | \N
20017 | Project Initiation | Mobilization | 2020-03-30 | 2020-03-30 | \N | S020
20028 | Conceptual Masterplanning | \N | 2020-02-01 | 2020-02-01 | Y | \N
20028 | Final Masterplanning | \N | 2020-02-01 | 2020-02-01 | Y | \N
20028 | Concept Design | \N | 2020-02-01 | 2020-02-01 | Y | \N
20028 | Schematic Design | \N | 2020-02-01 | 2020-02-01 | Y | \N
20028 | Design Development | \N | 2020-02-01 | 2020-02-01 | Y | \N
20028 | Contract Documentation | \N | 2020-02-01 | 2020-02-01 | Y | \N
20028 | Construction Administration | \N | 2020-02-01 | 2020-02-01 | Y | \N
20028 | Project Initiation | \N | 2020-02-01 | 2020-02-01 | Y | \N
20029 | Conceptual Masterplanning | \N | 2020-03-01 | 2021-02-28 | \N | S010
20029 | Final Masterplanning | \N | 2021-03-01 | 2021-11-30 | \N | S010
20029 | Project Initiation | \N | 2020-03-01 | 2020-03-01 | \N | S010
20033 | Concept Design | Schematic Design in SO | 2020-01-20 | 2020-04-30 | \N | \N
20033 | Contract Documentation | \N | 2020-08-31 | 2020-11-13 | \N | \N
20033 | Construction Administration | \N | 2021-04-01 | 2021-05-31 | \N | \N
20033 | Project Initiation | \N | 2020-01-20 | 2020-01-20 | \N | \N
20038 | Development Permit Alteration Plans | \N | 2020-01-01 | 2022-12-31 | N | S020
20038 | Master Deed and Declaration of Restrictions (MDDR) Annex | \N | 2020-01-01 | 2024-12-31 | N | S020
20038 | Conveyance Plans | \N | 2020-01-01 | 2024-12-31 | N | S020
20038 | Project Initiation | XX | 2020-01-01 | 2020-01-01 | Y | \N
20039 | Development Permit Alteration Plans | \N | 2020-01-01 | 2024-12-31 | N | S020
20039 | Master Deed and Declaration of Restrictions (MDDR) Annex | \N | 2020-01-01 | 2024-12-31 | N | S020
20039 | Project Initiation | XX | 2020-01-01 | 2020-01-01 | Y | \N
20048 | Data Collection and Analysis | not in S.O. | 2020-04-01 | 2020-04-01 | \N | \N
20048 | Conceptual Masterplanning | Preliminary | 2020-07-01 | 2020-11-30 | \N | \N
20048 | Final Masterplanning | Final | 2020-04-01 | 2021-01-31 | \N | \N
20048 | Project Initiation | Mobilization | 2020-04-01 | 2020-04-01 | \N | \N
16073A4 | Design Development | CTS Plans | 2020-03-03 | \N | N | \N
16073A4 | Project Initiation | \N | 2020-03-03 | \N | N | \N
1612408 | Contract Documentation | \N | 2020-08-28 | 2020-08-28 | Y | \N
1713102 | Contract Documentation | \N | 2020-02-03 | 2020-05-04 | \N | \N
1713102 | Project Initiation | XXX | 2020-02-03 | \N | \N | \N
1713103 | Contract Documentation | \N | 2018-11-01 | 2019-04-30 | \N | S020
1713103 | Project Initiation | XX | 2018-11-01 | \N | \N | \N
1812402 | Schematic Design | SO Line 1 | 2020-06-11 | 2020-06-11 | Y | \N
19150 | Construction Administration | \N | 2019-10-01 | 2020-02-28 | \N | \N
19150 | Schematic Design | Preliinary Design | 2019-07-01 | 2019-07-30 | \N | \N
19150 | Contract Documentation | \N | 2019-08-01 | 2019-09-30 | \N | \N
19150 | Others | not in contract | 2019-06-21 | 2019-06-21 | \N | \N
19150 | Project Initiation | \N | 2019-06-21 | 2019-06-21 | \N | \N
19159 | Contract Documentation | \N | 2020-03-01 | 2020-03-31 | \N | \N
19159 | Construction Administration | \N | 2020-03-01 | 2020-06-30 | \N | \N
19159 | Concept Design | \N | 2019-08-01 | 2019-09-30 | \N | \N
19159 | Schematic Design | \N | 2019-10-01 | 2019-11-01 | \N | \N
19159 | Design Development | \N | 2019-12-01 | 2020-01-31 | \N | \N
19159 | Tender | \N | 2020-02-01 | 2020-02-27 | \N | \N
19159 | Project Initiation | \N | 2019-07-29 | 2019-07-29 | \N | \N
19195 | Conceptual Masterplanning | \N | 2019-10-25 | 2019-10-25 | Y | \N
19195 | Project Initiation | \N | 2019-10-25 | 2019-10-25 | Y | \N
19195 | Concept Design | Preliminary Concept Masterplan | 2019-10-25 | 2019-10-25 | Y | \N
19200 | Concept Design | SO Line 1 | 2020-05-15 | 2020-07-30 | \N | \N
20030 | Conceptual Masterplanning | Concept Masterplanning | 2020-02-19 | 2020-05-15 | \N | \N
20030 | Others | Data Collection / Visioning | 2020-02-19 | 2020-05-15 | \N | \N
20030 | Project Initiation | Mobilization | 2020-02-19 | 2020-02-19 | \N | \N
20061 | Design Development | \N | 2020-05-30 | 2020-11-06 | \N | \N
20061 | Contract Documentation | no CD-part of DD | 2020-05-30 | 2020-11-06 | \N | \N
20061 | Construction Administration | \N | 2021-04-01 | 2021-08-30 | \N | \N
20061 | Concept Design | Schematic Design in SO | 2020-02-26 | 2020-05-30 | \N | \N
20061 | Project Initiation | \N | 2020-02-26 | 2020-02-26 | \N | \N
20072 | Design Development | \N | 2021-01-01 | 2022-02-28 | Y | S060
20072 | Schematic Design | \N | 2020-01-01 | 2021-02-28 | N | S060
20072 | BIM LOD 300 Architecture and Structural Modelling | \N | 2020-10-01 | 2021-10-31 | Y | S060
20072 | BIM LOD 300 MEPF Modelling | \N | 2020-10-01 | 2021-09-30 | Y | S060
20072 | Project Initiation | XX | 2020-01-01 | 2020-01-01 | Y | \N
20072 | Construction Administration | XX | 2020-01-01 | 2020-01-01 | Y | \N
20072 | Contract Documentation | XX | 2020-01-01 | 2020-01-01 | Y | \N
19057 | Concept Design | \N | 2019-03-25 | 2019-03-25 | Y | \N
19057 | Project Initiation | \N | 2019-03-25 | 2019-03-25 | Y | \N
19057 | Schematic Design | \N | 2019-03-25 | 2019-03-25 | Y | \N
19069 | Concept Design | \N | 2019-04-25 | 2019-04-25 | Y | \N
19069 | Project Initiation | \N | 2019-04-25 | 2019-04-25 | Y | \N
19069 | Schematic Design | \N | 2019-04-25 | 2019-04-25 | Y | \N
19095 | Concept Design | \N | 2019-05-21 | 2019-05-21 | Y | \N
19095 | Project Initiation | \N | 2019-05-21 | 2019-05-21 | Y | \N
19095 | Test-Fit | \N | 2019-05-21 | 2019-05-21 | Y | \N
19179 | Test-Fit | \N | 2020-04-01 | 2020-04-01 | Y | \N
19179 | Project Initiation | \N | 2020-04-01 | 2020-04-01 | Y | \N
20010 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20022 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20041 | Concept Design | \N | 2020-04-13 | 2020-04-13 | Y | \N
20041 | Project Initiation | \N | 2020-04-13 | 2020-04-13 | Y | \N
20044 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20052 | Project Initiation | \N | 2020-03-06 | 2020-03-06 | Y | \N
20078 | Project Initiation | \N | 2020-09-28 | 2020-09-28 | Y | \N
20079 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20080 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20082 | Project Initiation | \N | 2020-04-15 | 2020-04-15 | Y | \N
19145 | Construction Administration | \N | 2019-07-01 | 2019-07-01 | Y | \N
19145 | Project Initiation | \N | 2019-07-01 | 2019-07-01 | Y | \N
19145 | Concept Design | \N | 2019-07-01 | 2019-07-01 | Y | \N
19145 | Design Development | \N | 2019-07-01 | 2019-07-01 | Y | \N
20075 | Design Development | \N | 2020-05-01 | 2021-01-31 | Y | \N
20075 | Contract Documentation | 60%(T1-T3) 30%(T4-T6) | 2020-05-01 | 2023-02-28 | Y | \N
20075 | Construction Administration | 36 | 2024-01-01 | 2026-12-31 | Y | \N
20075 | BIM LOD 300 Architecture and Structural Modelling | XXX | 2020-03-01 | \N | Y | \N
20075 | BIM LOD 300 MEPF Modelling | XXX | 2020-03-01 | \N | Y | \N
20075 | Others | XXX | 2020-03-01 | \N | Y | \N
20075 | Schematic Design | XXX | 2020-03-01 | \N | Y | \N
20075 | Project Initiation | \N | 2020-03-01 | 2020-03-01 | Y | \N
20075 | Contract Documentation | 100%(T1-T3) 60%(T4-T6) | 2023-03-01 | 2023-05-31 | Y | \N
20075 | Contract Documentation | 100%(T4-T6) | 2023-06-01 | 2023-08-31 | Y | \N
20115 | Others | \N | 2020-06-15 | 2020-09-30 | \N | \N
20115 | Project Initiation | \N | 2020-06-15 | 2020-06-15 | \N | \N
1507525 | Construction Administration | \N | 2020-08-01 | \N | \N | \N
1507525 | Project Initiation | \N | 2020-08-01 | \N | \N | \N
1926101 | Design Development | \N | 2020-07-15 | 2020-07-15 | Y | S020
1926101 | Project Initiation | \N | 2020-07-15 | 2020-07-15 | Y | S020
20105 | Concept Design | XX | 2020-06-22 | 2020-06-22 | Y | S020
20105 | Schematic Design | \N | 2020-08-25 | 2020-10-30 | N | S020
20105 | Design Development | T1 & T2 | 2020-11-03 | 2021-10-20 | N | S020
20105 | Contract Documentation | T1 & T2 | 2021-08-31 | 2022-03-31 | N | S020
20105 | Construction Administration | T1 & T2 | 2023-05-01 | 2025-04-30 | N | S020
20105 | Design Development | T3 & T4 | 2021-01-04 | 2021-10-20 | N | S020
20105 | Contract Documentation | T3 & T4 | 2021-08-31 | 2022-03-31 | N | S020
20105 | Construction Administration | T3 & T4 | 2023-05-01 | 2025-04-30 | N | S020
20105 | Design Development | T5 & T6 | 2021-02-01 | 2022-12-31 | N | S020
20105 | Contract Documentation | T5 & T6 | 2023-01-01 | 2024-04-30 | N | S020
20105 | Construction Administration | T5 & T6 | 2024-04-01 | 2026-03-31 | N | S020
20105 | Project Initiation | \N | 2020-06-22 | 2020-06-22 | N | S020
20105 | Tender | \N | 2022-04-01 | 2022-12-31 | N | S020
20118 | Marketing Collaterals | \N | 2020-06-01 | 2020-07-15 | N | S020
20118 | Project Initiation | XXX | 2020-06-01 | 2020-06-01 | Y | \N
20119 | Marketing Collaterals | \N | 2020-06-01 | 2020-11-01 | N | S050
20119 | Project Initiation | XXX | 2020-06-01 | 2020-06-01 | Y | \N
20120 | Development Permit Alteration Plans | \N | 2020-06-01 | \N | N | S020
20120 | Project Initiation | XXX | 2020-06-01 | \N | Y | \N
20128 | Planning and Programming | not in S.O. | 2020-12-07 | 2021-04-26 | Y | S020
20128 | Concept Design | Assistance to Foreign Consultant & Code Review | 2020-11-17 | 2021-08-10 | N | S020
20128 | Schematic Design | SD (overlaps w/ BP Ph1) | 2020-12-04 | 2022-06-29 | N | S020
20128 | Contract Documentation | 30% DD/CD | 2022-03-09 | 2022-10-12 | N | S020
20128 | Contract Documentation | 60% DD/CD | 2022-07-21 | 2023-07-31 | N | S020
20128 | Contract Documentation | 90% DD/CD | 2022-09-01 | 2024-04-30 | N | S020
20128 | Contract Documentation | 100% DD/CD | 2024-01-01 | 2024-06-28 | N | S020
20128 | Project Initiation | Mobilization | 2020-07-09 | 2020-07-09 | N | S020
20128 | Construction Administration | 11/48 months | 2022-08-01 | 2023-06-30 | N | S020
20128 | Construction Administration | ON HOLD: 37/48 months | 2023-07-01 | 2026-07-31 | Y | S020
20112 | Concept Design | \N | 2020-01-01 | 2020-01-01 | Y | \N
20101 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
20085 | Concept Design | \N | 2020-05-07 | 2020-10-30 | \N | \N
20085 | Construction Administration | \N | 2020-11-01 | 2021-01-31 | N | \N
20085 | Project Initiation | \N | 2020-05-07 | 2020-05-07 | \N | \N
20100 | Project Initiation | \N | 2020-01-01 | 2020-01-01 | Y | \N
19205001 | Design Development | \N | 2020-01-01 | \N | \N | \N
19205001 | Project Initiation | \N | 2020-01-01 | \N | \N | \N
20124 | Project Initiation | \N | 2020-06-25 | 2020-06-25 | Y | \N
14107Z2 | Schematic Design | For resumption 2022 | 2022-11-01 | 2023-02-28 | Y | S020
14107Z2 | Contract Documentation | \N | 2023-03-01 | 2023-05-31 | Y | S020
14107Z2 | Construction Administration | \N | 2024-01-01 | 2026-07-31 | Y | S020
14107Z2 | Project Initiation | \N | 2015-03-01 | 2015-03-01 | \N | S020
1302902 | Construction Administration | \N | 2020-06-01 | 2021-05-31 | \N | S020
1302902 | Project Initiation | XX | 2020-06-01 | \N | \N | \N
20088 | Project Initiation | \N | 2020-07-01 | 2020-07-01 | Y | \N
20020 | Design Development | \N | 2020-03-01 | 2020-11-01 | N | S020
20020 | Project Initiation | XXX | 2020-03-01 | 2020-03-01 | Y | \N
16073G | Upon completion of clash detection / resolution | \N | 2020-11-01 | 2024-06-30 | N | S060
16073G | BIM LOD 300 MEPF Modelling | \N | 2020-11-01 | 2023-03-31 | N | S060
16073G | Upon completion of 2D Drawing Documentation | \N | 2020-11-01 | 2024-06-30 | N | S060
16073G | BIM LOD 300 Architecture and Structural Modelling | 40% BIM Modelling | 2018-02-07 | 2020-10-29 | N | S060
18016 | Concept Design | #NAME? | 2019-06-01 | 2019-09-18 | Y | S020
18016 | Schematic Design | AR, ID & Landscape | 2019-09-19 | 2020-07-30 | N | S020
18016 | Design Development | AR, ID & Landscape | 2019-09-19 | 2020-11-30 | N | S020
18016 | Contract Documentation | AR (finished) & Landscape | 2019-12-01 | 2022-05-31 | N | S020
18016 | Construction Administration | AR-Main(12) & Priory(10) | 2020-09-01 | 2022-03-31 | N | S020
18016 | Others | #NAME? | 2018-03-08 | 2018-03-08 | Y | S020
18016 | Conceptual Masterplanning | MP | 2022-07-01 | 2022-08-31 | N | S010
18016 | Final Masterplanning | MP | 2022-10-01 | 2022-12-31 | N | S010
18016 | Project Initiation | All scope | 2018-03-08 | 2018-03-08 | N | S020
18016 | Construction Administration | Landscape (12 mo) | 2024-01-01 | 2024-12-31 | Y | S070
18016 | Construction Administration | ID (6 mo) | 2021-09-01 | 2022-02-28 | N | S030
15075 | Construction Administration | \N | 2017-01-01 | 2019-12-31 | \N | \N
15075 | Schematic Design | \N | 2015-08-26 | 2016-01-12 | \N | \N
15075 | Design Development | \N | 2016-01-13 | 2016-07-05 | \N | \N
15075 | Contract Documentation | \N | 2016-07-06 | 2016-12-21 | \N | \N
15075 | Project Initiation | \N | 2015-08-26 | 2015-08-26 | \N | \N
15073 | Schematic Design | \N | 2015-07-01 | 2015-10-31 | \N | \N
15073 | Design Development | \N | 2016-05-01 | 2016-08-31 | \N | \N
15073 | Contract Documentation | \N | 2016-09-01 | 2017-01-31 | \N | \N
15073 | Construction Administration | \N | 2017-10-01 | 2020-09-30 | \N | \N
15073 | Others | Post Project | 2015-07-01 | 2020-09-30 | \N | \N
15073 | Post Construction Phase | XXX | 2020-09-30 | \N | \N | \N
15073 | Project Initiation | XXX | 2015-07-01 | \N | \N | \N
15068 | Schematic Design | \N | 2015-01-05 | 2015-08-31 | \N | \N
15068 | Design Development | \N | 2015-12-01 | 2016-03-31 | \N | \N
15068 | Contract Documentation | \N | 2018-02-01 | 2018-06-30 | \N | \N
15068 | Construction Administration | \N | 2017-06-01 | 2019-11-30 | \N | \N
15068 | Project Initiation | \N | 2015-05-01 | 2015-05-01 | \N | \N
15068/01 | Schematic Design | \N | 2015-01-05 | 2015-07-31 | N | S020
15068/01 | Design Development | \N | 2015-12-01 | 2016-03-31 | N | S020
15068/01 | Contract Documentation | \N | 2018-02-01 | 2018-06-30 | N | S020
15068/01 | Construction Administration | \N | 2019-01-01 | 2021-06-30 | N | S020
15068/01 | Project Initiation | \N | 2015-05-01 | 2015-05-01 | N | S020
14107Z1 | Contract Documentation | \N | 2020-10-01 | 2021-09-30 | N | S020
14107Z1 | Construction Administration | \N | 2024-01-01 | 2026-06-30 | Y | S020
14107Z1 | Schematic Design | \N | 2015-03-01 | 2020-02-29 | N | S020
14107Z1 | Project Initiation | \N | 2015-03-01 | 2015-03-01 | N | S020
1401801 | Construction Administration | AR | 2016-09-01 | 2021-08-31 | Y | S020
19125 | Contract Documentation | \N | 2020-07-01 | 2020-09-30 | \N | \N
19125 | Construction Administration | \N | 2020-10-01 | 2021-04-30 | \N | \N
19125 | Others | Project Close-out | 2021-05-01 | 2021-08-31 | \N | \N
19125 | Concept Design | \N | 2019-09-16 | 2019-12-31 | \N | \N
19125 | Schematic Design | \N | 2020-01-01 | 2020-03-18 | \N | \N
19125 | Design Development | \N | 2020-03-19 | 2020-06-30 | \N | \N
19125 | Tender | \N | 2020-07-01 | 2020-07-31 | \N | \N
19125 | Project Initiation | \N | 2019-08-30 | 2019-08-30 | \N | \N
15057 | Construction Administration | Construction Administration | 2016-01-01 | 2017-12-31 | N | S020
15057 | Schematic Design | 2nd S.O. | 2015-01-04 | 2016-01-04 | N | S020
15057 | Design Development | 2nd S.O. | 2015-01-01 | 2018-01-04 | N | S020
15057 | Contract Documentation | 2nd S.O. | 2015-01-01 | 2018-01-03 | N | S020
15057 | Tender | not in SO | 2018-01-01 | 2020-01-02 | Y | S020
15057 | BIM LOD 300 MEPF Modelling | 3rd S.O. | 2015-01-03 | 2019-06-18 | N | S020
15057 | Others | not in SO | 2015-01-03 | 2017-01-03 | Y | S020
15057 | Project Initiation | 2nd S.O. | 2015-01-01 | 2015-01-01 | N | S020
13095 | Construction Administration | \N | 2015-11-01 | 2019-02-28 | \N | S020
13095 | Others | Post Project | 2013-10-01 | \N | \N | S020
13095 | Project Initiation | \N | 2013-10-01 | \N | \N | S020
13095 | Contract Documentation | \N | 2013-11-01 | 2015-10-31 | \N | S020
13102 | Construction Administration | \N | 2017-10-01 | 2019-03-31 | \N | \N
13102 | Project Initiation | \N | 2013-12-15 | 2013-12-15 | \N | \N
13102 | Contract Documentation | \N | 2016-02-01 | 2016-04-30 | \N | \N
13102 | Design Development | \N | 2015-11-01 | 2016-01-31 | \N | \N
13102 | Schematic Design | \N | 2015-09-01 | 2015-10-31 | \N | \N
13102 | Concept Design | \N | 2013-12-15 | 2014-01-30 | \N | \N
14018 | Construction Administration | \N | 2015-03-01 | 2016-08-31 | \N | \N
14018 | Others | Post Project | 2014-07-01 | 2014-07-01 | \N | \N
14018 | Project Initiation | \N | 2014-07-01 | 2014-07-01 | \N | \N
14018 | Schematic Design | \N | 2014-06-17 | 2018-01-19 | \N | \N
14018 | Conceptual Masterplanning | \N | 2014-05-26 | 2014-11-21 | \N | \N
14018 | Contract Documentation | \N | 2014-06-04 | 2018-06-26 | \N | \N
14107 | Construction Administration | \N | 2017-09-01 | 2020-02-29 | \N | S020
14107 | Contract Documentation | \N | 2015-11-01 | 2017-11-30 | \N | S020
14107 | Schematic Design | \N | 2014-04-01 | 2015-10-31 | \N | S020
14107 | Others | \N | 2014-04-01 | 2014-04-01 | \N | \N
14107 | Project Initiation | \N | 2014-04-01 | 2014-04-01 | \N | S020
14112J | Construction Administration | \N | 2016-03-02 | 2019-03-01 | \N | \N
14112J | Project Initiation | \N | 2015-07-01 | 2015-07-01 | \N | \N
14112J | Schematic Design | \N | 2015-07-02 | 2015-10-01 | \N | \N
14112J | Design Development | \N | 2015-10-02 | 2015-12-01 | \N | \N
14112J | Contract Documentation | \N | 2015-12-02 | 2016-03-01 | \N | \N
15037 | Construction Administration | \N | 2016-11-12 | 2017-01-15 | \N | \N
15037 | Project Initiation | \N | 2015-03-01 | 2015-03-01 | \N | \N
15037 | Contract Documentation | \N | 2015-03-06 | 2016-11-11 | \N | \N
18069 | Construction Administration | \N | 2019-04-01 | 2020-06-30 | \N | \N
18069 | Concept Design | \N | 2018-05-17 | 2018-07-04 | \N | \N
18069 | Schematic Design | \N | 2018-07-05 | 2018-09-04 | \N | \N
18069 | Design Development | \N | 2018-09-05 | 2018-10-31 | \N | \N
18069 | Contract Documentation | \N | 2018-11-01 | 2018-12-31 | \N | \N
18069 | Tender | \N | 2019-01-01 | 2019-03-31 | \N | \N
18069 | Project Initiation | \N | 2018-05-17 | 2018-05-17 | \N | \N
19242 | Design Development | \N | 2020-06-23 | 2020-10-09 | N | S020
19242 | Contract Documentation | \N | 2020-10-12 | 2021-02-26 | N | S020
19242 | Construction Administration | AR + SUBCON FROM 2021 TO MARCH 2023 | 2021-07-01 | 2023-03-31 | N | S020
19242 | BIM LOD 300 Architecture and Structural Modelling | \N | 2020-06-23 | 2020-10-09 | N | S060
19242 | BIM LOD 300 MEPF Modelling | \N | 2020-09-01 | 2021-01-29 | N | S060
19242 | Schematic Design | \N | 2019-11-20 | 2020-02-11 | N | S020
19242 | Upon completion of clash detection / resolution | \N | 2020-09-01 | 2021-02-26 | N | S060
19242 | Upon completion of 2D Drawing Documentation | \N | 2020-10-12 | 2021-03-15 | N | S060
19242 | Project Initiation | Mobilization of AR & Subcon | 2019-11-20 | 2019-11-20 | N | S020
19242 | Construction Administration | Architecture | 2023-04-01 | 2024-06-30 | Y | S020
19242 | Construction Administration | Subcon | 2023-04-01 | 2024-06-30 | Y | S070
1506807 | Construction Administration | \N | 2020-01-01 | 2021-11-30 | \N | S020
1506807 | Project Initiation | XX | 2019-12-01 | \N | \N | \N
1607303 | Contract Documentation | \N | 2018-02-12 | 2018-03-23 | \N | \N
1806903 | Others | \N | 2020-10-01 | 2020-12-31 | \N | \N
1806903 | Project Initiation | \N | 2020-10-01 | 2020-10-01 | \N | \N
20149 | Data Collection and Analysis | \N | 2020-09-09 | 2020-10-15 | \N | \N
20149 | Visioning and Options Generation | \N | 2020-10-26 | 2020-12-18 | \N | \N
20149 | Conceptual Masterplanning | \N | 2021-02-01 | 2021-04-16 | \N | \N
20149 | Project Initiation | \N | 2020-10-02 | 2020-10-02 | \N | \N
20111 | Project Initiation | \N | 2020-06-04 | 2020-06-04 | Y | \N
20138 | Architecture Test-Fit | \N | 2020-07-24 | 2020-07-24 | Y | \N
20138 | Project Initiation | \N | 2020-07-24 | 2020-07-24 | Y | \N
19218 | Project Initiation | \N | 2020-07-27 | 2020-07-27 | Y | \N
18182A | Marketing Collaterals | \N | 2019-09-01 | 2020-09-30 | \N | S050
18182A | Project Initiation | XXX | 2019-09-01 | 2019-09-01 | \N | \N
20062 | Concept Design | \N | 2020-06-26 | 2020-09-30 | N | \N
20062 | Design Development | DD | 2020-10-01 | 2022-03-31 | N | \N
20062 | Construction Administration | \N | 2022-07-01 | 2023-01-31 | N | \N
20062 | Project Initiation | \N | 2020-08-28 | 2020-08-28 | N | \N
20062 | Detailed Design | DD | 2020-10-01 | 2020-11-13 | N | \N
1712403 | Schematic Design | \N | 2018-08-01 | 2018-08-20 | \N | \N
1712403 | Project Initiation | \N | 2018-07-02 | 2018-07-02 | \N | \N
2006201 | Final Renderings | \N | 2020-10-22 | 2020-11-13 | \N | \N
2006201 | Project Initiation | \N | 2020-10-22 | 2020-10-22 | \N | \N
IP001 | Others | \N | 2019-06-01 | \N | \N | \N
1716301 | Construction Administration | \N | 2019-01-03 | 2020-08-31 | \N | \N
1716301 | Project Initiation | \N | 2019-01-03 | 2019-01-03 | \N | \N
20161 | Preliminary Design | \N | 2020-10-02 | 2020-10-15 | \N | \N
20161 | Detailed Design | \N | 2020-11-04 | 2020-12-16 | \N | \N
20161 | Project Initiation | \N | 2020-10-02 | 2020-10-02 | \N | \N
1410702 | Construction Administration | Extended Construction | 2020-11-01 | 2021-01-31 | \N | S020
1507524 | Construction Administration | \N | 2020-02-01 | \N | \N | \N
1507524 | Project Initiation | \N | 2020-02-01 | \N | \N | \N
1817205 | Preliminary Architecture and Engineering Design | AR | 2020-03-01 | 2020-12-31 | \N | S020
1817205 | Detailed Architecture and Engineering Design | AR | 2020-03-01 | 2021-03-31 | \N | S020
1817205 | Preliminary Architecture and Engineering Design | SUBCON | 2020-03-01 | 2020-03-01 | \N | S070
1817205 | Detailed Architecture and Engineering Design | SUBCON | 2020-03-01 | 2021-03-31 | \N | S070
1817206 | Preliminary Architecture and Engineering Design | \N | 2020-03-01 | 2020-03-01 | Y | \N
1817206 | Detailed Architecture and Engineering Design | \N | 2020-03-01 | 2021-08-31 | N | S020
1817206 | Detailed Architecture and Engineering Design | \N | 2020-03-01 | 2021-08-31 | N | S070
1817207 | Preliminary Architecture and Engineering Design | \N | 2020-03-01 | 2021-08-31 | N | \N
1817207 | Detailed Architecture and Engineering Design | \N | 2020-03-01 | 2021-08-31 | N | S020
1817207 | Detailed Architecture and Engineering Design | \N | 2020-03-01 | 2021-08-31 | N | S070
1713104 | Contract Documentation | L Project, MH to 1713105 | 2020-07-16 | 2020-07-16 | Y | \N
1713104 | Project Initiation | L Project, MH to 1713105 | 2020-07-16 | 2020-07-16 | Y | \N
1712408 | Contract Documentation | \N | 2020-06-16 | 2020-07-28 | \N | \N
1712408 | Project Initiation | \N | 2020-06-16 | 2020-06-16 | \N | \N
2006101 | Design Development | Detailed Design in SO | 2020-10-02 | 2020-12-31 | \N | \N
2006101 | Project Initiation | \N | 2020-10-02 | 2020-10-02 | \N | \N
20175 | Schematic Design | \N | 2020-11-16 | 2021-07-31 | \N | \N
20175 | Design Development | \N | 2021-07-01 | 2022-06-30 | \N | \N
20175 | Project Initiation | \N | 2020-11-16 | 2020-11-16 | \N | \N
17131H | Construction Administration | \N | 2020-02-01 | 2020-08-31 | \N | S020
17131H | Project Initiation | XXX | 2020-02-01 | 2020-02-01 | \N | \N
1310403 | Construction Administration | 12 months Construction Administration extension | 2019-06-01 | 2020-05-31 | N | \N
1705601 | Construction Administration | \N | 2018-04-27 | 2018-09-26 | \N | \N
1705601 | Project Initiation | \N | 2018-08-20 | 2018-08-20 | \N | \N
1705601 | Contract Documentation | \N | 2018-02-23 | 2018-08-17 | \N | \N
1312105 | Construction Administration | \N | 2018-05-01 | 2018-12-31 | \N | \N
1312105 | Project Initiation | \N | 2018-05-01 | 2018-05-01 | \N | \N
1305608 | Construction Administration | \N | 2018-10-01 | 2019-03-31 | \N | \N
1305608 | Project Initiation | \N | 2018-10-01 | 2018-10-01 | \N | \N
1701403 | Construction Administration | extended construction services | 2020-11-01 | 2021-04-30 | \N | S020
1701403 | Project Initiation | \N | 2020-11-01 | 2020-11-01 | \N | \N
1713105 | Contract Documentation | \N | 2018-11-01 | 2021-12-31 | \N | S020
1713105 | Project Initiation | xx | 2020-12-11 | 2020-12-11 | \N | \N
20180 | Conceptual Masterplanning | Data Collection + Visioning and Options Generation | 2020-11-03 | 2021-09-30 | N | S010
20180 | Project Initiation | Mobilization | 2020-11-03 | 2020-11-03 | \N | S010
20180 | Data Collection and Analysis | \N | 2020-11-04 | 2021-02-01 | \N | S010
20180 | Visioning and Options Generation | \N | 2020-11-04 | 2021-02-01 | \N | S010
20180 | Final Masterplanning | \N | 2021-09-30 | 2021-12-30 | N | S010
20185 | Project Initiation | \N | 2020-12-01 | 2020-12-01 | \N | S010
20185 | Concept Design | \N | 2021-01-06 | 2021-02-19 | \N | S010
1800905 | Contract Documentation | Construction Administration in SO | 2021-01-01 | 2021-02-28 | \N | S020
1800905 | Project Initiation | XXX | 2021-01-01 | 2021-01-01 | \N | \N
1800906 | Construction Administration | \N | 2020-12-01 | 2021-03-31 | \N | S020
1800906 | Project Initiation | XXX | 2020-12-01 | \N | \N | \N
1806901 | Tender | \N | 2018-10-01 | 2018-12-21 | N | S030
21002 | Concept Design | \N | 2021-01-21 | 2021-02-28 | \N | \N
21002 | Schematic Design | \N | 2021-01-21 | 2021-04-23 | \N | \N
21002 | Design Development | \N | 2021-04-26 | 2021-12-31 | \N | \N
21002 | Contract Documentation | \N | 2022-01-01 | 2022-12-31 | \N | \N
21002 | Construction Administration | \N | 2022-01-31 | 2022-12-31 | \N | \N
21002 | BIM LOD 300 MEPF Modelling | \N | 2022-01-01 | 2022-12-31 | \N | \N
21002 | Project Initiation | \N | 2021-01-21 | 2021-01-21 | \N | \N
21006 | Project Initiation | \N | 2021-01-18 | 2021-01-18 | Y | \N
21006 | Schematic Design | \N | 2021-01-18 | 2021-01-18 | Y | \N
21006 | Contract Documentation | \N | 2021-01-18 | 2021-01-18 | Y | \N
21006 | Construction Administration | \N | 2021-01-18 | 2021-01-18 | Y | \N
21006 | Design Development | \N | 2021-01-18 | 2021-01-18 | Y | \N
1806904 | Others | Contract Documentation in SO | 2020-06-01 | 2020-11-30 | \N | \N
20174 | Project Initiation | ID Retail & Amenities | 2021-01-01 | 2021-01-11 | \N | \N
20174 | Construction Administration | AR-CS (9 months) | 2021-01-01 | 2021-10-31 | \N | \N
20174 | Construction Administration | AR-Site Rep (9 months) | 2021-01-01 | 2021-10-31 | \N | \N
20174 | Project Initiation | BOH | 2021-01-01 | 2021-01-11 | \N | \N
20174 | Contract Documentation | BOH | 2021-02-01 | 2021-02-28 | \N | \N
20174 | Final Renderings | Rendering | 2021-02-01 | 2022-05-28 | Y | \N
20174 | Contract Documentation | ID Retail & Amenities | 2021-01-01 | 2022-10-31 | \N | \N
20174 | Construction Administration | ID Retail & Amenities (6months) | 2021-12-01 | 2022-05-31 | N | \N
20174 | Project Initiation | Rendering | 2021-01-01 | 2021-01-11 | \N | \N
21020 | Project Initiation | \N | 2021-02-10 | 2021-02-10 | Y | \N
21020 | Building Audit | \N | 2021-02-10 | 2021-03-09 | Y | \N
21030 | Project Initiation | \N | 2021-03-01 | 2021-03-01 | \N | S030
21030 | Schematic Design | \N | 2021-03-01 | 2021-03-31 | \N | S030
21030 | Contract Documentation | \N | 2021-04-01 | 2021-04-30 | \N | S030
21030 | Construction Administration | \N | 2021-11-01 | 2021-12-31 | \N | S030
2017501 | Project Initiation | \N | 2021-02-22 | 2021-02-22 | \N | \N
2017501 | Schematic Design | \N | 2021-02-22 | 2021-07-30 | \N | \N
2017501 | Design Development | \N | 2021-07-01 | 2022-06-30 | \N | \N
21017 | Project Initiation | \N | 2021-03-15 | 2021-03-15 | \N | S010
21017 | Conceptual Masterplanning | \N | 2021-03-15 | 2021-09-17 | \N | S010
21017 | Final Masterplanning | \N | 2021-09-17 | 2021-11-30 | \N | S010
12064 | Project Initiation | Inclusive of ID (BOH Offices & Facilities) | 2012-10-04 | 2012-10-04 | \N | \N
12064 | Schematic Design | Inclusive of ID (BOH Offices & Facilities) | 2012-10-04 | 2014-07-07 | \N | \N
12064 | Design Development | Inclusive of ID (BOH Offices & Facilities) | 2013-02-22 | 2015-12-02 | \N | \N
12064 | Contract Documentation | Inclusive of ID (BOH Offices & Facilities) | 2013-01-28 | 2016-11-15 | \N | \N
12064 | Construction Administration | Inclusive of ID (BOH Offices & Facilities) | 2013-02-14 | 2017-11-13 | \N | \N
12064 | Project Initiation | BIM Land Devt and Site Services | 2012-10-04 | 2012-10-04 | \N | \N
12064 | Clash Detection and Resolution | BIM Land Devt and Site Services | 2013-04-11 | 2015-07-15 | \N | \N
12064 | 2D Combined Services Drawings | BIM Land Devt and Site Services | 2013-04-11 | 2015-07-15 | \N | \N
12064 | Project Initiation | BIM AR & ST | 2012-10-04 | 2012-10-04 | \N | \N
12064 | Clash Detection and Resolution | BIM AR & ST | 2013-04-11 | 2015-07-15 | \N | \N
12064 | 2D Combined Services Drawings | BIM AR & ST | 2013-04-11 | 2015-07-15 | \N | \N
12064 | Project Initiation | BIM MEPF | 2012-10-04 | 2012-10-04 | \N | \N
12064 | Clash Detection and Resolution | BIM MEPF | 2014-07-14 | 2015-07-15 | \N | \N
12064 | 2D Combined Services Drawings | BIM MEPF | 2014-07-14 | 2015-07-15 | \N | \N
10011 | Contract Documentation | \N | 2011-06-01 | 2014-11-30 | \N | \N
10011 | Construction Administration | \N | 2011-10-01 | 2015-03-31 | \N | \N
10011 | Construction Administration | XX | 2011-10-01 | 2014-02-28 | \N | \N
10011 | Construction Administration | XX | 2014-03-01 | 2015-02-28 | \N | \N
10011 | Project Initiation | \N | 2011-03-01 | 2011-03-01 | \N | \N
10011 | Schematic Design | \N | 2011-03-01 | 2011-04-01 | \N | \N
10011 | Design Development | \N | 2011-04-01 | 2011-07-01 | \N | \N
16061 | Project Initiation | \N | 2016-10-24 | 2016-10-24 | \N | S020
16061 | Schematic Design | \N | 2016-10-24 | 2016-11-30 | \N | S020
16061 | Contract Documentation | Scope Aborted | 2016-12-01 | 2017-01-31 | \N | S020
16061 | Construction Administration | Scope Aborted | 2017-02-01 | 2018-05-31 | \N | S020
1106809 | Final Masterplanning | \N | 2014-09-01 | 2014-11-07 | N | \N
17162 | Project Initiation | \N | 2017-04-12 | 2017-04-12 | \N | \N
17162 | Contract Documentation | \N | 2017-04-12 | 2018-02-28 | \N | \N
17162 | Construction Administration | \N | 2018-03-01 | 2018-12-31 | \N | \N
1410701 | Others | Fee included in 14107 | 2017-09-07 | 2017-10-07 | \N | S020
\N | Project Initiation | \N | 2018-07-09 | 2018-07-09 | \N | \N
\N | Contract Documentation | \N | 2018-07-09 | 2018-08-15 | \N | \N
\N | Construction Administration | \N | 2018-08-16 | 2018-12-15 | \N | \N
14018Z | Project Initiation | \N | 2017-12-11 | 2017-12-11 | Y | \N
14018Z | Schematic Design | \N | 2017-12-11 | 2017-12-11 | Y | \N
14018Z | Contract Documentation | \N | 2017-12-11 | 2017-12-11 | Y | \N
14018Z | Construction Administration | \N | 2017-12-11 | 2017-12-11 | Y | \N
13059 | Project Initiation | \N | 2013-10-12 | 2013-10-12 | \N | S020
13059 | Schematic Design | Preliminary Detailed Deisgn | 2013-10-12 | 2014-05-30 | \N | S020
13059 | Design Development | Detailed Design | 2014-06-01 | 2014-08-30 | \N | S020
13059 | Contract Documentation | Tender | 2014-09-01 | 2014-12-31 | \N | S020
13059 | Construction Administration | \N | 2015-01-01 | 2017-07-30 | \N | S020
13059 | Construction Administration | Post Construction | 2017-08-01 | 2017-12-31 | \N | S020
10129 | Project Initiation | \N | 2010-09-24 | 2010-09-24 | \N | S020
10129 | Schematic Design | \N | 2010-09-24 | 2012-09-15 | \N | S020
10129 | Design Development | \N | 2012-09-16 | 2012-11-30 | \N | S020
10129 | Contract Documentation | \N | 2012-12-01 | 2013-06-30 | \N | S020
10129 | Construction Administration | \N | 2013-07-01 | 2016-07-30 | \N | S020
13006 | Project Initiation | \N | 2013-01-01 | 2013-01-01 | \N | S030
13006 | Schematic Design | \N | 2013-01-01 | 2013-04-30 | \N | S030
13006 | Design Development | \N | 2013-05-01 | 2013-11-30 | \N | S030
13006 | Contract Documentation | \N | 2013-12-01 | 2014-12-30 | \N | S030
13006 | Construction Administration | \N | 2015-01-01 | 2015-10-31 | \N | S030
13006 | Others | \N | 2015-11-01 | 2015-12-30 | \N | S030
21011 | Project Initiation | \N | 2021-02-15 | 2021-02-15 | \N | S060
21011 | BIM LOD 300 Architecture and Structural Modelling | \N | 2021-03-01 | 2021-04-29 | \N | S060
21011 | BIM LOD 300 MEPF Modelling | \N | 2021-07-01 | 2021-09-30 | \N | S060
21011 | Clash Detection and Resolution | 75% COMPLETION | 2021-10-01 | 2021-11-30 | Y | S060
21011 | 2D Combined Services Drawings | ABORTED STAGE | 2022-04-01 | 2022-04-01 | Y | S060
19180J | Design Development | 50% DD | 2021-02-28 | 2021-04-24 | N | S020
19180J | Design Development | 100% DD | 2021-05-19 | 2021-07-18 | N | S020
19180J | Contract Documentation | 50% CD | 2021-09-01 | 2021-10-14 | N | S020
19180J | Contract Documentation | 100% CD | 2022-02-01 | 2023-02-28 | N | S020
19180J | Construction Administration | \N | 2024-01-01 | 2026-12-31 | Y | S020
1711501 | Project Initiation | \N | 2020-10-20 | 2020-10-20 | \N | \N
1711501 | Schematic Design | \N | 2020-10-21 | 2020-11-05 | \N | \N
1711501 | Design Development | \N | 2020-11-06 | 2020-11-13 | \N | \N
1711501 | Contract Documentation | \N | 2020-11-14 | 2020-11-27 | \N | \N
1711502 | Project Initiation | \N | 2020-10-19 | 2020-10-19 | N | S020
1711502 | Schematic Design | \N | 2020-10-20 | 2020-11-04 | N | S020
1711502 | Design Development | \N | 2020-11-05 | 2020-11-30 | N | S020
1711502 | Contract Documentation | \N | 2020-12-01 | 2020-12-14 | N | S020
16069 | Project Initiation | \N | 2016-02-01 | 2016-02-01 | Y | \N
16069 | Schematic Design | \N | 2016-02-06 | 2016-02-01 | Y | \N
16069 | Design Development | \N | 2016-02-01 | 2016-02-01 | Y | \N
16069 | Contract Documentation | \N | 2016-02-01 | 2016-02-01 | Y | \N
16069 | Construction Administration | \N | 2016-02-01 | 2016-02-01 | Y | \N
1300804 | Construction Administration | \N | 2017-01-28 | 2017-06-28 | N | \N
1303801 | Contract Documentation | \N | 2017-08-25 | 2017-12-31 | \N | \N
1303802 | Contract Documentation | \N | 2017-08-25 | 2017-12-31 | \N | \N
1306301 | Schematic Design | \N | 2014-04-15 | 2014-06-15 | \N | \N
1405502 | Design Development | \N | 2016-09-26 | 2016-12-31 | N | \N
1409301 | Contract Documentation | \N | 2016-05-24 | 2016-12-31 | N | \N
1506903 | Contract Documentation | \N | 2017-12-07 | 2017-12-31 | N | S020
1722301 | Schematic Design | \N | 2019-04-25 | 2019-04-25 | N | \N
17013 | Project Initiation | \N | 2017-01-12 | 2017-01-12 | \N | \N
17013 | Conceptual Masterplanning | \N | 2017-02-12 | 2017-03-12 | \N | \N
17013 | Final Masterplanning | \N | 2017-04-01 | 2017-06-01 | \N | \N
15024 | Project Initiation | \N | 2016-01-01 | 2016-01-01 | \N | \N
15024 | Schematic Design | \N | 2016-01-01 | 2016-03-31 | \N | \N
15024 | Contract Documentation | \N | 2016-04-01 | 2016-08-31 | \N | \N
15024 | Construction Administration | \N | 2016-09-01 | 2019-08-31 | \N | \N
20126 | Project Initiation | \N | 2021-04-01 | 2021-04-01 | N | \N
20126 | Schematic Design | \N | 2021-04-01 | 2022-03-31 | N | \N
20126 | Design Development | \N | 2022-04-01 | 2024-07-31 | N | \N
20126 | Contract Documentation | \N | 2022-09-02 | 2024-12-31 | N | \N
20126 | Construction Administration | \N | 2025-01-01 | 2026-12-31 | N | \N
21041 | Project Initiation | \N | 2021-03-25 | 2021-03-25 | \N | \N
21041 | Concept Design | CANCELLED | 2021-04-01 | 2021-05-18 | \N | \N
1410703 | Construction Administration | \N | 2021-02-01 | 2021-04-30 | \N | S020
20175D | Project Initiation | \N | 2021-04-26 | 2021-04-26 | \N | \N
20175D | Animation | Preliminary | 2021-04-26 | 2021-07-31 | \N | \N
20175D | Animation | Final | 2021-06-01 | 2022-01-31 | \N | \N
21005 | Project Initiation | \N | 2021-02-01 | 2021-02-01 | \N | S020
21005 | Conceptual Masterplanning | \N | 2021-03-01 | 2021-07-31 | \N | S010
21005 | Final Masterplanning | \N | 2021-07-01 | 2022-12-31 | Y | S010
21005 | Preliminary Design | \N | 2021-03-01 | 2021-12-31 | \N | S020
21005 | Detailed Design | \N | 2021-07-01 | 2022-12-31 | Y | S020
21005 | Construction Administration | \N | 2024-01-01 | 2024-09-30 | Y | S020
21005 | Conceptual Masterplanning | Infrastructure & Civil | 2021-03-01 | 2022-12-31 | Y | S070
21005 | Final Masterplanning | Infrastructure & Civl | 2021-07-01 | 2022-12-31 | Y | S070
21005 | Preliminary Design | Engineering for Model Units | 2021-03-01 | 2022-12-31 | Y | S070
21005 | Detailed Design | Engineering for Model Units | 2021-07-01 | 2022-12-31 | Y | S070
21005 | Construction Administration | Engineering for Model Units | 2024-01-01 | 2024-09-30 | Y | S070
1410704 | Construction Administration | \N | 2021-05-01 | 2021-07-31 | \N | S020
1817201 | Preliminary Architecture and Engineering Design | \N | 2019-01-08 | \N | \N | \N
1817201 | Detailed Architecture and Engineering Design | \N | 2019-06-02 | \N | \N | \N
1817201 | Construction Administration | \N | 2019-11-01 | 2022-10-31 | \N | \N
1817202 | Preliminary Architecture and Engineering Design | \N | 2019-01-08 | \N | \N | \N
1817202 | Detailed Architecture and Engineering Design | \N | 2019-06-02 | \N | \N | \N
1817202 | Construction Administration | \N | 2019-11-01 | 2022-10-31 | \N | \N
21048 | Project Initiation | T1 | 2021-05-28 | 2021-05-28 | N | S020
21048 | Concept Design | T1 | 2021-05-28 | 2021-07-17 | N | S020
21048 | Detailed Design | 50% Completion T1 | 2021-07-17 | 2021-11-30 | N | S020
21048 | Detailed Design | 100% Completion T1 | 2021-08-14 | 2022-01-22 | N | S020
21048 | Construction Administration | 18 months T1 | 2025-01-01 | 2026-06-30 | N | S020
21048 | Project Initiation | LOD300 T1 | 2022-01-17 | 2022-01-17 | N | S060
21048 | BIM LOD 300 Architecture and Structural Modelling | LOD300 T1 | 2022-01-17 | 2022-04-30 | N | S060
21048 | BIM LOD 300 MEPF Modelling | LOD300 T1 | 2022-01-17 | 2022-04-30 | N | S060
21048 | Clash Detection and Resolution | LOD300 T1 | 2022-01-17 | 2022-04-30 | N | S060
21048 | 2D Combined Services Drawings | LOD300 T1 | 2022-01-17 | 2022-04-30 | N | S060
21048 | Project Initiation | T2 | 2021-05-28 | 2021-05-28 | N | S020
21048 | Concept Design | T2 | 2021-05-28 | 2021-07-17 | N | S020
21048 | Detailed Design | 50% Completion T2 | 2023-06-01 | 2023-08-31 | N | S020
21048 | Detailed Design | 100% Completion T2 | 2023-09-01 | 2024-06-30 | N | S020
21048 | Construction Administration | 18 months T2 | 2025-01-01 | 2026-06-30 | N | S020
21048 | Project Initiation | LOD300 T2 | 2024-01-01 | 2024-01-01 | N | S060
21048 | BIM LOD 300 Architecture and Structural Modelling | LOD300 T2 | 2024-01-01 | 2024-06-30 | N | S060
21048 | BIM LOD 300 MEPF Modelling | LOD300 T2 | 2024-01-01 | 2024-06-30 | N | S060
21048 | Clash Detection and Resolution | LOD300 T2 | 2024-01-01 | 2024-06-30 | N | S060
21048 | 2D Combined Services Drawings | LOD300 T2 | 2024-01-01 | 2024-06-30 | N | S060
21048 | Tender | \N | 2022-05-01 | 2024-12-31 | N | \N
21042 | Project Initiation | \N | 2021-05-26 | 2021-05-26 | \N | S040
21042 | Visioning and Options Generation | \N | 2021-05-26 | 2021-06-16 | \N | S040
21042 | Concept Design | \N | 2021-06-16 | 2021-08-06 | \N | S040
21014 | Project Initiation | \N | 2021-02-01 | 2021-02-01 | Y | \N
21014 | Preliminary Design | \N | 2021-02-01 | 2021-02-01 | Y | \N
21014 | Detailed Design | \N | 2021-02-01 | 2021-02-01 | Y | \N
21014 | Tender | \N | 2021-02-01 | 2021-02-01 | Y | \N
21014 | Construction Administration | \N | 2021-02-01 | 2021-02-01 | Y | \N
21014 | Design Development | \N | 2021-02-01 | 2021-02-01 | Y | \N
1800907 | Construction Administration | \N | 2021-04-01 | 2021-06-30 | \N | S020
1800908 | Construction Administration | \N | 2021-07-01 | 2021-09-30 | \N | S020
1818201 | Detailed Design | AR | 2021-06-01 | 2023-05-31 | N | S020
1818201 | Detailed Design | SUBCON | 2021-06-01 | 2023-05-31 | N | S070
21028 | Project Initiation | AR | 2021-03-01 | 2021-03-01 | N | S020
21028 | Schematic Design | AR: Concept Design | 2021-03-01 | 2024-02-28 | N | S020
20107 | Project Initiation | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Schematic Design | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Design Development | AR 2023 | 2023-01-01 | 2024-02-15 | N | S020
20107 | Contract Documentation | AR 2023 | 2023-04-01 | 2024-04-05 | N | S020
20107 | Project Initiation | AR + SUBCON 2021 | 2021-01-01 | 2021-01-01 | N | S020
20107 | Schematic Design | AR + SUBCON 2022 | 2021-01-01 | 2023-02-28 | N | S020
20107 | Design Development | AR+ SUBCON 2022 | 2021-06-01 | 2024-02-15 | N | S020
20107 | Contract Documentation | SUBCON 2023 | 2023-04-01 | 2024-04-05 | N | S070
20107 | Project Initiation | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Schematic Design | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Design Development | SUBCON 2023 | 2023-01-01 | 2024-02-15 | N | S070
20107 | Contract Documentation | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Project Initiation | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Schematic Design | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Design Development | N/A | 2021-01-01 | 2021-01-01 | Y | \N
20107 | Contract Documentation | N/A | 2021-01-01 | 2021-01-01 | Y | \N
1713106 | Construction Administration | AR | 2021-03-01 | 2021-10-31 | N | S020
1701404 | Project Initiation | \N | 2021-05-01 | 2021-05-01 | \N | \N
1701404 | Construction Administration | extended construction | 2021-05-01 | 2021-12-31 | \N | \N
21058 | Project Initiation | \N | 2021-06-04 | 2021-06-04 | N | S030
21058 | Concept Design | 7F Concept/SD | 2021-06-04 | 2021-11-03 | N | S030
21058 | Tender | 7F Tender | 2021-10-01 | 2021-11-15 | N | S030
21058 | Concept Design | Ground Floor: ON HOLD | 2023-03-01 | 2023-03-31 | Y | S030
21058 | Tender | Ground Floor: ON HOLD | 2023-04-01 | 2023-04-30 | Y | S030
21058 | Concept Design | 5th Floor | 2021-11-08 | 2022-07-15 | N | S030
21058 | Tender | 5th Floor | 2022-02-07 | 2022-07-29 | N | S030
21058 | Concept Design | 4th Floor | 2021-11-08 | 2022-07-15 | N | S030
21058 | Tender | 4th Floor | 2022-02-07 | 2022-07-29 | N | S030
21058 | Concept Design | 3rd Floor | 2022-02-07 | 2022-07-29 | N | S030
21058 | Tender | 3rd Floor | 2022-07-01 | 2022-11-11 | N | S030
21058 | Concept Design | 8th Floor | 2022-10-27 | 2023-02-03 | N | S030
21058 | Tender | 8th Floor | 2023-02-02 | 2023-03-31 | N | S030
1507526 | Construction Administration | \N | 2020-11-01 | \N | \N | \N
1817208 | Preliminary Architecture and Engineering Design | SDP RDAED | 2020-08-07 | 2020-10-01 | N | S020
1817208 | Preliminary Architecture and Engineering Design | SDP RDAED | 2020-08-07 | 2020-10-01 | N | S070
1507528 | Construction Administration | 5th Extension | 2021-08-01 | 2021-12-31 | \N | \N
21099 | Conceptual Masterplanning | Competition | 2021-07-21 | 2022-05-31 | N | \N
21099 | Data Collection and Analysis | \N | 2021-10-01 | 2023-06-30 | N | S010
21099 | Project Initiation | \N | 2021-07-21 | 2021-07-21 | \N | S010
21099 | Conceptual Masterplanning | \N | 2023-07-01 | 2024-06-30 | N | S010
2101701 | Project Initiation | \N | 2021-07-01 | 2021-07-01 | \N | S010
2101701 | Conceptual Masterplanning | \N | 2021-07-01 | 2021-09-30 | \N | S010
2101701 | Final Masterplanning | \N | 2021-09-30 | 2021-11-30 | \N | S010
21007 | Project Initiation | \N | 2021-05-01 | 2021-05-01 | \N | S020
21007 | Concept Design | \N | 2021-06-01 | 2021-07-31 | \N | S020
21007 | Schematic Design | \N | 2021-09-01 | 2023-06-30 | Y | S020
21007 | Design Development | \N | 2023-07-01 | 2023-12-31 | Y | S020
21007 | Contract Documentation | \N | 2024-01-01 | 2024-05-30 | Y | S020
21007 | Construction Administration | VALIDATE NUMBER OF MONTHS TO PM | 2024-04-01 | 2025-11-30 | Y | S020
1302903 | Construction Administration | \N | 2021-06-01 | 2021-12-31 | \N | \N
21074 | Project Initiation | Banyan GF, Podium T1-3 & BOH | 2021-07-19 | 2021-07-19 | N | S030
21074 | Preliminary Design | Banyan T1 ID & EGD | 2022-01-17 | 2023-12-31 | Y | S030
21074 | Detailed Design | Banyan T1 ID & EGD | 2024-01-01 | 2024-06-30 | Y | S030
21074 | Construction Administration | Banyan T1 ID & EGD | 2024-07-01 | 2028-06-30 | Y | S030
21074 | Preliminary Design | Banyan T2-3 ID & EGD | 2022-07-01 | 2024-03-31 | Y | S030
21074 | Detailed Design | Banyan T2-3 ID & EGD | 2024-04-01 | 2024-09-30 | Y | S030
21074 | Construction Administration | Banyan T2-3 ID & EGD | 2024-10-01 | 2028-09-30 | Y | S030
21074 | Preliminary Design | GF & Amenities ID & EGD | 2022-01-17 | 2023-12-31 | Y | S030
21074 | Detailed Design | GF & Amenities ID & EGD | 2024-01-01 | 2024-06-30 | Y | S030
21074 | Construction Administration | GF & Amenities ID & EGD | 2024-07-01 | 2028-06-30 | Y | S030
21074 | Preliminary Design | Podium ID & EGD | 2022-11-15 | 2023-12-31 | Y | S030
21074 | Detailed Design | Podium ID & EGD | 2024-01-01 | 2024-06-30 | Y | S030
21074 | Construction Administration | Podium ID & EGD | 2024-07-01 | 2028-06-30 | Y | S030
21074 | Preliminary Design | BOH ID & EGD | 2022-07-01 | 2022-11-30 | N | S030
21074 | Detailed Design | BOH ID & EGD | 2022-12-01 | 2023-12-31 | Y | S030
21074 | Construction Administration | BOH ID & EGD | 2024-01-01 | 2027-12-31 | Y | S030
21100 | Conceptual Masterplanning | \N | 2021-07-23 | 2021-08-23 | \N | \N
1506809 | Construction Administration | \N | 2021-07-01 | 2021-12-31 | \N | S020
2017502 | Project Initiation | \N | 2021-06-18 | 2021-06-18 | \N | \N
2017502 | Preliminary Renderings | \N | 2021-06-21 | 2021-07-30 | \N | \N
2017502 | Final Renderings | \N | 2021-08-02 | 2022-02-28 | \N | \N
13102J | Project Initiation | \N | 2013-12-15 | 2013-12-15 | \N | \N
13102J | Schematic Design | \N | 2015-09-01 | 2015-10-31 | \N | \N
13102J | Design Development | \N | 2015-11-01 | 2016-01-31 | \N | \N
13102J | Contract Documentation | \N | 2016-02-01 | 2016-04-30 | \N | \N
13102J | Construction Administration | \N | 2017-10-01 | 2019-03-31 | \N | \N
13102J | Project Initiation | Structural | 2013-12-15 | 2013-12-15 | \N | \N
13102J | Schematic Design | Structural | 2015-09-01 | 2015-10-31 | \N | \N
13102J | Design Development | Structural | 2015-11-01 | 2016-01-31 | \N | \N
13102J | Contract Documentation | Structural | 2016-02-01 | 2016-04-30 | \N | \N
13102J | Construction Administration | Structural | 2017-10-01 | 2019-03-31 | \N | \N
13102J | Project Initiation | Mechanical | 2013-12-15 | 2013-12-15 | \N | \N
13102J | Schematic Design | Mechanical | 2015-09-01 | 2015-10-31 | \N | \N
13102J | Design Development | Mechanical | 2015-11-01 | 2016-01-31 | \N | \N
13102J | Contract Documentation | Mechanical | 2016-02-01 | 2016-04-30 | \N | \N
13102J | Construction Administration | Mechanical | 2017-10-01 | 2019-03-31 | \N | \N
13102J | Project Initiation | Electrical | 2013-12-15 | 2013-12-15 | \N | \N
13102J | Schematic Design | Electrical | 2015-09-01 | 2015-10-31 | \N | \N
13102J | Design Development | Electrical | 2015-11-01 | 2016-01-31 | \N | \N
13102J | Contract Documentation | Electrical | 2016-02-01 | 2016-04-30 | \N | \N
13102J | Construction Administration | Electrical | 2017-10-01 | 2019-03-31 | \N | \N
13102J | Project Initiation | Sanitary & Fire Protection | 2013-12-15 | 2013-12-15 | \N | \N
13102J | Schematic Design | Sanitary & Fire Protection | 2015-09-01 | 2015-10-31 | \N | \N
13102J | Design Development | Sanitary & Fire Protection | 2015-11-01 | 2016-01-31 | \N | \N
13102J | Contract Documentation | Sanitary & Fire Protection | 2016-02-01 | 2016-04-30 | \N | \N
13102J | Construction Administration | Sanitary & Fire Protection | 2017-10-01 | 2019-03-31 | \N | \N
16039J01 | Contract Documentation | \N | 2021-10-01 | 2022-03-31 | \N | S020
16039J02 | Contract Documentation | \N | 2021-11-01 | 2022-01-31 | \N | S020
16039J03 | Contract Documentation | \N | 2021-10-12 | 2022-04-29 | \N | S020
16039J04 | Contract Documentation | AR & PG CD VO-04 | 2021-11-01 | 2022-02-28 | \N | S020
16039J06 | Contract Documentation | AR, ID, PG/SAN, EE, ME VO-06 | 2021-10-01 | 2022-07-31 | \N | S020
16039J07 | Contract Documentation | AR, PG/SAN, ME, EE VO-07 | 2021-12-01 | 2022-05-31 | \N | S020
16039J09 | Contract Documentation | CD VO-09 AR/ PG/ ME/ EE | 2021-11-01 | 2022-04-30 | \N | S020
16039J10 | Contract Documentation | CD VO-10 AR, PG/SAN, ME, EE | 2021-11-01 | 2022-02-28 | \N | S020
16039J11 | Contract Documentation | CD VO-11 for AR, PG/SAN, ME, EE | 2021-11-01 | 2022-02-28 | \N | S020
16039J12 | Contract Documentation | \N | 2021-11-01 | 2022-02-28 | \N | S020
1507304 | Construction Administration | \N | 2021-04-01 | 2021-05-31 | N | \N
2003901 | Contract Documentation | \N | 2021-03-01 | 2021-12-31 | \N | S020
2003902 | Contract Documentation | \N | 2021-03-01 | 2024-02-29 | N | S020
2003903 | Contract Documentation | \N | 2021-03-01 | 2024-02-29 | N | S020
20095 | Project Initiation | \N | 2022-11-28 | 2022-01-01 | \N | S020
20095 | Concept Design | XXX | 2022-11-28 | 2022-11-28 | Y | S020
20095 | Schematic Design | \N | 2022-12-01 | 2023-01-31 | N | S020
20095 | Design Development | \N | 2023-02-01 | 2024-06-30 | N | S020
20095 | Contract Documentation | \N | 2024-07-01 | 2024-08-31 | N | S020
20095 | Construction Administration | Dates to be confirmed | 2024-09-01 | 2027-08-31 | N | S020
21078 | Project Initiation | \N | 2021-07-12 | 2021-07-12 | N | \N
21078 | Schematic Design | CN / SD | 2021-07-15 | 2021-11-08 | N | \N
21078 | Design Development | Tower2 Podium & Basement | 2021-11-09 | 2022-09-30 | Y | \N
21078 | Contract Documentation | Tower2 Podium & Basement | 2022-10-01 | 2023-03-31 | Y | \N
21078 | Design Development | Tower3 | 2023-01-31 | 2023-06-30 | Y | \N
21078 | Contract Documentation | Tower3 | 2023-07-31 | 2023-12-31 | Y | \N
21078 | Construction Administration | \N | 2024-01-01 | 2027-12-31 | Y | \N
1410705 | Construction Administration | \N | 2021-08-01 | 2021-10-31 | \N | S020
16039 | Project Initiation | \N | 2016-01-11 | 2016-01-11 | \N | S020
16039 | Schematic Design | \N | 2016-06-28 | 2016-09-01 | \N | S020
16039 | Design Development | \N | 2017-01-08 | 2017-04-07 | \N | S020
16039 | Project Initiation | ID -Mall | 2016-01-11 | 2016-01-11 | \N | S030
16039 | Schematic Design | ID - Mall | 2016-06-28 | 2016-09-01 | \N | S030
16039 | Design Development | ID - Mall | 2017-01-08 | 2017-04-07 | \N | S030
16039 | Project Initiation | ID - Hotel | 2016-01-11 | 2016-01-11 | \N | S030
16039 | Schematic Design | ID - Hotel | 2016-06-28 | 2016-09-01 | \N | S030
16039 | Design Development | ID - Hotel | 2017-01-08 | 2017-04-07 | \N | S030
16039 | Project Initiation | EGD - Mall | 2016-01-11 | 2016-01-11 | \N | S040
16039 | Schematic Design | EGD - Mall | 2016-06-28 | 2016-09-01 | \N | S040
16039 | Design Development | EGD - Mall | 2017-01-08 | 2017-04-07 | \N | S040
16039 | Project Initiation | Structural | 2016-01-11 | 2016-01-11 | \N | S070
16039 | Schematic Design | Structural | 2016-06-28 | 2016-09-01 | \N | S070
16039 | Design Development | Structural | 2017-01-08 | 2017-04-07 | \N | S070
16039 | Project Initiation | Mechanical | 2016-01-11 | 2016-01-11 | \N | S070
16039 | Schematic Design | Mechanical | 2016-06-28 | 2016-09-01 | \N | S070
16039 | Design Development | Mechanical | 2017-01-08 | 2017-04-07 | \N | S070
16039 | Project Initiation | Electrical | 2016-01-11 | 2016-01-11 | \N | S070
16039 | Schematic Design | Electrical | 2016-06-28 | 2016-09-01 | \N | S070
16039 | Design Development | Electrical | 2017-01-08 | 2017-04-07 | \N | S070
16039 | Project Initiation | Sanitary Plumbing Design | 2016-01-11 | 2016-01-11 | \N | S070
16039 | Schematic Design | Sanitary Plumbing Design | 2016-06-28 | 2016-09-01 | \N | S070
16039 | Design Development | Sanitary Plumbing Design | 2017-01-08 | 2017-04-07 | \N | S070
16039 | Project Initiation | Fire Protection | 2016-01-11 | 2016-01-11 | \N | S070
16039 | Schematic Design | Fire Protection | 2016-06-28 | 2016-09-01 | \N | S070
16039 | Design Development | Fire Protection | 2017-01-08 | 2017-04-07 | \N | S070
16039 | Project Initiation | Landscape | 2016-01-11 | 2016-01-11 | \N | S070
16039 | Schematic Design | Fire Protection | 2016-06-28 | 2016-09-01 | \N | S070
16039 | Design Development | Fire Protection | 2017-01-08 | 2017-04-07 | \N | S070
16039 | Contract Documentation | \N | 2017-12-15 | 2018-04-14 | \N | S070
1819202 | Construction Administration | additional area | 2021-06-01 | 2021-11-30 | \N | \N
20190 | Project Initiation | \N | 2021-07-21 | 2021-07-21 | \N | S020
20190 | Schematic Design | \N | 2021-08-01 | 2021-08-31 | \N | S020
20190 | Contract Documentation | 50% CD (AR/ID) | 2021-09-01 | 2021-10-31 | \N | S020
20190 | Contract Documentation | 100% CD (AR/ID) | 2021-11-01 | 2021-12-31 | \N | S020
20190 | Construction Administration | \N | 2022-01-01 | 2022-08-31 | \N | S020
1716302 | Construction Administration | \N | 2020-06-01 | 2021-01-31 | \N | \N
1716802 | Construction Administration | ID | 2020-03-01 | 2020-10-31 | Y | S030
1825601 | Construction Administration | AR | 2020-07-01 | 2020-10-31 | \N | S020
1923801 | Construction Administration | ID | 2021-01-01 | 2021-07-31 | \N | S030
1908103 | Construction Administration | \N | 2022-01-01 | 2022-03-31 | \N | \N
1816001 | Contract Documentation | ID | 2022-04-01 | 2022-04-01 | \N | S030
1816001 | Construction Administration | ID | 2022-04-01 | 2022-04-01 | \N | \N
21111 | Project Initiation | \N | 2021-08-27 | 2021-08-27 | N | \N
21111 | Contract Documentation | \N | 2021-08-30 | 2021-11-30 | N | \N
21111 | Construction Administration | \N | 2023-01-01 | 2024-01-31 | N | \N
21124 | Project Initiation | \N | 2021-09-16 | 2021-09-16 | \N | \N
21124 | Concept Design | Bldg 1 Phase 1 | 2021-09-16 | 2022-02-04 | \N | \N
21124 | Project Initiation | \N | 2022-02-07 | 2022-02-07 | \N | \N
21124 | Concept Design | Bldg 2-4 Phase 2 | 2022-02-07 | 2022-04-30 | \N | \N
21096 | Project Initiation | AR | 2021-09-16 | 2021-09-16 | N | S030
21096 | Schematic Design | AR | 2021-09-16 | 2022-01-31 | N | S030
21096 | Design Development | AR | 2022-02-01 | 2022-06-30 | N | S030
21096 | Contract Documentation | AR | 2022-06-21 | 2022-09-30 | N | S030
21096 | Construction Administration | AR | 2023-11-01 | 2024-06-30 | N | S030
2017503 | Project Initiation | \N | 2021-09-02 | 2021-09-02 | \N | \N
2017503 | Final Renderings | \N | 2021-09-02 | 2022-06-30 | \N | \N
1507527 | Construction Administration | \N | 2021-02-01 | \N | \N | \N
1507701 | Construction Administration | 1st CS Extension | 2021-06-01 | 2023-05-31 | N | S020
1711503 | Concept Design | \N | 2021-10-01 | 2021-11-30 | N | S020
1711503 | Contract Documentation | \N | 2022-01-25 | 2023-02-28 | N | S020
21128 | Project Initiation | \N | 2021-09-21 | 2021-09-21 | \N | S020
21128 | Preliminary Design | \N | 2021-09-22 | 2022-01-31 | \N | S020
1506904 | Construction Administration | CS Extension | 2021-01-01 | 2022-06-30 | \N | S020
21125 | Project Initiation | \N | 2021-09-01 | 2021-09-01 | \N | S020
21125 | Preliminary Design | \N | 2021-10-01 | 2021-10-31 | \N | S020
21125 | Detailed Design | \N | 2021-11-01 | 2022-04-30 | \N | S020
21125 | Construction Administration | \N | 2022-03-01 | 2022-12-31 | \N | S020
11068 | Project Initiation | AR | 2011-06-01 | 2011-06-01 | \N | S020
11068 | Schematic Design | AR | 2011-06-01 | 2011-07-31 | \N | S020
11068 | Design Development | AR | 2011-08-01 | 2011-10-31 | \N | S020
11068 | Contract Documentation | AR | 2011-11-01 | 2012-03-31 | \N | S020
11068 | Construction Administration | AR | 2013-09-01 | 2017-08-31 | \N | S020
17068 | Project Initiation | \N | 2017-05-01 | 2017-05-01 | \N | S020
17068 | Preliminary Design | \N | 2017-05-01 | 2017-07-31 | \N | S020
17068 | Detailed Design | \N | 2017-08-01 | 2017-12-15 | \N | S020
17068 | Construction Administration | CANCELLED | 2018-02-01 | 2019-07-31 | N | S020
1800909 | Construction Administration | \N | 2021-10-01 | 2021-12-31 | \N | S020
21140 | Project Initiation | \N | 2021-10-12 | 2021-10-12 | N | \N
21140 | Schematic Design | \N | 2021-10-12 | 2022-04-01 | N | \N
21140 | Design Development | \N | 2023-02-21 | 2024-07-31 | N | \N
21140 | Contract Documentation | \N | 2024-08-01 | 2024-12-31 | N | \N
21140 | Construction Administration | \N | 2025-06-01 | 2026-05-31 | N | \N
21116 | Schematic Design | ID | 2021-10-14 | 2023-08-31 | Y | \N
21060 | Project Initiation | AR | 2021-07-26 | 2021-07-26 | N | S020
21060 | Schematic Design | AR | 2021-08-01 | 2022-05-31 | N | S020
21060 | Design Development | AR | 2021-10-01 | 2022-09-30 | N | S020
21060 | Contract Documentation | AR | 2022-10-01 | 2024-04-15 | N | S020
21060 | Construction Administration | AR | 2024-06-01 | 2028-05-31 | N | S020
1410706 | Construction Administration | \N | 2021-11-01 | 2022-01-31 | \N | S020
21130 | Project Initiation | \N | 2021-10-01 | 2021-10-01 | N | S010
21130 | Conceptual Masterplanning | \N | 2021-10-01 | 2024-12-31 | Y | S010
21130 | Final Masterplanning | Final Conceptual Masterplan | 2025-01-01 | 2025-02-28 | Y | S010
21029 | Project Initiation | \N | 2021-10-28 | 2021-10-28 | N | S060
21029 | BIM LOD 300 Architecture and Structural Modelling | Phase1 | 2022-02-01 | 2023-06-30 | N | S060
21029 | BIM LOD 300 MEPF Modelling | Phase1 | 2022-06-01 | 2023-06-30 | N | S060
21029 | Clash Detection and Resolution | ABORTED: Phase1-Initial | 2023-04-18 | 2023-06-30 | Y | S060
21029 | 2D Combined Services Drawings | ABORTED: Phase1 | 2024-07-01 | 2024-08-31 | Y | S060
21029 | 4D Quantity Take off | ABORTED: Phase1 | 2024-09-01 | 2024-10-31 | Y | S060
21029 | BIM LOD 300 Architecture and Structural Modelling | Phase2 - Initial | 2023-02-01 | 2023-07-11 | N | S060
21029 | BIM LOD 300 MEPF Modelling | ABORTED: Phase2 | 2024-09-01 | 2025-01-31 | Y | S060
21029 | Clash Detection and Resolution | ABORTED: Phase2 | 2025-02-01 | 2025-06-30 | Y | S060
21029 | 2D Combined Services Drawings | ABORTED: Phase2 | 2025-07-01 | 2025-09-30 | Y | S060
21029 | 4D Quantity Take off | ABORTED: Phase2 | 2025-10-01 | 2025-11-30 | Y | S060
21029 | Clash Detection and Resolution | ABORTED: Phase 1-Final | 2024-04-01 | 2024-06-30 | Y | S060
21029 | BIM LOD 300 Architecture and Structural Modelling | ABORTED: Phase2 -Final | 2024-07-11 | 2024-08-31 | Y | S060
21130J | Project Initiation | \N | 2021-10-01 | 2021-10-01 | N | S010
21130J | Conceptual Masterplanning | \N | 2021-10-01 | 2024-12-31 | Y | S010
21130J | Final Masterplanning | Final Conceptual Masterplanning | 2025-01-01 | 2025-02-28 | Y | S010
21064 | Construction Administration | Tax Declaration Document | 2021-07-01 | 2021-07-15 | \N | \N
21063 | Construction Administration | Supplementary Services, Tax Declaration Docs | 2021-07-15 | 2021-07-31 | \N | \N
1608502 | Construction Administration | ID CS Extension | 2021-09-01 | 2022-10-31 | \N | S020
1926102 | Contract Documentation | \N | 2021-10-29 | 2021-12-15 | \N | S020
1609401 | Construction Administration | 1st CS Ext: Construction Services Extension 1 | 2018-12-01 | 2019-12-31 | \N | \N
21153 | Concept Design | \N | 2021-10-26 | 2021-10-26 | Y | \N
1818202 | Detailed Design | \N | 2021-10-01 | 2024-05-31 | Y | S020
IP003 | Others | \N | 2021-10-26 | 2021-12-31 | \N | \N
1411003 | Construction Administration | 1st CS Extension | 2021-06-01 | 2021-08-31 | \N | \N
21087 | Project Initiation | \N | 2021-06-21 | 2021-06-21 | N | S020
21087 | Concept Design | \N | 2021-06-21 | 2021-11-15 | N | S020
21087 | Schematic Design | \N | 2021-11-15 | 2022-04-30 | N | S020
21087 | Design Development | \N | 2022-04-01 | 2024-04-15 | N | S020
21087 | Contract Documentation | \N | 2024-04-16 | 2024-12-31 | N | S020
21087 | Construction Administration | 40 months | 2025-01-01 | 2028-04-30 | N | S020
21087 | Post Construction Phase | \N | 2028-05-01 | 2028-09-30 | N | S020
21087 | Nothing Follows | XXX | 2021-06-21 | \N | Y | \N
1612412 | Schematic Design | \N | 2021-11-01 | 2022-03-31 | N | S020
1612412 | Design Development | Cancelled Scope | 2021-11-01 | 2021-11-01 | Y | S020
1612412 | Contract Documentation | Cancelled Scope | 2021-11-01 | 2021-11-01 | Y | S020
1612412 | Project Initiation | \N | 2021-11-01 | 2021-11-01 | N | S020
21093 | Project Initiation | \N | 2021-11-01 | 2021-11-01 | N | S060
21093 | BIM LOD 350 | DD (LOD350 + QTO) | 2023-05-01 | 2023-07-31 | Y | S060
21093 | Clash Detection and Resolution | CD (BIM report & QTO) | 2023-05-01 | 2023-07-31 | Y | S060
21093 | 2D Combined Services Drawings | FCD (Final BIM Report) | 2023-05-01 | 2023-07-31 | Y | S060
21093 | BIM LOD 350 | SUBCON: DD (LOD350 + QTO) | 2023-05-01 | 2023-07-31 | Y | S070
21093 | Clash Detection and Resolution | SUBCON: CD (BIM report & QTO) | 2023-05-01 | 2023-07-31 | Y | S070
21093 | 2D Combined Services Drawings | SUBCON: FCD (FINAL BIM REPORT) | 2023-05-01 | 2023-07-31 | Y | S070
21093 | Project Initiation | NOT USED | 2021-11-01 | 2021-11-01 | Y | \N
21093 | Project Initiation | SUBCON | 2021-11-01 | 2021-11-01 | Y | \N
21094 | Project Initiation | \N | 2021-11-01 | 2021-11-01 | \N | S060
21094 | BIM LOD 350 | DD (LOD350 + QTO) | 2023-02-01 | 2023-08-31 | Y | S060
21094 | Clash Detection and Resolution | CD (BIM REPORT & QTO) | 2023-05-01 | 2023-09-30 | Y | S060
21094 | 2D Combined Services Drawings | FCD (FINAL BIM REPORT) | 2023-05-01 | 2023-09-30 | Y | S060
21094 | Project Initiation | SUBCON | 2021-11-01 | 2021-11-01 | \N | S070
21094 | BIM LOD 350 | SUBCON: DD (LOD350 + QTO) | 2023-02-01 | 2023-08-31 | Y | S070
21094 | Clash Detection and Resolution | SUBCON: CD (BIM REPORT & QTO) | 2023-05-01 | 2023-09-30 | Y | S070
21094 | 2D Combined Services Drawings | SUBCON: FCD (FINAL BIM REPORT) | 2023-05-01 | 2023-09-30 | Y | S070
1607309 | Contract Documentation | \N | 2021-11-19 | 2021-12-10 | N | \N
21141 | Project Initiation | Data Center 700KW | 2021-11-15 | 2021-11-15 | N | S020
21141 | Schematic Design | Data Center 700KW | 2021-11-15 | 2022-09-30 | N | S020
21141 | Design Development | Data Center 700KW | 2022-01-20 | 2022-09-30 | N | S020
21141 | Detailed Design | Data Center 700KW | 2022-06-01 | 2022-09-30 | N | S020
21141 | Tender | Data Center 700KW Tender Docs | 2022-07-01 | 2022-10-31 | N | S020
21141 | Tender | Data Center 700KW Tender Evaluation | 2022-07-01 | 2022-11-30 | N | S020
21141 | Contract Documentation | Data Center 700KW 2 | 2022-06-01 | 2022-09-30 | Y | S020
21141 | Construction Administration | Data Center 700KW 2 | 2023-01-01 | 2024-03-30 | Y | S020
21141 | Schematic Design | Data Center 700KW 2 | 2022-04-01 | 2022-09-30 | N | S020
21141 | Design Development | Data Center 700KW 2 | 2022-05-01 | 2022-09-30 | N | S020
21141 | Detailed Design | Data Center 700KW 2 | 2022-07-01 | 2022-09-30 | N | S020
21141 | Tender | Data Center 700KW Tender Docss 2 | 2022-10-01 | 2022-10-31 | N | S020
21141 | Schematic Design | Data Center Phase 1 & 2, Admin Block and MP | 2021-11-15 | 2022-09-30 | N | S020
21141 | Schematic Design | Data Center Phase 1 & 2, Admin Block and MP 2 | 2022-05-01 | 2022-09-30 | N | S020
21141 | Design Development | Data Center Phase 1 & 2, Admin Block and MP | 2022-06-01 | 2022-09-30 | N | S020
21141 | Detailed Design | Data Center Phase 1 & 2, Admin Block and MP | 2022-09-01 | 2022-09-30 | N | S020
21141 | Tender | Data Center Phase 1 & 2, Admin Block and MP Tender Documentation | 2022-08-01 | 2022-10-31 | N | S020
21141 | Tender | Data Center Phase 1 & 2, Admin Block and MP Tender Evaluation | 2022-11-01 | 2022-11-30 | Y | S020
21141 | Contract Documentation | Data Center Phase 1 & 2, Admin Block and MP | 2022-12-01 | 2022-12-31 | Y | S020
21141 | Construction Administration | Data Center Phase 1 & 2, Admin Block and MP | 2023-01-01 | 2024-03-31 | Y | S020
21141 | Construction Administration | Practical completion and defects liability period | 2023-11-01 | 2024-03-31 | Y | S020
21141 | BIM Attendance | BIM Manager services during construction stage | 2023-01-01 | 2024-03-31 | Y | S060
21141 | Schematic Design | Facade | 2022-09-01 | 2022-12-01 | Y | S070
21141 | Design Development | Facade | 2022-09-01 | 2022-12-01 | Y | S070
21141 | Contract Documentation | Facade | 2022-10-01 | 2022-12-01 | Y | S070
21141 | Tender | Facade | 2022-10-01 | 2022-12-31 | Y | S070
21141 | Construction Administration | Facade | 2023-01-01 | 2024-03-31 | Y | S070
21141 | Schematic Design | Traffic Impact Analysis - Upon Submission of Draft Report | 2022-10-01 | 2022-12-01 | Y | S070
21141 | Schematic Design | Traffic Impact Analysis - Upon Submission of Final Report | 2022-12-01 | 2022-12-01 | Y | S070
16025Z | Project Initiation | \N | 2017-03-01 | 2021-03-01 | \N | \N
16025Z | Contract Documentation | \N | 2017-04-01 | 2017-04-30 | \N | \N
16025Z | Tender | \N | 2017-05-01 | 2017-05-31 | \N | \N
16025Z | Tender | \N | 2017-06-01 | 2017-06-30 | \N | \N
1602502 | Contract Documentation | \N | 2017-09-01 | 2017-09-30 | \N | \N
1602502 | Contract Documentation | \N | 2017-10-01 | 2017-10-31 | \N | \N
1602504 | Construction Administration | \N | 2017-10-01 | 2017-10-31 | \N | \N
1602504 | Construction Administration | \N | 2017-11-01 | 2017-11-30 | \N | \N
1602504 | Construction Administration | \N | 2017-12-01 | 2017-12-31 | \N | \N
1602504 | Construction Administration | \N | 2018-01-01 | 2018-01-31 | \N | \N
1805901 | Construction Administration | 1st CA/CS Extension | 2021-04-01 | 2021-07-31 | \N | \N
1908101 | Contract Documentation | \N | 2020-01-06 | 2020-04-30 | \N | \N
1908102 | Contract Documentation | \N | 2020-09-01 | 2020-11-06 | \N | \N
1305605 | Contract Documentation | \N | 2016-08-01 | 2016-09-30 | \N | \N
1701405 | Project Initiation | \N | 2022-01-01 | 2022-01-01 | \N | \N
1701405 | Detailed Design | \N | 2022-01-01 | 2022-02-28 | \N | \N
1701405 | Construction Administration | \N | 2022-03-01 | 2022-09-30 | \N | \N
21150 | Final Renderings | \N | 2021-10-27 | 2021-11-18 | \N | S050
21168 | Project Initiation | \N | 2021-11-15 | 2021-11-15 | \N | \N
21168 | Conceptual Masterplanning | \N | 2021-11-15 | 2022-01-31 | \N | \N
21168 | Final Masterplanning | \N | 2022-02-01 | 2022-03-31 | \N | \N
1701407 | Construction Administration | \N | 2022-01-01 | 2022-06-30 | \N | \N
21127 | Schematic Design | Main Building | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Schematic Design | Show Suites & Sales Galery | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Design Development | Main Building | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Design Development | Show Suites & Sales Galery | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Contract Documentation | Including Tendering for Main Building | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Contract Documentation | Including Tendring for Show Suites & Sales Galery | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Construction Administration | Main Building | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Construction Administration | Show Suites & Sales Galery | 2021-11-01 | 2021-11-01 | Y | S020
21127 | Post Construction Phase | Retention for both Main Building & Sales Galery | 2021-11-01 | 2021-11-01 | Y | S020
21115 | Conceptual Masterplanning | \N | 2022-01-01 | 2022-03-31 | \N | \N
21144 | Project Initiation | 70% DD By Haskel | 2022-01-01 | 2022-01-01 | \N | S020
21144 | Design Development | 90% DD | 2022-10-01 | 2022-11-30 | Y | S020
21144 | Design Development | 100% inc. Permit Submission | 2022-12-01 | 2022-12-31 | Y | S020
21144 | Contract Documentation | Construction Docs 70% | 2022-11-01 | 2023-02-28 | Y | S020
21144 | Contract Documentation | Construction Docs 100% | 2023-03-01 | 2023-06-30 | Y | S020
21144 | Construction Administration | 23 months | 2023-07-01 | 2025-05-31 | Y | S020
21147 | Project Initiation | \N | 2021-10-25 | 2021-10-25 | \N | \N
21147 | Preliminary Design | \N | 2021-10-25 | 2021-11-26 | \N | \N
21147 | Detailed Design | \N | 2021-11-29 | 2022-03-14 | \N | \N
21147 | Construction Administration | \N | 2022-03-01 | 2022-08-31 | \N | \N
21175 | Test-Fit | MP | 2021-11-29 | 2022-02-28 | Y | \N
21088 | Project Initiation | \N | 2022-09-01 | 2022-09-01 | Y | S020
21088 | Design Development | \N | 2025-01-01 | 2025-02-28 | Y | S020
21088 | Contract Documentation | \N | 2025-07-01 | 2025-11-30 | Y | S020
21088 | Construction Administration | \N | 2025-12-01 | 2029-11-30 | Y | S020
21088 | Project Initiation | \N | 2025-01-01 | 2025-01-01 | Y | S060
21088 | BIM LOD 300 Architecture and Structural Modelling | \N | 2025-01-01 | 2025-06-30 | Y | S060
21088 | BIM LOD 300 MEPF Modelling | \N | 2025-01-01 | 2025-06-30 | Y | S060
21088 | Clash Detection and Resolution | \N | 2025-01-01 | 2025-06-30 | Y | S060
21088 | 2D Combined Services Drawings | \N | 2025-01-01 | 2025-06-30 | Y | S060
21171 | Test-Fit | XX Conceptual Masterplanning | 2021-11-22 | 2022-10-12 | Y | S010
21171 | Project Initiation | \N | 2022-10-12 | 2022-10-12 | Y | S010
21171 | Data Collection and Analysis | Preliminary Conceptual MP | 2022-10-12 | 2023-01-31 | Y | S010
21171 | Visioning and Options Generation | Preliminary Conceptual MP | 2023-02-01 | 2023-05-31 | Y | S010
21171 | Conceptual Masterplanning | Final Conceptual MP Phase 1 | 2023-06-01 | 2023-10-31 | Y | S010
21171 | Conceptual Masterplanning | Final Conceptual MP Phase 2 | 2023-09-01 | 2023-12-31 | Y | S010
1601902 | Construction Administration | 22 months | 2021-03-01 | 2022-12-31 | \N | \N
21107 | Project Initiation | \N | 2022-01-01 | 2022-01-01 | N | S020
21107 | Schematic Design | Concept / SD | 2022-01-01 | 2023-03-31 | N | S020
21107 | Design Development | \N | 2023-04-01 | 2023-07-31 | N | S020
21107 | Contract Documentation | \N | 2023-08-01 | 2024-05-31 | N | S020
21107 | Construction Administration | \N | 2024-06-01 | 2030-05-31 | N | S020
22004 | Schematic Design | \N | 2022-01-17 | 2022-02-11 | Y | \N
22004 | Contract Documentation | \N | 2022-02-14 | 2022-02-28 | Y | \N
22004 | Construction Administration | \N | 2022-03-01 | 2022-04-30 | Y | \N
22009 | Concept Design | \N | 2022-01-24 | 2022-01-24 | Y | \N
22009 | Detailed Design | \N | 2022-01-24 | 2022-01-24 | Y | \N
22009 | Construction Administration | \N | 2022-01-24 | 2022-01-24 | Y | \N
1506810 | Construction Administration | \N | 2022-01-01 | 2022-07-31 | \N | S020
1506811 | Construction Administration | \N | 2022-01-01 | 2022-07-31 | \N | S020
21135 | Project Initiation | \N | 2022-01-10 | 2022-01-10 | N | S010
21135 | Data Collection and Analysis | \N | 2022-01-10 | 2022-01-31 | N | S010
21135 | Visioning and Options Generation | \N | 2022-02-01 | 2022-02-16 | N | S010
21135 | Conceptual Masterplanning | WITH 5% DISCOUNT | 2022-02-17 | 2023-07-31 | N | S010
1612413 | Construction Administration | \N | 2022-01-01 | 2022-07-31 | \N | \N
1800910 | Construction Administration | \N | 2022-01-01 | 2022-02-28 | \N | S020
1612414 | Design Development | Alteration Plans | 2022-02-15 | 2022-03-31 | N | \N
1507529 | Construction Administration | \N | 2022-01-01 | 2022-03-31 | \N | \N
21012 | Contract Documentation | Boardroom | 2022-02-03 | 2022-07-29 | \N | \N
21012 | Contract Documentation | Innovation Hub | 2022-04-11 | 2022-05-15 | \N | \N
21012 | Project Initiation | \N | 2022-02-03 | 2022-02-03 | \N | \N
21183 | Schematic Design | AR + VO1 | 2022-02-01 | 2023-01-31 | N | S020
21183 | Design Development | AR + VO1 | 2022-10-15 | 2024-05-31 | N | S020
21183 | Contract Documentation | AR + VO1 | 2024-06-01 | 2025-02-28 | N | S020
21183 | Construction Administration | AR + VO1 | 2025-03-01 | 2027-02-28 | N | S020
21183 | Project Initiation | AR + SUBCON | 2022-02-01 | 2022-02-01 | N | S020
21183 | Project Initiation | N/A | 2022-02-01 | 2022-02-01 | Y | S070
21183 | Schematic Design | SUBCON (WITH VO#1) | 2022-02-01 | 2023-01-31 | N | S070
21183 | Design Development | SUBCON (WITH VO#1) | 2022-10-15 | 2024-05-31 | N | S070
21183 | Contract Documentation | SUBCON (WITH VO#1) | 2024-06-01 | 2025-02-28 | N | S070
21183 | Construction Administration | SUBCON (WITH VO#1) | 2025-03-01 | 2027-02-28 | N | S070
21183 | Schematic Design | N/A: DO NOT USE (WITH ATC) | 2022-02-01 | 2022-02-01 | Y | \N
21183 | Design Development | N/A: DO NOT USE (WITH ATC) | 2022-02-01 | 2022-02-01 | Y | \N
21183 | Project Initiation | WELL | 2022-02-01 | 2022-02-01 | N | S080
21183 | Schematic Design | WELL | 2022-02-01 | 2023-01-31 | N | S080
21183 | Design Development | WELL | 2022-10-15 | 2024-05-31 | N | S080
21183 | Contract Documentation | WELL | 2024-06-01 | 2025-02-28 | N | S080
21183 | Construction Administration | WELL | 2025-03-01 | 2027-02-28 | N | S080
22005 | Concept Design | \N | 2022-03-01 | 2022-03-31 | Y | \N
1819201 | Construction Administration | \N | 2021-08-01 | 2021-12-31 | \N | S030
2017405 | Construction Administration | 6 mo. Support for Signage | 2021-12-01 | 2022-05-31 | \N | S020
2017405 | Construction Administration | 6 mo. Site Architect | 2021-12-01 | 2022-05-31 | \N | S020
1607310 | Miscellaneous | AR Plans, Enlarged Unit, CTS, Colored Mrktg Plans | 2022-02-22 | 2022-08-31 | N | S020
22022 | Preliminary Renderings | \N | 2022-02-07 | 2022-02-18 | \N | S050
22022 | Final Renderings | \N | 2022-02-21 | 2022-03-11 | \N | S050
22026 | Data Collection and Analysis | \N | 2022-02-01 | 2022-03-31 | \N | \N
22026 | Visioning and Options Generation | \N | 2022-08-01 | 2022-08-31 | \N | \N
22026 | Conceptual Masterplanning | \N | 2022-09-01 | 2022-09-30 | \N | \N
21129 | Project Initiation | AR | 2022-01-04 | 2022-01-04 | N | S020
21129 | Schematic Design | AR | 2022-01-04 | 2023-10-31 | N | S020
21129 | Contract Documentation | ON HOLD: AR | 2023-11-01 | 2024-03-31 | Y | S020
21129 | Construction Administration | ON HOLD: AR | 2024-04-01 | 2025-03-31 | Y | S020
21129 | Post Construction Phase | ON HOLD: AR | 2025-04-01 | 2025-04-30 | Y | S020
21129 | Project Initiation | SUBCON | 2022-01-04 | 2022-01-04 | N | S070
21129 | Schematic Design | SUBCON | 2022-01-04 | 2023-10-31 | N | S070
21129 | Contract Documentation | SUBCON 2023 | 2023-11-01 | 2023-12-31 | N | S070
21129 | Construction Administration | ON HOLD: SUBCON | 2024-04-01 | 2025-03-31 | Y | S070
21129 | Post Construction Phase | ON HOLD: SUBCON TURN OVER | 2025-04-01 | 2025-04-30 | Y | S070
21129 | Contract Documentation | ON HOLD: SUBCON 2024 | 2024-01-01 | 2024-03-31 | Y | S070
21162 | Project Initiation | AR | 2022-01-04 | 2022-01-04 | N | S020
21162 | Schematic Design | AR | 2022-01-04 | 2022-12-31 | N | S020
21162 | Contract Documentation | AR | 2022-10-08 | 2024-05-31 | N | S020
21162 | Construction Administration | AR | 2024-06-01 | 2026-01-31 | N | S020
21162 | Project Initiation | SUBCON | 2022-01-04 | 2022-01-04 | N | S070
21162 | Schematic Design | SUBCON | 2022-01-04 | 2022-12-31 | N | S070
21162 | Contract Documentation | SUBCON | 2022-10-08 | 2024-01-31 | N | S070
21162 | Construction Administration | SUBCON | 2024-06-01 | 2026-01-31 | N | S070
2100201 | Project Initiation | \N | 2021-03-03 | 2021-03-03 | N | S070
2100201 | Design Development | WT - at 25% DD - Upon Submission of Structural Load Study for Client Review | 2021-04-01 | 2021-04-30 | Y | S070
2100201 | Design Development | WT - at 50% DD - Upon Submission of results of cladding pressure for Client review | 2021-05-01 | 2021-05-31 | Y | \N
2100201 | Design Development | WT - at 50% DD - Upon Submission of results of Environmental Wind Study for Client review | 2021-06-01 | 2021-06-30 | Y | \N
2100201 | Design Development | WT - at 75% DD - Upon Submission of Final Reports | 2021-07-01 | 2021-07-31 | Y | \N
2100202 | Project Initiation | \N | 2021-03-01 | 2021-03-01 | N | \N
2100202 | Schematic Design | PSHA - At 50% SD - Review of Geotechnical Report & Consultation | 2021-04-01 | 2021-04-30 | Y | \N
2100202 | Schematic Design | PSHA - At 100% SD - Development of Site-Specific Response | 2021-05-01 | 2021-05-31 | Y | \N
2100202 | Design Development | PSHA - At 50% DD - Development of Site-Specific Time Series (Thirty-six) | 2021-06-01 | 2021-06-30 | Y | \N
2100202 | Design Development | PSHA - At 100% DD - Preparation of Report | 2021-07-01 | 2021-07-31 | Y | \N
2100203 | Project Initiation | \N | 2022-01-01 | 2022-01-01 | Y | \N
2100203 | Schematic Design | \N | 2022-01-01 | 2022-01-31 | Y | \N
2100203 | Design Development | \N | 2022-01-01 | 2022-01-31 | Y | \N
1410707 | Construction Administration | \N | 2022-02-01 | 2022-04-30 | \N | S020
1800911 | Construction Administration | \N | 2022-03-01 | 2022-03-31 | \N | S020
21134 | Project Initiation | \N | 2022-03-01 | 2022-03-01 | N | S030
21134 | Concept Design | Preliminary Design - EGD only | 2022-03-01 | 2023-12-31 | N | S040
21134 | Design Development | ID | 2022-03-01 | 2023-08-31 | N | S030
21134 | Contract Documentation | ID | 2023-01-01 | 2024-04-30 | N | S030
21134 | BIM Attendance | \N | 2022-03-01 | 2024-04-30 | N | S060
21134 | Construction Administration | ID | 2025-10-01 | 2026-09-30 | N | S030
21134 | Detailed Design | EGD | 2023-11-01 | 2024-04-30 | N | S040
21134 | Contract Documentation | EGD | 2024-05-01 | 2024-05-31 | N | S040
21134 | Construction Administration | EGD | 2025-10-01 | 2026-09-30 | N | S040
1902302 | Contract Documentation | ID PER MC FORMAT | 2021-12-01 | 2023-01-31 | N | S030
1711504 | Construction Administration | 1ST Extension | 2022-02-01 | 2024-03-31 | N | S020
21159 | Contract Documentation | ID - COMBINED CN/SD/CD | 2022-01-01 | 2022-12-31 | N | S030
21159 | Construction Administration | ID | 2023-05-01 | 2023-10-31 | N | S030
21159 | Contract Documentation | MECHANICAL - COMBINED CN/SD/CD | 2022-01-01 | 2022-12-31 | N | S070
21159 | Construction Administration | MECHANICAL | 2023-05-01 | 2023-10-31 | N | S070
21159 | Contract Documentation | ELECTRICAL - COMBINED CN/SD/CD | 2022-01-01 | 2022-12-31 | N | S070
21159 | Construction Administration | ELECTRICAL | 2023-05-01 | 2023-10-31 | N | S070
21159 | Contract Documentation | PLUMBING & FP - COMBINED CN/SD/CD | 2022-01-01 | 2022-12-31 | N | S070
21159 | Construction Administration | PLUMBING & FP | 2023-05-01 | 2023-10-31 | N | S070
1902303 | Contract Documentation | ID Revision - Megaworld | 2022-01-01 | 2023-01-31 | N | S030
22027 | Project Initiation | \N | 2022-03-01 | 2022-03-01 | \N | \N
22027 | Data Collection and Analysis | \N | 2022-03-01 | 2022-07-31 | \N | \N
22027 | Visioning and Options Generation | \N | 2022-05-01 | 2022-07-31 | \N | \N
22027 | Conceptual Masterplanning | \N | 2022-08-01 | 2022-09-30 | \N | \N
22006 | Project Initiation | \N | 2022-02-01 | 2022-02-01 | N | S020
22006 | Schematic Design | \N | 2022-02-01 | 2022-06-30 | N | S020
22006 | Design Development | \N | 2022-06-01 | 2022-11-15 | N | S020
22006 | Contract Documentation | \N | 2022-11-01 | 2024-06-30 | N | S020
22006 | Construction Administration | \N | 2024-07-01 | 2029-06-30 | N | S020
22017 | Project Initiation | ID | 2022-04-01 | 2022-04-01 | N | S030
22017 | Planning and Programming | ID | 2022-04-01 | 2022-07-31 | N | S030
22017 | Schematic Design | ID | 2022-05-01 | 2023-10-31 | N | S030
22017 | Contract Documentation | ON HOLD: ID: MAIN & VO1 | 2023-11-01 | 2024-03-31 | Y | S030
22017 | Construction Administration | ON HOLD: ID: MAIN & VO1 | 2024-04-01 | 2025-03-31 | Y | S030
22017 | Project Initiation | SUBCON | 2022-04-01 | 2022-04-01 | N | S030
22017 | Planning and Programming | SUBCON | 2022-04-01 | 2022-07-31 | N | S070
22017 | Schematic Design | SUBCON | 2022-05-01 | 2023-10-31 | N | S070
22017 | Contract Documentation | SUBCON 2023 | 2023-11-01 | 2023-12-31 | N | S070
22017 | Construction Administration | ON HOLD: SUBCON | 2024-04-01 | 2025-03-31 | Y | S070
22017 | Post Construction Phase | ON HOLD: ID TURN OVER: MAIN & VO1 | 2025-04-01 | 2025-04-30 | Y | S030
22017 | Post Construction Phase | ON HOLD: SUBCON TURN OVER | 2025-04-01 | 2025-04-30 | Y | S070
22017 | Contract Documentation | ON HOLD: SUBCON 2024 | 2024-01-01 | 2024-03-31 | Y | S070
21154 | Project Initiation | AOR | 2022-01-01 | 2022-01-01 | N | S020
21154 | Project Initiation | Wellness Consutancy | 2022-01-01 | 2022-01-01 | Y | S020
21154 | Project Initiation | n/a | 2022-01-01 | 2022-01-01 | Y | S020
21154 | Concept Design | Foreign Architect | 2022-01-01 | 2022-06-30 | Y | S020
21154 | Schematic Design | AOR/FA | 2022-08-01 | 2023-12-30 | Y | S020
21154 | Design Development | AOR | 2024-01-01 | 2024-03-31 | Y | S020
21154 | Contract Documentation | AOR | 2024-04-01 | 2024-06-30 | Y | S020
21154 | Construction Administration | AOR | 2024-07-01 | 2026-06-30 | Y | S020
21154 | Schematic Design | WELL | 2023-10-01 | 2024-08-31 | Y | S020
21154 | Design Development | WELL | 2024-09-01 | 2024-11-30 | Y | S020
21154 | Contract Documentation | WELL | 2024-12-01 | 2025-02-28 | Y | S020
21154 | Construction Administration | WELL | 2025-03-01 | 2027-02-28 | Y | S020
21154 | Contract Documentation | N/A | 2022-12-01 | 2022-12-31 | Y | S020
21154 | Construction Administration | N/A | 2022-12-01 | 2022-12-31 | Y | S020
21154 | WELL Certification | N/A | 2022-12-01 | 2022-12-31 | Y | S020
1302904 | Construction Administration | AR | 2022-01-01 | 2022-12-31 | \N | S020
1507530 | Construction Administration | \N | 2022-05-01 | 2022-06-30 | \N | \N
1923201 | Contract Documentation | AR | 2021-05-01 | 2022-09-30 | \N | S020
1817214 | Preliminary Architecture and Engineering Design | AR | 2022-04-01 | 2022-10-31 | N | S020
1817214 | Detailed Architecture and Engineering Design | AR | 2022-05-01 | 2022-10-31 | N | S020
1817214 | Preliminary Architecture and Engineering Design | ACOUSTICS | 2022-04-01 | 2022-10-31 | N | S070
1817214 | Detailed Architecture and Engineering Design | ACOUSTICS | 2022-05-01 | 2022-10-31 | N | S070
1817214 | Preliminary Architecture and Engineering Design | LIGHTING | 2022-04-01 | 2022-10-31 | N | S070
1817214 | Detailed Architecture and Engineering Design | LIGHTING | 2022-05-01 | 2022-10-31 | N | S070
1817214 | Preliminary Architecture and Engineering Design | ID - BY7X | 2022-04-01 | 2022-10-31 | N | S070
1817214 | Detailed Architecture and Engineering Design | ID - BY7X | 2022-05-01 | 2022-10-31 | N | S070
1817214 | Preliminary Architecture and Engineering Design | AUDIO VISUALS | 2022-04-01 | 2022-10-31 | N | S070
1817214 | Detailed Architecture and Engineering Design | AUDIO VISUALS | 2022-05-01 | 2022-10-31 | N | S070
1817214 | Preliminary Architecture and Engineering Design | MEPF | 2022-04-01 | 2022-10-31 | N | S070
1817214 | Detailed Architecture and Engineering Design | MEPF | 2022-05-01 | 2022-10-31 | N | S070
1817214 | Preliminary Architecture and Engineering Design | KITCHEN | 2022-04-01 | 2022-10-31 | N | S070
1817214 | Detailed Architecture and Engineering Design | KITCHEN | 2022-05-01 | 2022-10-31 | N | S070
1817214 | Preliminary Architecture and Engineering Design | STRUCTURAL | 2022-04-01 | 2022-10-31 | N | S070
1817214 | Detailed Architecture and Engineering Design | STRUCTURAL | 2022-05-01 | 2022-10-31 | N | S070
1817215 | Preliminary Architecture and Engineering Design | AR | 2022-04-01 | 2022-10-31 | N | S020
1817215 | Detailed Architecture and Engineering Design | AR | 2022-06-01 | 2022-10-31 | N | S020
1817215 | Preliminary Architecture and Engineering Design | ACOUSTICS | 2022-04-01 | 2022-10-31 | N | S070
1817215 | Detailed Architecture and Engineering Design | ACOUSTICS | 2022-06-01 | 2022-10-31 | N | S070
1817215 | Preliminary Architecture and Engineering Design | LIGHTING | 2022-04-01 | 2022-10-31 | N | S070
1817215 | Detailed Architecture and Engineering Design | LIGHTING | 2022-06-01 | 2022-10-31 | N | S070
1817215 | Preliminary Architecture and Engineering Design | ID - BY7X | 2022-04-01 | 2022-10-31 | N | S070
1817215 | Detailed Architecture and Engineering Design | ID - BY7X | 2022-06-01 | 2022-10-31 | N | S070
1817215 | Preliminary Architecture and Engineering Design | MEPF | 2022-04-01 | 2022-10-31 | N | S070
1817215 | Detailed Architecture and Engineering Design | MEPF | 2022-06-01 | 2022-10-31 | N | S070
1817215 | Preliminary Architecture and Engineering Design | AUDIO VISUALS | 2022-04-01 | 2022-10-31 | N | S070
1817215 | Detailed Architecture and Engineering Design | AUDIO VISUALS | 2022-06-01 | 2022-10-31 | N | S070
1817215 | Preliminary Architecture and Engineering Design | STRUCTURAL | 2022-04-01 | 2022-10-31 | N | S070
1817215 | Detailed Architecture and Engineering Design | STRUCTURAL | 2022-06-01 | 2022-10-31 | N | S070
1817216 | Preliminary Architecture and Engineering Design | AR | 2022-04-01 | 2022-10-31 | N | S020
1817216 | Detailed Architecture and Engineering Design | AR | 2022-05-01 | 2022-10-31 | N | S020
1817216 | Preliminary Architecture and Engineering Design | ACOUSTICS | 2022-04-01 | 2022-10-31 | N | S070
1817216 | Detailed Architecture and Engineering Design | ACOUSTICS | 2022-05-01 | 2022-10-31 | N | S070
1817216 | Preliminary Architecture and Engineering Design | LIGHTING | 2022-04-01 | 2022-10-31 | N | S070
1817216 | Detailed Architecture and Engineering Design | LIGHTING | 2022-05-01 | 2022-10-31 | N | S070
1817216 | Preliminary Architecture and Engineering Design | ID - BY7X | 2022-04-01 | 2022-10-31 | N | S070
1817216 | Detailed Architecture and Engineering Design | ID - BY7X | 2022-05-01 | 2022-10-31 | N | S070
1817216 | Preliminary Architecture and Engineering Design | MEPF | 2022-04-01 | 2022-10-31 | N | S070
1817216 | Detailed Architecture and Engineering Design | MEPF | 2022-05-01 | 2022-10-31 | N | S070
1817216 | Preliminary Architecture and Engineering Design | STRUCTURAL | 2022-04-01 | 2022-10-31 | N | S070
1817216 | Detailed Architecture and Engineering Design | STRUCTURAL | 2022-05-01 | 2022-10-31 | N | S070
1817216 | Preliminary Architecture and Engineering Design | AUDIO VISUALS | 2022-04-01 | 2022-10-31 | N | S070
1817216 | Detailed Architecture and Engineering Design | AUDIO VISUALS | 2022-05-01 | 2022-10-31 | N | S070
1817217 | Preliminary Architecture and Engineering Design | \N | 2022-04-01 | 2022-11-30 | Y | S020
1817217 | Detailed Architecture and Engineering Design | \N | 2022-05-01 | 2022-11-30 | Y | S020
1817218 | Preliminary Architecture and Engineering Design | \N | 2022-04-01 | 2022-12-31 | Y | S020
1817218 | Detailed Architecture and Engineering Design | \N | 2022-05-01 | 2022-12-31 | Y | S020
1817219 | Preliminary Architecture and Engineering Design | \N | 2022-04-01 | 2022-12-31 | Y | S020
1817219 | Detailed Architecture and Engineering Design | \N | 2022-07-01 | 2022-12-31 | Y | S020
1817220 | Preliminary Architecture and Engineering Design | \N | 2022-04-01 | 2022-12-31 | Y | S020
1817220 | Detailed Architecture and Engineering Design | \N | 2022-06-01 | 2022-12-31 | Y | S020
1817221 | Preliminary Architecture and Engineering Design | \N | 2022-04-01 | 2022-12-31 | Y | S020
1817221 | Detailed Architecture and Engineering Design | \N | 2022-08-01 | 2022-12-31 | Y | S020
1817222 | Preliminary Architecture and Engineering Design | \N | 2022-06-01 | 2022-06-30 | Y | \N
1817209 | Detailed Architecture and Engineering Design | \N | 2022-04-01 | 2022-07-31 | N | S020
1817209 | Detailed Architecture and Engineering Design | \N | 2022-04-01 | 2022-07-31 | N | S070
1817210 | Detailed Architecture and Engineering Design | \N | 2022-04-01 | 2022-07-31 | N | S020
1817210 | Detailed Architecture and Engineering Design | \N | 2022-04-01 | 2022-07-31 | N | S070
1817211 | Detailed Architecture and Engineering Design | \N | 2022-04-01 | 2022-07-31 | N | S020
1817212 | Detailed Architecture and Engineering Design | \N | 2022-04-01 | 2022-07-31 | N | S020
1817213 | Detailed Architecture and Engineering Design | \N | 2022-04-01 | 2022-10-31 | N | S020
22025 | Project Initiation | \N | 2022-05-09 | 2022-05-09 | N | S010
22025 | Visioning and Options Generation | Data Gathering + Visioning | 2022-05-09 | 2022-08-31 | N | S010
22025 | Conceptual Masterplanning | Preliminary Conceptual Masterplan | 2022-08-01 | 2022-10-31 | N | S010
22025 | Final Masterplanning | Final Conceptual | 2022-11-01 | 2023-01-31 | N | S010
1817223 | Preliminary Architecture and Engineering Design | \N | 2022-08-01 | 2022-12-31 | Y | S020
1817223 | Detailed Architecture and Engineering Design | \N | 2022-09-01 | 2022-12-31 | Y | S020
1817224 | Preliminary Architecture and Engineering Design | \N | 2022-05-06 | 2022-12-31 | Y | S020
1817224 | Detailed Architecture and Engineering Design | \N | 2022-09-15 | 2022-12-31 | Y | S020
1817225 | Preliminary Architecture and Engineering Design | \N | 2022-04-15 | 2022-10-31 | Y | \N
1817225 | Detailed Architecture and Engineering Design | \N | 2022-05-16 | 2022-10-31 | Y | \N
1817226 | Preliminary Architecture and Engineering Design | \N | 2022-04-01 | 2022-06-30 | N | S020
1817226 | Detailed Architecture and Engineering Design | \N | 2022-05-01 | 2022-10-31 | N | S020
1817227 | Preliminary Architecture and Engineering Design | \N | 2022-04-15 | 2022-06-30 | N | S020
1817227 | Detailed Architecture and Engineering Design | \N | 2022-05-15 | 2022-10-31 | N | S020
1924204 | Project Initiation | \N | 2022-01-03 | 2022-01-03 | \N | \N
1924204 | Contract Documentation | \N | 2022-01-03 | 2023-07-31 | Y | \N
1924205 | Project Initiation | \N | 2022-04-01 | 2022-04-01 | \N | \N
1924205 | Contract Documentation | \N | 2022-04-01 | 2022-04-30 | \N | \N
2111101 | Detailed Design | \N | 2022-02-01 | 2022-08-31 | N | \N
2102801 | Concept Design | \N | 2022-02-01 | 2022-05-31 | N | \N
2012601 | Design Development | \N | 2022-02-21 | 2022-09-09 | N | S030
22028 | Project Initiation | \N | 2022-05-11 | 2022-05-11 | N | S030
22028 | Preliminary Architecture and Engineering Design | \N | 2022-05-11 | 2022-05-31 | N | S030
22028 | Detailed Architecture and Engineering Design | \N | 2022-06-01 | 2022-06-30 | N | S030
22028 | Construction Administration | \N | 2022-11-01 | 2023-02-28 | N | S030
22059 | Project Initiation | \N | 2022-05-02 | 2022-05-02 | N | S030
22059 | Schematic Design | \N | 2022-05-02 | 2022-06-14 | N | S030
22059 | Design Development | \N | 2022-06-15 | 2022-08-31 | N | S030
22059 | Contract Documentation | \N | 2022-09-01 | 2023-10-31 | N | S030
22059 | Construction Administration | \N | 2023-10-01 | 2024-05-31 | N | S030
22039 | Project Initiation | \N | 2022-03-01 | 2022-03-01 | \N | \N
22039 | Schematic Design | \N | 2022-03-01 | 2022-08-31 | \N | \N
22042 | Project Initiation | AR | 2022-05-01 | 2022-05-01 | \N | S020
22042 | Schematic Design | AR | 2022-05-01 | 2022-11-04 | \N | S020
22042 | Design Development | AR | 2023-01-01 | 2023-01-31 | N | S020
22042 | Contract Documentation | AR | 2023-02-01 | 2023-04-30 | N | S020
22042 | Construction Administration | AR | 2023-05-01 | 2025-04-30 | N | S020
1701408 | Construction Administration | \N | 2022-03-01 | 2022-06-30 | \N | S020
21012A | Design Development | \N | 2022-04-28 | 2022-05-16 | \N | S060
21012A | Contract Documentation | \N | 2022-05-19 | 2022-06-02 | \N | S060
21012A | Construction Administration | \N | 2022-07-01 | 2022-09-30 | \N | S060
22032 | Pre-Design Services | \N | 2022-03-10 | \N | Y | \N
1305610 | Construction Administration | \N | 2022-04-01 | 2022-09-30 | \N | S020
22071 | Animation | \N | 2022-05-16 | 2022-07-08 | \N | S050
22076 | Project Initiation | ID | 2022-06-01 | 2022-06-01 | N | S030
22076 | Schematic Design | ID | 2022-06-01 | 2022-10-10 | N | S030
22076 | Detailed Design | ID | 2022-09-12 | 2023-07-15 | N | S030
22076 | Construction Administration | ID | 2023-12-01 | 2024-07-31 | N | S030
22048 | Project Initiation | \N | 2022-06-13 | 2022-06-13 | \N | S010
22048 | Data Collection and Analysis | \N | 2022-06-13 | 2022-06-30 | \N | S010
22048 | Visioning and Options Generation | \N | 2022-07-01 | 2022-08-05 | \N | S010
22048 | Conceptual Masterplanning | \N | 2022-08-08 | 2022-09-30 | \N | S010
1806905 | Construction Administration | \N | 2022-05-02 | 2022-07-29 | \N | \N
22055 | Conceptual Masterplanning | MP | 2022-04-30 | 2023-04-30 | N | S010
22044 | Project Initiation | \N | 2022-06-01 | 2022-06-01 | N | S010
22044 | Data Collection and Analysis | \N | 2022-07-01 | 2022-08-31 | N | S010
22044 | Visioning and Options Generation | \N | 2022-09-01 | 2022-10-31 | N | S010
22044 | Conceptual Masterplanning | \N | 2022-10-01 | 2022-11-30 | N | S010
22044 | Final Masterplanning | \N | 2022-11-12 | 2023-04-30 | N | S010
22044 | Urban Design Guidelines | \N | 2023-04-01 | 2023-10-31 | N | S010
22046 | Project Initiation | \N | 2022-05-01 | 2022-05-01 | \N | S080
22046 | Urban Design Guidelines | \N | 2022-09-01 | 2022-11-30 | \N | S080
22046 | Merchant Retail Cut-Up Plans | \N | 2022-10-01 | 2022-11-30 | \N | S080
22023 | Project Initiation | \N | 2022-04-01 | 2022-04-01 | N | S020
22023 | Preliminary Design | Phase 1&2 | 2022-04-01 | 2022-07-31 | N | S020
22023 | Detailed Design | Phase 1 | 2022-08-01 | 2024-04-30 | N | S020
22023 | Construction Administration | Phase 1 | 2024-06-01 | 2027-05-31 | N | S020
22023 | Detailed Design | Phase 2 | 2023-01-01 | 2024-04-30 | N | S020
22023 | Construction Administration | Phase 2 | 2027-06-01 | 2028-05-31 | N | S020
22019 | Schematic Design | AR (Includes Pre-Design) | 2022-06-01 | 2023-05-30 | N | S020
22019 | Design Development | AR | 2022-10-20 | 2024-04-30 | N | S020
22019 | Contract Documentation | AR | 2024-05-01 | 2024-07-31 | N | S020
22019 | Tender | Includes Bidding Phase | 2024-08-01 | 2024-11-30 | N | S020
22019 | Construction Administration | AR | 2024-12-01 | 2026-11-30 | N | S020
22019 | Project Initiation | AR + SUBCON | 2022-06-01 | 2022-06-01 | N | S020
22019 | Contract Documentation | SUBCON | 2024-05-01 | 2024-07-31 | N | S070
22019 | Construction Administration | SUBCON | 2024-12-01 | 2026-11-30 | N | S070
22019 | Schematic Design | SUBCON | 2022-06-01 | 2023-05-30 | N | S070
22019 | Design Development | SUBCON | 2022-10-20 | 2024-04-30 | N | S070
1701409 | Construction Administration | \N | 2022-07-01 | 2022-07-31 | \N | \N
22060 | Project Initiation | \N | 2022-07-01 | 2022-07-01 | N | S020
22060 | Preliminary Design | \N | 2022-07-01 | 2023-01-31 | N | S020
22060 | Detailed Design | \N | 2023-02-01 | 2023-12-31 | N | S020
22060 | Construction Administration | \N | 2024-03-01 | 2026-02-28 | N | S020
22060 | Tender | \N | 2024-01-01 | 2024-02-29 | N | S020
22081 | Project Initiation | \N | 2022-07-01 | 2022-07-01 | N | S010
22081 | Conceptual Masterplanning | Preliminary | 2022-07-01 | 2023-03-13 | N | S010
22081 | Conceptual Masterplanning | Developed | 2023-08-16 | 2023-08-16 | Y | \N
22081 | Final Masterplanning | \N | 2023-08-16 | 2023-08-16 | Y | \N
21043 | Project Initiation | \N | 2022-07-01 | 2022-07-01 | \N | S020
21043 | Concept Design | \N | 2022-07-01 | 2022-11-15 | \N | S020
22043 | Project Initiation | Subcon with MF except Hospitality | 2022-07-01 | 2022-07-01 | N | S070
22043 | Schematic Design | Subcon with MF (Acoustics, AV, IT, Security, Landscape, Pools) | 2022-07-01 | 2023-07-31 | N | S070
22043 | Detailed Design | ON HOLD: Subcon except Hospitality | 2022-08-16 | 2023-09-30 | Y | S070
22043 | Construction Administration | Subcon except ID Local Culture (no CA) and Hospitality (separate row) | 2023-07-01 | 2023-12-31 | N | S070
22043 | Detailed Design | ON HOLD: MF all trades except Hospitality | 2022-07-01 | 2023-09-30 | Y | S020
22043 | Schematic Design | DO NOT USE (WITH ATC) | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Construction Administration | ON HOLD: MF all trades except Hospitality | 2023-07-01 | 2025-06-30 | Y | S020
22043 | Construction Administration | 2022 Hospitality monthly advisory (AR & SUBCON) | 2022-09-01 | 2022-10-31 | N | S070
22043 | Construction Administration | 2022 MF Hospitality | 2022-11-01 | 2022-12-31 | N | S020
22043 | Schematic Design | DO NOT USE (WITH ATC) | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Construction Administration | 2022 Subcon Hospitality | 2022-11-01 | 2022-12-31 | N | S070
22043 | Construction Administration | 2023 Subcon Hospitality | 2023-01-01 | 2023-08-31 | Y | S070
22043 | Construction Administration | ON HOLD: 2023 MF Hospitality | 2023-01-01 | 2023-08-31 | Y | S020
22043 | Schematic Design | Subcon (Lighting, Kitchen, ID Culture, and Spa) | 2022-07-01 | 2023-07-31 | N | S070
22043 | Detailed Design | n/a | 2022-08-16 | 2022-08-16 | Y | \N
22043 | Construction Administration | n/a | 2022-10-01 | 2022-10-01 | Y | \N
22043 | Project Initiation | n/a | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Schematic Design | ON HOLD: MF (Lighting, Kitchen, ID Culture, and Spa) | 2022-07-01 | 2023-07-31 | Y | S020
22043 | Detailed Design | n/a | 2022-08-16 | 2022-08-16 | Y | \N
22043 | Construction Administration | n/a | 2022-10-01 | 2022-10-01 | Y | \N
22043 | Project Initiation | n/a | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Schematic Design | n/a | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Detailed Design | n/a | 2022-08-16 | 2022-08-16 | Y | \N
22043 | Construction Administration | n/a | 2022-10-01 | 2022-10-01 | Y | \N
22043 | Project Initiation | n/a | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Schematic Design | n/a | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Detailed Design | n/a | 2022-10-01 | 2022-10-01 | Y | \N
22043 | Construction Administration | n/a | 2022-10-01 | 2022-10-01 | Y | \N
22043 | Project Initiation | n/a | 2022-07-01 | 2022-07-01 | Y | \N
22043 | Construction Administration | ON HOLD: Spa 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Lighting 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Swimming Pool Filtration Design 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Kitchen & Laundry Design 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Landscape 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Acoustics 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Audio-Visual Design 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Information Technology 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
22043 | Construction Administration | ON HOLD: Security 2024 & 2025 | 2024-01-01 | 2025-06-30 | Y | S070
1716801 | Contract Documentation | \N | 2019-07-01 | 2019-10-31 | \N | S030
1716801 | Construction Administration | \N | 2019-01-01 | 2019-04-30 | \N | S030
1924203 | Contract Documentation | \N | 2021-05-14 | 2021-06-14 | N | \N
1924202 | Project Initiation | \N | 2019-03-18 | 2019-03-18 | Y | \N
1924202 | Schematic Design | \N | 2019-03-18 | 2019-03-18 | Y | \N
1924202 | Design Development | \N | 2019-03-18 | 2019-03-18 | Y | \N
1924202 | Contract Documentation | \N | 2019-03-18 | 2019-03-18 | Y | \N
1924202 | Construction Administration | \N | 2019-03-18 | 2019-03-18 | Y | \N
22070 | Project Initiation | \N | 2022-05-02 | 2022-05-02 | \N | S050
22070 | Final Renderings | Batch 1 | 2022-05-02 | 2022-08-26 | \N | S050
22070 | Final Renderings | Batch 2 | 2022-08-29 | 2023-06-30 | N | S050
1701406 | Detailed Design | tagged to main project | 2020-03-01 | 2020-12-31 | Y | \N
22051 | Project Initiation | \N | 2022-08-01 | 2022-08-01 | Y | S010
22051 | Data Collection and Analysis | \N | 2022-08-01 | 2022-09-30 | Y | S010
22051 | Visioning and Options Generation | Preliminary Conceptual Masterplan Package | 2022-10-01 | 2023-02-28 | Y | S010
22051 | Conceptual Masterplanning | Final Conceptual Masterplan Package | 2022-12-01 | 2022-12-01 | Y | S010
1506812 | Construction Administration | \N | 2022-08-01 | 2023-02-28 | N | S020
1506813 | Construction Administration | AR | 2022-08-01 | 2023-02-28 | N | S020
22011 | Project Initiation | AR | 2022-08-01 | 2022-08-01 | N | \N
22011 | Concept Design | AR | 2022-08-11 | 2023-01-23 | N | \N
22011 | Schematic Design | AR-Phase 1A & VO-01 (Phase 1B) | 2023-01-24 | 2023-07-15 | N | \N
22011 | Design Development | AR-Phase 1A & VO-01 (Phase 1B) | 2023-07-01 | 2024-01-31 | N | \N
22011 | Contract Documentation | AR-Phase 1A & VO-01 (Phase 1B) | 2024-02-01 | 2024-04-30 | N | \N
22011 | Construction Administration | AR-Phase 1A & VO-01 (Phase 1B) | 2024-05-01 | 2027-04-30 | N | \N
22011 | Schematic Design | DELETED SCOPE: AR-Phase 1B | 2022-08-01 | 2022-08-01 | Y | \N
22011 | Design Development | DELETED SCOPE: AR-Phase 1B | 2022-08-01 | 2022-08-01 | Y | \N
22011 | Contract Documentation | DELETED SCOPE: AR-Phase 1B | 2022-08-01 | 2022-08-01 | Y | \N
22011 | Construction Administration | DELETED SCOPE: AR-Phase 1B | 2022-08-01 | 2022-08-01 | Y | \N
22089 | Project Initiation | ID | 2022-07-20 | 2022-07-20 | N | S030
22089 | Contract Documentation | ID | 2022-07-20 | 2022-08-19 | N | S030
22089 | Construction Administration | ID | 2023-03-01 | 2023-05-31 | N | S030
2017504 | Final Renderings | \N | 2022-01-03 | 2022-07-29 | N | S050
22072 | Others | XXX | 2022-07-01 | 2022-07-01 | Y | \N
22072 | Schematic Design | Concept/SD | 2023-01-01 | 2023-04-21 | N | S030
22072 | Design Development | ID | 2023-03-01 | 2023-08-31 | N | S030
22072 | Tender | ID | 2023-08-01 | 2023-12-31 | N | S030
22072 | Construction Administration | ID | 2024-01-01 | 2025-02-28 | N | S030
22072 | Project Initiation | ID | 2022-07-01 | 2022-07-01 | N | S030
22072 | Test-Fit | ID | 2022-07-01 | 2023-02-17 | N | S030
16039J13 | Construction Administration | AR | 2020-09-01 | 2023-03-31 | N | S020
16039J13 | Construction Administration | Structural | 2020-09-01 | 2022-12-31 | N | S070
16039J13 | Construction Administration | Hotel ID | 2022-11-01 | 2023-03-31 | N | S070
16039J13 | Construction Administration | Mall ID and EGD | 2021-08-01 | 2023-02-28 | N | S030
16039J13 | Construction Administration | ME+EL+San | 2020-09-01 | 2023-03-31 | N | S070
22086 | Contract Documentation | Tax Declaration Plan Supp Services | 2022-08-01 | 2022-09-30 | N | S080
22087 | Contract Documentation | Tax Declaration Plan Supp Services | 2022-08-01 | 2022-09-30 | N | S080
22088 | Contract Documentation | Tax Declaration Plan Supp Services | 2022-08-01 | 2022-09-30 | \N | S080
2114101 | Design Development | \N | 2022-08-08 | 2022-09-07 | Y | \N
2114101 | Contract Documentation | \N | 2022-09-08 | 2022-10-07 | Y | \N
2114101 | Tender | \N | 2022-10-08 | 2022-11-07 | Y | \N
2114101 | Construction Administration | \N | 2022-11-08 | 2023-03-07 | Y | \N
2114101 | Project Initiation | \N | 2022-08-08 | 2022-08-08 | Y | \N
1310402 | Construction Administration | CS Extension | 2018-06-01 | 2019-05-31 | \N | \N
2105801 | Concept Design | 1st and 2nd Floor Concept | 2022-07-01 | 2022-08-05 | \N | S030
2105801 | Tender | 1st and 2nd Floor Tender | 2022-08-08 | 2022-09-02 | \N | S030
2105802 | Concept Design | \N | 2022-02-07 | 2022-06-29 | \N | S030
2105802 | Tender | \N | 2022-07-01 | 2022-12-30 | \N | S030
1612415 | BIM LOD 350 | A&S | 2025-01-01 | 2025-01-31 | N | S060
1612415 | BIM LOD 350 | MEPF | 2025-02-01 | 2025-02-28 | N | S060
1612415 | Clash Detection and Resolution | \N | 2025-03-01 | 2025-03-31 | N | S060
1612415 | 2D Combined Services Drawings | \N | 2025-04-01 | 2025-04-30 | N | S060
22045 | Project Initiation | \N | 2022-07-01 | 2022-07-31 | \N | S020
22045 | Urban Design Guidelines | 50% Completion | 2022-10-01 | 2022-12-31 | Y | S020
22045 | Urban Design Guidelines | 100% Completion | 2023-01-01 | 2023-03-31 | Y | S020
2111102 | Contract Documentation | \N | 2022-05-02 | 2022-11-30 | N | \N
1906501 | Construction Administration | 1st CS Extension | 2022-08-01 | 2023-03-31 | N | S020
22105 | Project Initiation | \N | 2022-08-01 | 2022-08-01 | \N | \N
22105 | Code Review | Upon submission of preliminary report | 2022-09-01 | 2022-09-30 | \N | \N
22105 | Code Review | NOT USED | 2022-10-01 | 2022-10-31 | \N | \N
2017506 | Project Initiation | \N | 2022-08-30 | 2022-08-30 | \N | S050
2017506 | Animation | \N | 2022-08-31 | 2022-09-30 | \N | S050
2105803 | Project Initiation | \N | 2022-08-22 | 2022-08-22 | \N | S030
2105803 | Concept Design | \N | 2022-08-22 | 2022-10-21 | \N | S030
2105803 | Tender | \N | 2022-10-24 | 2022-12-30 | \N | S030
2017403 | Construction Administration | \N | 2021-11-01 | 2021-11-30 | \N | S020
2017404 | Construction Administration | \N | 2021-11-01 | 2021-11-30 | \N | S020
2105804 | Project Initiation | \N | 2022-09-12 | 2022-09-12 | Y | \N
2105804 | Concept Design | \N | 2022-09-12 | 2022-09-12 | Y | \N
2105804 | Tender | \N | 2022-09-12 | 2022-09-12 | Y | \N
2019001 | Construction Administration | Extension of Construction | 2022-09-01 | 2022-11-30 | \N | S020
22098 | Project Initiation | AR | 2022-07-01 | 2022-07-01 | N | S020
22098 | Preliminary Design | AR | 2022-07-01 | 2022-10-31 | N | S020
22098 | Detailed Design | AR | 2022-09-01 | 2023-02-28 | N | S020
22098 | Construction Administration | AR | 2023-01-01 | 2023-08-31 | N | S020
1612416 | Construction Administration | \N | 2022-08-01 | 2022-10-31 | \N | S020
1817228 | Preliminary Architecture and Engineering Design | \N | 2022-05-01 | 2022-05-01 | Y | \N
1817228 | Detailed Architecture and Engineering Design | \N | 2022-05-01 | 2022-08-31 | Y | S020
1817228 | Detailed Architecture and Engineering Design | \N | 2022-05-01 | 2022-08-31 | Y | S070
22126 | Test-Fit | \N | 2022-09-01 | 2022-09-30 | \N | S010
1410708 | Contract Documentation | AR | 2022-08-01 | 2023-03-31 | Y | S020
1801601 | Construction Administration | \N | 2022-04-01 | 2022-04-01 | Y | \N
22029 | Project Initiation | Phase 1: Existing Building Refurbishment | 2022-08-01 | 2022-08-01 | N | S020
22029 | Preliminary Design | Phase 1: Existing Building Refurbishment | 2022-08-01 | 2022-10-31 | N | S020
22029 | Detailed Design | Phase 1: Existing Building Refurbishment | 2022-11-01 | 2023-03-31 | N | S020
22029 | Construction Administration | Phase 1: Existing Building Refurbishment | 2023-03-01 | 2023-08-31 | N | S020
22029 | Project Initiation | Phase 2: New Building | 2023-01-04 | 2023-01-04 | N | S020
22029 | Preliminary Design | Consolidated Phases 2 & 3 | 2023-03-19 | 2024-05-31 | N | S020
22029 | Detailed Design | ON HOLD: Phase 2: New Building Detail Design | 2023-12-01 | 2024-02-28 | Y | S020
22029 | Construction Administration | ON HOLD: Phase 2: New Building Construction | 2024-03-01 | 2025-02-28 | Y | S020
22029 | Project Initiation | ON HOLD: Phase 3: New Building | 2023-01-04 | 2023-01-04 | Y | S020
22029 | Preliminary Design | XXX | 2022-08-01 | 2022-08-01 | N | S020
22029 | Detailed Design | ON HOLD: Phase 3: New Building Detail Design | 2025-02-01 | 2025-02-28 | Y | S020
22029 | Construction Administration | ON HOLD: Phase 3: New Building Construction | 2025-03-01 | 2025-05-30 | Y | S020
1601701 | Construction Administration | \N | 2022-10-01 | 2023-09-30 | N | S010
16039J14 | Project Initiation | AR | 2022-09-01 | 2022-09-01 | N | S020
16039J14 | Contract Documentation | AR: UPON SUBMISSION OF REVISED DRAWINGS/ UPON SUBMISSION OF ADDITIONAL PERSPECTIVE RENDERS | 2022-09-01 | 2022-11-30 | N | S020
16039J14 | Project Initiation | MECHANICAL | 2022-09-01 | 2022-09-01 | N | S070
16039J14 | Contract Documentation | MECHANICAL: UPON SUBMISSION OF REVISED DRAWINGS/ UPON SUBMISSION OF ADDITIONAL PERSPECTIVE RENDERS | 2022-09-01 | 2022-11-30 | N | S070
16039J14 | Project Initiation | ELECTRICAL | 2022-09-01 | 2022-09-01 | N | S070
16039J14 | Contract Documentation | ELECTRICAL: UPON SUBMISSION OF REVISED DRAWINGS/ UPON SUBMISSION OF ADDITIONAL PERSPECTIVE RENDERS | 2022-09-01 | 2022-11-30 | N | S070
16039J14 | Project Initiation | PLUMBING & FP | 2022-09-01 | 2022-09-01 | N | S070
16039J14 | Contract Documentation | PLUMBING & FP: UPON SUBMISSION OF REVISED DRAWINGS/ UPON SUBMISSION OF ADDITIONAL PERSPECTIVE RENDERS | 2022-09-01 | 2022-11-30 | N | S070
16039J15 | Project Initiation | AR | 2022-09-01 | 2022-09-01 | Y | S020
16039J15 | Contract Documentation | AR - UPON SUBMISSION OF REVISED DRAWINGS/ UPON SUBMISSION OF ADDITIONAL PERSPECTIVE RENDERS | 2022-09-01 | 2023-02-28 | Y | S020
16039J15 | Project Initiation | SUBCON | 2022-09-01 | 2022-09-01 | Y | S070
16039J15 | Contract Documentation | SUBCON - UPON SUBMISSION OF REVISED DRAWINGS/ UPON SUBMISSION OF ADDITIONAL PERSPECTIVE RENDERS | 2022-09-01 | 2023-02-28 | Y | S070
21022 | Project Initiation | AIDEA: UPON APPOINTMENT /NOTICE TO PROCEED (NTP) | 2022-08-25 | 2022-08-25 | N | S060
21022 | BIM LOD 300 Architecture and Structural Modelling | AIDEA: UPON COMPLETION OF THE INITIAL REPORT OF BIM BASED ON THE SIGNED-OFF CD DOCS | 2022-09-01 | 2022-10-31 | N | S060
21022 | BIM LOD 300 MEPF Modelling | AIDEA: UPON COMPLETION OF BUILDING SERVICES (MEPF) MODELLING | 2022-11-01 | 2023-01-31 | N | S060
21022 | Project Initiation | SUBCON: UPON APPOINTMENT /NOTICE TO PROCEED (NTP) | 2022-08-25 | 2022-08-25 | N | S070
21022 | BIM LOD 300 Architecture and Structural Modelling | SUBCON: UPON COMPLETION OF THE INITIAL REPORT OF BIM BASED ON THE SIGNED-OFF CD DOCS | 2022-09-01 | 2022-10-31 | N | S070
21022 | BIM LOD 300 MEPF Modelling | SUBCON: UPON COMPLETION OF BUILDING SERVICES (MEPF) MODELLING | 2022-11-01 | 2023-01-31 | N | S070
22131 | Project Initiation | \N | 2022-09-14 | 2022-09-14 | Y | \N
22131 | Schematic Design | \N | 2022-09-14 | 2022-10-31 | Y | \N
22131 | Design Development | \N | 2022-11-01 | 2022-12-30 | Y | \N
22131 | Contract Documentation | \N | 2023-01-02 | 2023-02-28 | Y | \N
22131 | Construction Administration | \N | 2023-03-01 | 2023-04-30 | Y | \N
1902301 | Contract Documentation | \N | 2021-05-01 | 2023-12-31 | Y | \N
1701410 | For Construction Drawings | \N | 2020-06-05 | 2022-06-10 | N | \N
2100205 | Design Development | \N | 2021-04-22 | 2021-09-13 | N | \N
2100206 | Design Development | \N | 2022-08-08 | 2022-08-08 | N | \N
2100207 | Design Development | \N | 2022-08-08 | 2022-08-08 | N | \N
20067 | Project Initiation | \N | 2022-09-23 | 2022-09-23 | N | S020
20067 | Conceptual Masterplanning | \N | 2022-11-01 | 2023-05-31 | N | S010
20067 | Schematic Design | \N | 2022-12-01 | 2023-05-31 | N | S020
20067 | Design Development | \N | 2023-06-01 | 2024-12-31 | N | S020
20067 | Contract Documentation | \N | 2024-01-01 | 2026-07-31 | N | S020
20067 | Construction Administration | Building A | 2024-01-01 | 2024-12-31 | N | S020
20067 | Construction Administration | Building B | 2025-08-01 | 2026-07-31 | N | S020
20067 | Construction Administration | Building C | 2026-01-01 | 2026-12-31 | N | S020
22113 | Project Initiation | \N | 2022-10-01 | 2022-10-01 | N | S020
22113 | Schematic Design | \N | 2022-10-01 | 2023-01-31 | N | S020
22113 | Design Development | \N | 2023-02-01 | 2023-11-15 | N | S020
22113 | Contract Documentation | \N | 2023-11-01 | 2024-05-31 | N | S020
22113 | Construction Administration | \N | 2024-06-01 | 2027-05-31 | N | S020
22129 | Preliminary Design | ID | 2023-06-01 | 2023-08-31 | N | S030
22129 | Detailed Design | ID | 2023-09-01 | 2024-01-31 | N | S030
22129 | Construction Administration | ID | 2024-02-01 | 2024-08-31 | N | S030
22129 | Project Initiation | ID | 2023-06-01 | 2023-06-01 | N | S030
22129 | Project Initiation | XXX LIGHTING (EXCLUDED) | 2023-06-01 | 2023-06-01 | Y | \N
22129 | Preliminary Design | XXX LIGHTING (EXCLUDED) | 2023-06-01 | 2023-06-01 | Y | \N
22129 | Detailed Design | XXX LIGHTING (EXCLUDED) | 2023-06-01 | 2023-06-01 | Y | \N
22129 | Construction Administration | XXX LIGHTING (EXCLUDED) | 2023-06-01 | 2023-06-01 | Y | \N
2204201 | Design Development | \N | 2022-10-01 | 2022-10-01 | \N | S020
2204201 | Contract Documentation | \N | 2022-10-01 | 2022-10-01 | \N | S020
2010501 | Contract Documentation | \N | 2021-08-31 | 2022-03-31 | \N | S020
2105805 | Project Initiation | \N | 2022-09-01 | 2022-09-01 | \N | S040
2105805 | Schematic Design | \N | 2022-09-01 | 2022-10-31 | \N | S040
22127 | Project Initiation | \N | 2022-09-01 | 2022-09-01 | N | S030
22127 | Preliminary Design | \N | 2022-11-03 | 2022-11-11 | N | S030
22127 | Detailed Design | \N | 2022-11-14 | 2023-02-28 | N | S030
22127 | Construction Administration | \N | 2023-03-01 | 2023-05-31 | N | S030
22128 | Project Initiation | ID | 2022-10-24 | 2022-10-24 | N | S030
22128 | Schematic Design | ID | 2022-11-28 | 2023-03-17 | N | S030
22128 | Detailed Design | ID | 2023-02-13 | 2023-10-31 | N | S030
22128 | Construction Administration | ID | 2023-12-01 | 2024-05-31 | N | S030
22128 | Project Initiation | SUBCON | 2022-10-24 | 2022-10-24 | N | S070
22128 | Schematic Design | SUBCON | 2022-11-28 | 2023-03-17 | N | S070
22128 | Detailed Design | SUBCON | 2023-02-13 | 2023-10-31 | N | S070
22128 | Construction Administration | SUBCON | 2023-12-01 | 2024-05-31 | N | S070
1722401 | Schematic Design | \N | 2017-11-01 | 2018-12-30 | N | S020
22109 | Project Initiation | ID | 2022-10-24 | 2022-10-24 | N | S030
22109 | Preliminary Design | ID | 2022-10-24 | 2022-11-18 | N | S030
22109 | Detailed Design | ID | 2022-11-21 | 2023-01-31 | N | S030
22109 | Construction Administration | ID: JANUARY TO MARCH | 2023-01-01 | 2023-03-31 | N | S030
22109 | Construction Administration | ID: SEPTEMBER | 2023-09-01 | 2023-09-30 | N | S030
21012B | Design Development | ID | 2022-10-17 | 2022-11-11 | N | S030
21012B | Contract Documentation | ID | 2022-11-14 | 2023-01-31 | N | S030
21012B | Construction Administration | ID | 2023-03-01 | 2023-08-31 | N | S030
21012B | Design Development | SUBCON | 2022-10-17 | 2022-11-11 | N | S070
21012B | Contract Documentation | SUBCON | 2022-11-14 | 2023-01-31 | N | S070
21012B | Construction Administration | SUBCON | 2023-03-01 | 2023-08-31 | N | S070
22136 | Schematic Design | Phase 1 | 2022-10-17 | 2022-12-31 | N | S030
22136 | Contract Documentation | Phase 1 | 2023-01-04 | 2023-03-31 | N | S030
22136 | Construction Administration | Phase 1: 1st month | 2023-05-01 | 2023-05-31 | N | S030
22136 | Schematic Design | Phase 2 | 2023-03-03 | 2023-07-14 | N | S030
22136 | Contract Documentation | Phase 2 | 2023-06-01 | 2023-12-31 | N | S030
22136 | Construction Administration | Phase 1: 2nd & 3rd month | 2023-10-01 | 2023-11-30 | N | S030
22136 | Project Initiation | \N | 2022-10-17 | 2022-10-17 | N | S030
22136 | Construction Administration | Phase 2 | 2023-12-01 | 2024-05-31 | N | S030
2207001 | Final Renderings | \N | 2022-05-02 | 2022-08-26 | N | S050
1612417 | Project Initiation | XXX | 2022-10-01 | 2022-10-01 | Y | S020
1612417 | Schematic Design | \N | 2022-10-01 | 2024-02-29 | N | S020
1612417 | Design Development | XXX | 2024-02-29 | 2024-02-29 | Y | S020
1612417 | Contract Documentation | XXX | 2024-02-29 | 2024-02-29 | Y | S020
2116201 | Project Initiation | \N | 2022-01-04 | 2022-01-04 | Y | S020
2116201 | Schematic Design | \N | 2022-01-04 | 2022-01-04 | Y | S020
2116201 | Contract Documentation | \N | 2022-01-04 | 2022-01-04 | Y | S020
2116201 | Construction Administration | \N | 2022-01-04 | 2022-01-04 | Y | S020
22140 | Concept Design | Design Competition | 2022-10-01 | 2022-10-01 | \N | S020
2017406 | Construction Administration | \N | 2022-11-01 | 2023-02-15 | N | S020
22135 | Conceptual Masterplanning | Test Fit Masterplan | 2022-10-15 | 2023-04-15 | N | S010
1911201 | Others | VAT for 19112 | 2020-01-01 | 2020-03-31 | \N | S030
2115001 | Final Renderings | \N | 2021-10-27 | 2021-11-18 | \N | S050
2118301 | Project Initiation | \N | 2022-02-01 | 2022-02-01 | \N | \N
2118301 | Schematic Design | \N | 2022-02-01 | 2022-02-01 | \N | \N
2118301 | Design Development | \N | 2022-02-01 | 2022-02-01 | \N | \N
2118301 | Contract Documentation | \N | 2022-02-01 | 2022-02-01 | \N | \N
2118301 | Construction Administration | \N | 2022-02-01 | 2022-02-01 | \N | \N
2012801 | Construction Administration | \N | 2023-01-01 | 2025-08-31 | Y | S020
22134 | Project Initiation | \N | 2022-12-01 | 2022-12-01 | N | S010
22134 | Conceptual Masterplanning | \N | 2022-12-01 | 2023-02-28 | N | S010
1923202 | Contract Documentation | \N | 2022-09-01 | 2022-10-31 | N | S070
1817229 | Construction Administration | Architectural | 2022-11-01 | 2024-07-31 | N | S020
1817229 | Construction Administration | BIM | 2022-11-01 | 2023-02-28 | N | S060
1817229 | Construction Administration | Structural | 2022-11-01 | 2023-12-31 | N | S070
1817229 | Construction Administration | MEPF + Lift | 2022-11-01 | 2024-07-31 | N | S070
1817229 | Construction Administration | Facade | 2022-11-01 | 2024-01-31 | N | S070
1817229 | Construction Administration | ID | 2022-11-01 | 2023-02-28 | N | S070
1817229 | Construction Administration | Landscape | 2022-11-01 | 2023-03-31 | N | S070
1817229 | Construction Administration | Sustainability | 2022-11-01 | 2023-03-31 | N | S070
22161 | Project Initiation | \N | 2022-12-07 | 2022-12-07 | N | S010
22161 | Conceptual Masterplanning | Preliminary Conceptual MP | 2022-12-08 | 2023-03-31 | N | S010
22161 | Conceptual Masterplanning | Final Conceptual MP | 2023-04-01 | 2023-05-31 | N | S010
1800912 | Construction Administration | \N | 2022-04-01 | 2022-04-30 | \N | S020
22150 | Project Initiation | AR | 2023-01-01 | 2023-01-01 | N | S020
22150 | Schematic Design | AR | 2023-01-01 | 2023-04-13 | N | S020
22150 | Design Development | AR | 2023-04-14 | 2023-08-15 | N | S020
22150 | Contract Documentation | AR | 2023-08-01 | 2023-12-31 | N | S020
22150 | Construction Administration | AR | 2024-01-01 | 2024-12-31 | N | S020
22150 | Project Initiation | For ID works | 2023-01-01 | 2023-01-01 | N | S030
22150 | Schematic Design | For ID works | 2023-01-01 | 2023-08-31 | N | S030
22150 | Design Development | For ID works | 2023-07-16 | 2023-11-30 | N | S030
22150 | Contract Documentation | For ID works | 2023-12-01 | 2024-04-30 | N | S030
22150 | Construction Administration | For ID works | 2024-03-01 | 2025-04-30 | N | S030
22165 | Pre-Design Services | Demolition Package | 2022-11-01 | 2022-12-31 | N | S020
22152 | Project Initiation | AR | 2023-01-03 | 2023-01-03 | N | S020
22152 | Preliminary Design | AR | 2023-01-03 | 2023-07-31 | N | S020
22152 | Detailed Design | AR | 2023-08-01 | 2023-10-31 | N | S020
22152 | Construction Administration | AR | 2023-10-01 | 2024-05-31 | N | S020
22152 | Project Initiation | ID | 2023-01-03 | 2023-01-03 | N | S030
22152 | Preliminary Design | ID | 2023-01-03 | 2023-07-31 | N | S030
22152 | Detailed Design | ID | 2023-08-01 | 2024-02-29 | N | S030
22152 | Construction Administration | ID | 2023-10-01 | 2024-05-31 | N | S030
22152 | Project Initiation | Landscape | 2023-01-03 | 2023-01-03 | N | S070
22152 | Preliminary Design | Landscape | 2023-01-03 | 2023-07-31 | N | S070
22152 | Detailed Design | Landscape | 2023-08-01 | 2023-10-31 | N | S070
22152 | Construction Administration | Landscape | 2023-10-01 | 2024-05-31 | N | S070
22120 | Project Initiation | AR | 2022-12-20 | 2022-12-20 | Y | S020
22120 | Concept Design | Not in SO | 2022-12-20 | 2022-12-20 | Y | S020
22120 | Schematic Design | AR | 2022-12-20 | 2022-12-20 | Y | S020
22120 | Design Development | AR | 2022-12-20 | 2022-12-20 | Y | S020
22120 | Contract Documentation | AR | 2022-12-20 | 2022-12-20 | Y | S020
22120 | Construction Administration | AR | 2022-12-20 | 2022-12-20 | Y | S020
22167 | Tenant Design Guidelines | \N | 2023-01-09 | 2023-04-30 | N | S020
22145 | Project Initiation | Building 4 - AR | 2023-01-01 | 2023-01-01 | N | S020
22145 | Preliminary Design | Building 4 - AR | 2023-01-01 | 2024-06-30 | N | S020
22145 | Detailed Design | Building 4 - AR | 2024-05-01 | 2024-06-30 | N | S020
22145 | Construction Administration | Building 4 - AR | 2024-09-01 | 2026-08-31 | N | S020
22145 | Project Initiation | OPTIONAL: ID - Building 4 | 2023-01-01 | 2023-01-01 | Y | S030
22145 | Preliminary Design | OPTIONAL: ID - Building 4 | 2023-01-01 | 2023-01-01 | Y | S030
22145 | Detailed Design | OPTIONAL: ID - Building 4 | 2023-01-01 | 2023-01-01 | Y | S030
22145 | Construction Administration | OPTIONAL: ID - Building 4 | 2023-01-01 | 2023-01-01 | Y | S030
22145 | Project Initiation | Building 6 - AR | 2023-01-01 | 2023-01-01 | N | S020
22145 | Preliminary Design | Building 6 - AR | 2023-01-01 | 2023-08-31 | N | S020
22145 | Detailed Design | Building 6 - AR | 2023-09-01 | 2024-06-30 | N | S020
22145 | Construction Administration | Building 6 - AR | 2024-09-01 | 2027-08-31 | N | S020
22145 | Tender | Building 4 - Upon Completion of Bidding, Evaluation, and Negotiation Phase | 2024-07-01 | 2024-08-31 | N | S020
22145 | Tender | OPTIONAL: ID B4 - Upon Completion of Bidding, Evaluation, and Negotiation Phase | 2023-01-01 | 2023-01-01 | Y | S030
22145 | Tender | Building 6 - Upon Completion of Bidding, Evaluation, and Negotiation Phase | 2024-07-01 | 2024-08-31 | N | S020
1506814 | Construction Administration | AR | 2023-01-01 | 2023-06-30 | Y | S020
1506815 | Construction Administration | AR | 2023-01-01 | 2023-06-30 | Y | S020
1302905 | Construction Administration | AR | 2023-01-01 | 2023-02-28 | N | S020
22077 | Project Initiation | AR | 2023-01-03 | 2023-01-03 | N | S020
22077 | Planning and Programming | AR | 2023-01-03 | 2023-03-31 | N | S010
22077 | Concept Design | AR | 2023-03-01 | 2023-11-30 | N | S020
22077 | Schematic Design | AR | 2024-02-12 | 2024-05-31 | N | S020
22077 | Design Development | AR | 2024-06-01 | 2024-08-31 | N | S020
22077 | Contract Documentation | AR | 2024-09-01 | 2024-11-30 | N | S020
22077 | Tender | AR | 2024-12-01 | 2024-12-31 | N | S020
22077 | Construction Administration | AR | 2025-01-01 | 2027-12-31 | N | S020
22077 | Post Construction Phase | AR | 2028-01-01 | 2028-12-31 | N | S020
22077 | Project Initiation | Subcon | 2023-01-03 | 2023-01-03 | N | S070
22077 | Planning and Programming | Subcon | 2023-01-03 | 2023-03-31 | N | S070
22077 | Concept Design | Subcon | 2023-03-01 | 2023-11-30 | N | S070
22077 | Schematic Design | Subcon | 2024-02-12 | 2024-05-31 | N | S070
22077 | Design Development | Subcon | 2024-06-01 | 2024-08-31 | N | S070
22077 | Contract Documentation | Subcon | 2024-09-01 | 2024-11-30 | N | S070
22077 | Tender | Subcon | 2024-12-01 | 2024-12-31 | N | S070
22077 | Construction Administration | Subcon | 2025-01-01 | 2027-12-31 | N | S070
22077 | Post Construction Phase | Subcon | 2028-01-01 | 2028-12-31 | N | S070
22077 | Project Initiation | ID | 2023-01-03 | 2023-01-03 | N | S030
22077 | Planning and Programming | XXXX | 2023-01-03 | 2023-01-03 | Y | S030
22077 | Concept Design | ID | 2023-03-01 | 2023-11-30 | N | S030
22077 | Schematic Design | ID | 2024-02-12 | 2024-05-31 | N | S030
22077 | Design Development | ID | 2024-06-01 | 2024-08-31 | N | S030
22077 | Contract Documentation | ID | 2024-09-01 | 2024-11-30 | N | S030
22077 | Tender | ID | 2024-12-01 | 2024-12-31 | N | S030
22077 | Construction Administration | ID | 2025-01-01 | 2027-12-31 | N | S030
22077 | Post Construction Phase | ID | 2028-01-01 | 2028-12-31 | N | S030
22077 | Project Initiation | BIM LOD 300 | 2023-01-03 | 2023-01-03 | N | S060
22077 | Planning and Programming | XXX | 2023-01-03 | 2023-01-03 | Y | S060
22077 | Concept Design | XXX | 2023-01-03 | 2023-01-03 | Y | S060
22077 | Schematic Design | XXX | 2023-01-03 | 2023-01-03 | Y | S060
22077 | Design Development | BIM LOD 300 | 2024-06-01 | 2024-08-31 | N | S060
22077 | Contract Documentation | BIM LOD 300 | 2024-09-01 | 2024-11-30 | N | S060
22077 | Tender | XXX | 2023-01-03 | 2023-01-03 | Y | S060
22077 | Construction Administration | XXX | 2023-01-03 | 2023-01-03 | Y | S060
22077 | Post Construction Phase | XXX | 2023-01-03 | 2023-01-03 | Y | S060
22077 | Project Initiation | EGD | 2023-01-03 | 2023-01-03 | N | S040
22077 | Planning and Programming | XXX | 2023-01-03 | 2023-01-03 | Y | S040
22077 | Concept Design | EGD | 2023-03-01 | 2023-11-30 | N | S040
22077 | Schematic Design | EGD | 2024-02-12 | 2024-05-31 | N | S040
22077 | Design Development | EGD | 2024-06-01 | 2024-08-31 | N | S040
22077 | Contract Documentation | EGD | 2024-09-01 | 2024-11-30 | N | S040
22077 | Tender | EGD | 2024-12-01 | 2024-12-31 | N | S040
22077 | Construction Administration | EGD | 2025-01-01 | 2027-12-31 | N | S040
22077 | Post Construction Phase | EGD | 2028-01-01 | 2028-12-31 | N | S040
22139 | Project Initiation | ID | 2023-01-19 | 2023-01-19 | N | S030
22139 | Preliminary Design | ID | 2023-01-19 | 2023-07-31 | Y | S030
22139 | Detailed Design | ID | 2023-08-01 | 2023-10-31 | Y | S030
22139 | Construction Administration | ID | 2023-11-01 | 2024-04-30 | Y | S030
22163 | Conceptual Masterplanning | Draft & Final MP | 2023-01-03 | 2023-04-15 | N | S010
22163 | Schematic Design | Concept/ SD | 2023-03-01 | 2023-07-31 | N | S020
22163 | Detailed Design | DD/ Detailed Design | 2023-05-01 | 2024-02-29 | N | S020
22163 | Contract Documentation | Tender/ For Construction Package | 2023-08-01 | 2023-12-31 | N | S020
22163 | Construction Administration | \N | 2024-01-01 | 2025-04-30 | N | S020
22163 | Project Initiation | Including Test Fit | 2023-01-03 | 2023-01-03 | N | S020
22163 | Schematic Design | Fire & Life Safety: Concept/ SD | 2023-03-01 | 2023-10-31 | N | S070
22163 | Detailed Design | Fire & Life Safety: DD/ Detailed Design | 2023-05-01 | 2023-11-30 | N | S070
22163 | Contract Documentation | Fire & Life Safety: Tender/ For Construction Package | 2023-08-01 | 2023-12-07 | N | S070
22163 | Construction Administration | Fire & Life Safety: CA | 2024-01-01 | 2025-04-30 | N | S070
2112501 | Construction Administration | AR | 2023-01-01 | 2023-04-30 | Y | \N
22173 | Project Initiation | \N | 2023-01-23 | 2023-01-23 | N | S010
22173 | Conceptual Masterplanning | Preliminary Concept MP | 2023-01-23 | 2023-03-31 | N | S010
22173 | Conceptual Masterplanning | Final Conceptual MP | 2023-04-01 | 2023-10-31 | N | S010
22176 | Project Initiation | \N | 2023-01-23 | 2023-01-23 | N | S010
22176 | Conceptual Masterplanning | Upon Completion Conceptual Plan Studies | 2023-01-23 | 2023-05-31 | N | S010
1909901 | Contract Documentation | AR | 2022-05-31 | 2022-12-31 | N | S020
1909902 | Design Development | AR | 2022-01-01 | 2022-01-14 | N | S020
1909903 | Design Development | AR | 2022-01-01 | 2022-01-14 | N | S020
1506905 | Construction Administration | AR | 2022-07-01 | 2022-12-31 | N | S020
23010 | Concept Design | ID | 2023-01-03 | 2023-03-31 | \N | S030
1807801 | Contract Documentation | AR | 2021-08-01 | 2022-01-31 | N | S020
1722303 | Construction Administration | AR | 2022-06-01 | 2022-06-01 | Y | \N
1722304 | Construction Administration | AR | 2022-06-01 | 2022-06-01 | Y | \N
1908001 | Design Development | AR | 2022-06-01 | 2022-08-31 | N | S020
1908002 | Design Development | AR | 2022-06-01 | 2022-08-31 | N | S020
1908003 | Design Development | AR | 2022-06-01 | 2022-08-31 | \N | S020
1908004 | Contract Documentation | AR: VO NO. 4.1 GF CURTAIN WALL (VO05) | 2023-01-01 | 2024-02-07 | N | S020
1908004 | Contract Documentation | AR: VO NO. 4.2 APMC MAINTAINABILITY (VO06) | 2023-01-01 | 2024-03-31 | N | S020
1908004 | Contract Documentation | AR: VO NO. 4.3 3BR ADJUSTMENT (VO07) | 2023-01-01 | 2024-03-31 | N | S020
22118 | Conceptual Masterplanning | COMPETITION | 2022-12-22 | 2023-02-28 | N | \N
22118 | Project Initiation | AR | 2023-10-01 | 2023-10-01 | N | S020
22118 | Planning and Programming | AR | 2023-10-01 | 2024-04-30 | N | S020
22118 | Concept Design | AR | 2024-04-01 | 2024-08-31 | N | S020
22118 | Schematic Design | AR | 2024-09-01 | 2024-11-30 | N | S020
22118 | Design Development | AR | 2024-12-01 | 2025-07-31 | N | S020
22118 | Contract Documentation | AR | 2025-08-01 | 2026-02-28 | N | S020
22118 | Construction Administration | AR | 2026-03-01 | 2030-02-28 | N | S020
22118 | Project Initiation | ID | 2023-10-01 | 2023-10-01 | N | S030
22118 | Planning and Programming | ID | 2023-10-01 | 2024-04-30 | N | S030
22118 | Concept Design | ID | 2024-04-01 | 2024-08-31 | N | S030
22118 | Schematic Design | ID | 2024-09-01 | 2024-11-30 | N | S030
22118 | Design Development | ID | 2024-12-01 | 2025-07-31 | N | S030
22118 | Contract Documentation | ID | 2025-08-01 | 2026-02-28 | N | S030
22118 | Construction Administration | ID | 2026-03-01 | 2030-02-28 | N | S030
22054 | Project Initiation | ID | 2023-01-27 | 2023-01-27 | N | S030
22054 | Preliminary Design | ID | 2023-01-27 | 2023-02-15 | N | S030
22054 | Detailed Design | ID | 2023-02-16 | 2023-04-30 | N | S030
22054 | Construction Administration | ID | 2023-06-01 | 2023-07-31 | N | S030
22054 | Project Initiation | XXX | 2023-01-27 | 2023-01-27 | Y | \N
22054 | Preliminary Design | XXX | 2023-01-27 | 2023-01-27 | Y | \N
22054 | Detailed Design | XXX | 2023-01-27 | 2023-01-27 | Y | \N
22054 | Construction Administration | XXX | 2023-01-27 | 2023-01-27 | Y | \N
23008 | Test-Fit | MP | 2023-01-27 | 2023-02-28 | Y | \N
22175 | Project Initiation | \N | 2023-01-23 | 2023-01-23 | N | S010
22175 | Conceptual Masterplanning | Upon completion of Conceptual Plan Studies | 2023-01-23 | 2023-05-31 | N | S010
1902304 | Contract Documentation | AR | 2023-01-10 | 2023-04-30 | N | S020
23001 | Data Collection and Analysis | MP | 2023-01-03 | 2023-02-28 | Y | \N
23001 | Visioning and Options Generation | MP | 2023-03-01 | 2023-03-31 | Y | \N
23001 | Conceptual Masterplanning | MP | 2023-04-01 | 2023-04-30 | Y | \N
2212701 | Project Initiation | ID | 2023-01-16 | 2023-01-16 | N | S030
2212701 | Concept Design | ID | 2023-01-16 | 2023-03-31 | N | S030
2212701 | Contract Documentation | ID | 2023-04-03 | 2023-04-28 | N | S030
2212701 | Construction Administration | ID | 2023-05-01 | 2023-05-31 | N | S030
21032 | Project Initiation | \N | 2023-02-08 | 2023-02-08 | N | S050
21032 | Final Renderings | \N | 2023-02-08 | 2024-12-31 | N | S050
23009 | Project Initiation | AR | 2023-02-01 | 2023-02-01 | N | S020
23009 | Concept Design | AR | 2023-02-01 | 2024-04-30 | N | S020
23014 | Final Renderings | \N | 2023-02-06 | 2023-02-28 | N | S050
2112901 | Schematic Design | AR | 2022-01-04 | 2022-01-04 | Y | S020
1506816 | Construction Administration | AR | 2023-03-01 | 2023-09-30 | N | S020
1506817 | Construction Administration | AR | 2023-03-01 | 2023-09-30 | N | S020
1818207 | Construction Administration | AR | 2022-09-01 | 2023-10-31 | N | S020
1302906 | Construction Administration | AR | 2023-03-01 | 2023-06-30 | N | S020
1817230 | Construction Administration | AR | 2023-04-01 | 2025-02-28 | N | S020
1817230 | Construction Administration | EGD | 2023-04-01 | 2024-03-31 | N | S040
1817230 | Construction Administration | MEPF | 2023-04-01 | 2025-02-28 | N | S070
1817230 | Construction Administration | ID | 2023-04-01 | 2025-02-28 | N | S070
1817230 | Construction Administration | LANDSCAPE | 2023-04-01 | 2024-01-31 | N | S070
1817230 | Construction Administration | LIGHTING | 2023-04-01 | 2024-05-31 | N | S070
1817230 | Construction Administration | KITCHEN | 2023-04-01 | 2024-01-31 | N | S070
1817230 | Construction Administration | ACOUSTIC | 2023-04-01 | 2024-01-31 | N | S070
1817230 | Construction Administration | SUSTAINABILITY | 2023-04-01 | 2025-02-28 | N | S070
1817230 | Construction Administration | FACADE | 2023-04-01 | 2024-05-31 | N | S070
23017 | Project Initiation | \N | 2023-03-09 | 2023-03-09 | N | S010
23017 | Data Collection and Analysis | \N | 2023-03-09 | 2023-07-31 | N | S010
23017 | Visioning and Options Generation | \N | 2023-08-01 | 2023-10-31 | N | S010
23017 | Conceptual Masterplanning | Upon Completion of Land use Planning | 2023-09-01 | 2023-11-30 | N | S010
23017 | Conceptual Masterplanning | Upon Completion of Conceptual MP | 2023-10-01 | 2024-06-30 | N | S010
23036 | Project Initiation | ID | 2023-03-16 | 2023-03-16 | N | S030
23036 | Detailed Design | UPON COMPLETION OF DETAILED DESIGN DRAWINGS | 2023-03-16 | 2023-04-15 | N | S030
2112902 | Schematic Design | AR | 2023-03-23 | 2023-03-23 | Y | S020
2112902 | Contract Documentation | AR | 2023-03-23 | 2023-03-23 | Y | S020
2112902 | Construction Administration | AR - INCLUDING TURNOVER | 2023-03-23 | 2023-03-23 | Y | S020
2112902 | Schematic Design | SUBCON | 2023-03-23 | 2023-03-23 | Y | S070
2112902 | Contract Documentation | SUBCON | 2023-03-23 | 2023-03-23 | Y | S070
2112902 | Construction Administration | SUBCON - INCLUDING TURNOVER | 2023-03-23 | 2023-03-23 | Y | S070
23056 | Test-Fit | \N | 2023-03-27 | 2023-04-21 | N | S010
23007 | Concept Design | ID | 2023-03-27 | 2023-05-12 | N | S030
23007 | Schematic Design | ID | 2023-04-29 | 2023-07-14 | N | S030
23007 | Design Development | ID - DETAILED DESIGN (90%) | 2023-06-21 | 2023-07-31 | N | S030
23007 | Contract Documentation | ID - TENDER DRAWINGS AND PERFORMANCE SPECIFICATION | 2023-08-01 | 2023-08-31 | N | S030
23007 | Tender | ID - GC TENDER | 2023-08-20 | 2023-10-31 | N | S030
23007 | Tender | ID - CONSTRUCTION PERMITS | 2023-11-01 | 2024-01-31 | N | S030
23007 | Construction Administration | ID | 2024-02-01 | 2024-04-30 | N | S030
23007 | Post Construction Phase | ID - POST CONSTRUCTION PERMITS, DEFECTS, AND TESTING | 2024-05-01 | 2024-06-30 | N | S030
23007 | Concept Design | SUBCON | 2023-03-30 | 2023-05-12 | N | S070
23007 | Schematic Design | SUBCON | 2023-04-29 | 2023-07-14 | N | S070
23007 | Design Development | SUBCON - DETAILED DESIGN (90%) | 2023-06-21 | 2023-07-31 | N | S070
23007 | Contract Documentation | SUBCON - TENDER DRAWINGS AND PERFORMANCE SPECIFICATION | 2023-08-01 | 2023-08-31 | N | S070
23007 | Tender | SUBCON - GC TENDER | 2023-08-20 | 2023-10-31 | N | S070
23007 | Tender | SUBCON - CONSTRUCTION PERMITS | 2023-11-01 | 2024-01-31 | N | S070
23007 | Construction Administration | SUBCON | 2024-02-01 | 2024-04-30 | N | S070
23007 | Post Construction Phase | SUBCON - POST CONSTRUCTION PERMITS, DEFECTS, AND TESTING | 2024-05-01 | 2024-06-30 | N | S070
23039 | Concept Design | ID | 2023-03-27 | 2023-04-14 | \N | S030
1711508 | Project Initiation | AR | 2023-06-01 | 2023-06-01 | N | S020
1711508 | Schematic Design | AR- Concept | 2023-07-01 | 2023-09-30 | N | S020
1711508 | For Construction Drawings | AR - Tender Documentation/ FCD | 2023-10-15 | 2023-11-30 | N | S020
1711508 | Tender | AR | 2023-12-01 | 2023-12-31 | N | S020
1711508 | Project Initiation | Lighting | 2023-06-01 | 2023-06-01 | N | S070
1711508 | Schematic Design | Lighting - Concept | 2023-07-01 | 2023-09-30 | N | S070
1711508 | For Construction Drawings | Lighting - Tender Documentation/ FCD | 2023-10-15 | 2023-11-30 | N | S070
1711508 | Tender | Lighting | 2023-12-01 | 2023-12-31 | N | S070
23022 | Design Development | ID | 2023-03-20 | 2023-04-28 | N | S030
23022 | Contract Documentation | ID | 2023-04-24 | 2023-06-30 | N | S030
23022 | Construction Administration | ID | 2023-08-01 | 2024-01-31 | N | S030
23022 | Design Development | SUBCON | 2023-04-14 | 2023-04-28 | N | S070
23022 | Contract Documentation | SUBCON | 2023-04-24 | 2023-06-30 | N | S070
23022 | Construction Administration | SUBCON | 2023-08-01 | 2024-01-31 | N | S070
2201701 | Schematic Design | ID | 2022-04-01 | 2022-04-01 | Y | S030
2201701 | Contract Documentation | ID | 2022-04-01 | 2022-04-01 | Y | S030
2201701 | Construction Administration | ID: CA & TURNOVER | 2022-04-01 | 2022-04-01 | Y | S030
23038 | Project Initiation | AR | 2023-03-28 | 2023-03-28 | N | S020
23038 | Schematic Design | AR - CONCEPT/SD | 2023-03-28 | 2024-02-29 | N | S020
23038 | Design Development | AR | 2024-03-01 | 2024-06-30 | N | S020
23038 | Contract Documentation | AR | 2024-07-01 | 2024-07-31 | N | S020
23038 | Tender | AR - NOT INCLUDED IN SO | 2024-08-01 | 2024-08-31 | Y | S020
23038 | Construction Administration | AR | 2024-09-01 | 2025-11-30 | N | S020
23038 | Post Construction Phase | AR - TURN OVER | 2026-11-01 | 2026-11-30 | N | S020
23038 | Project Initiation | SUBCON | 2023-03-28 | 2023-03-28 | N | S070
23038 | Schematic Design | SUBCON - CONCEPT/SD | 2023-03-28 | 2024-02-29 | N | S070
23038 | Design Development | SUBCON | 2024-03-01 | 2024-06-30 | N | S070
23038 | Contract Documentation | SUBCON | 2024-07-01 | 2024-07-31 | N | S070
23038 | Tender | SUBCON - NOT INCLUDED IN SO | 2024-08-01 | 2024-08-31 | Y | S070
23038 | Construction Administration | SUBCON | 2024-09-01 | 2025-11-30 | N | S070
23038 | Post Construction Phase | SUBCON - TURN OVER | 2026-11-01 | 2026-11-30 | N | S070
1608503 | Construction Administration | ID | 2022-11-01 | 2023-03-31 | N | S030
23019 | Project Initiation | ID | 2023-04-13 | 2023-04-13 | N | S030
23019 | Preliminary Design | ID | 2023-04-14 | 2024-04-30 | N | S030
23041 | Project Initiation | Mobilization | 2023-04-15 | 2023-04-15 | N | S050
23041 | Animation | Upon Completion of Initial Animation and 360 Virtual Tour Render | 2023-05-01 | 2023-05-31 | N | S050
23041 | Animation | Upon Completion ofFinal Animation and 360 Virtual Tour Render | 2023-06-01 | 2023-07-31 | N | S050
16039J17 | Construction Administration | AR | 2023-04-01 | 2023-07-31 | N | S020
16039J17 | Construction Administration | STRUCTURAL ENGINEERING | 2023-04-01 | 2023-07-31 | N | S070
16039J17 | Construction Administration | MECHANICAL ENGINEERING | 2023-04-01 | 2023-07-31 | N | S070
16039J17 | Construction Administration | ELECTRICAL ENGINEERING | 2023-04-01 | 2023-07-31 | N | S070
16039J17 | Construction Administration | PLUMB., SANIT. & FIRE PROTECT. | 2023-04-01 | 2023-07-31 | N | S070
1608501 | Detailed Design | ID | 2018-01-01 | 2019-12-31 | \N | S030
23057 | Concept Design | ID CODE REVIEW | 2023-04-25 | 2023-08-31 | N | S030
23057 | Concept Design | SUBCON CODE REVIEW | 2023-05-15 | 2023-08-31 | N | S070
1711507 | Construction Administration | AR | 2022-03-01 | 2024-02-29 | N | S020
1711507 | Construction Administration | SUBCON | 2022-03-01 | 2024-02-29 | N | S070
2106002 | Project Initiation | SUBCON | 2023-04-01 | 2023-04-01 | N | S070
2106002 | Others | SUBCON: UPON COMPLETION OF ADVISORY CONSULTING | 2023-04-01 | 2023-04-15 | N | S070
2106002 | Others | SUBCON: UPON COMPLETION OF FOLLOW-UP REVIEW/MEETINGS | 2023-04-16 | 2023-04-30 | N | S070
23042 | Project Initiation | AR | 2023-04-01 | 2023-04-01 | N | S020
23042 | Concept Design | AR | 2023-04-01 | 2023-04-30 | N | S020
23042 | Schematic Design | AR | 2023-05-01 | 2024-03-31 | N | S020
23042 | Detailed Design | AR | 2024-04-01 | 2024-07-31 | N | S020
23042 | Construction Administration | AR | 2024-08-01 | 2027-07-31 | N | S020
23042 | Project Initiation | ID | 2023-05-04 | 2023-05-04 | N | S030
23042 | Concept Design | ID | 2023-09-01 | 2024-02-29 | N | S030
23042 | Schematic Design | ID: BRANDED RESIDENCE | 2024-03-01 | 2024-04-30 | N | S030
23042 | Detailed Design | ID: MOCK-UP HOTEL VILLA | 2024-03-01 | 2024-05-31 | N | S030
23042 | Construction Administration | ID: MOCK-UP HOTEL VILLA | 2024-06-01 | 2027-05-31 | N | S030
23042 | Project Initiation | EGD | 2023-05-04 | 2023-05-04 | N | S040
23042 | Concept Design | EGD | 2023-10-01 | 2024-03-31 | N | S040
23042 | Schematic Design | EGD | 2024-04-01 | 2024-05-31 | N | S040
23042 | Detailed Design | EGD | 2024-06-01 | 2024-08-31 | N | S040
23042 | Construction Administration | EGD | 2024-09-01 | 2027-08-31 | N | S040
23042 | Project Initiation | LANDSCAPE | 2023-05-04 | 2023-05-04 | N | S070
23042 | Concept Design | LANDSCAPE | 2023-10-01 | 2024-03-31 | N | S070
23042 | Schematic Design | LANDSCAPE | 2024-02-01 | 2024-05-31 | N | S070
23042 | Detailed Design | LANDSCAPE | 2024-04-01 | 2024-07-31 | N | S070
23042 | Construction Administration | LANDSCAPE | 2024-08-01 | 2027-07-31 | N | S070
23042 | Schematic Design | ID: AMENITIES | 2024-03-01 | 2024-04-30 | N | S030
23042 | Schematic Design | ID: HOTEL GUESTROOM | 2024-03-01 | 2024-04-30 | N | S030
23042 | Schematic Design | ID: BACK OF HOUSE | 2024-02-01 | 2024-03-31 | N | S030
23042 | Detailed Design | ID: MOCK UP BRANDED RESIDENCE | 2024-03-01 | 2024-04-30 | N | S030
23042 | Detailed Design | ID: AMENITIES | 2024-04-01 | 2024-06-30 | N | S030
23042 | Detailed Design | ID: HOTEL GUESTROOMS | 2024-07-01 | 2024-08-31 | N | S030
23042 | Detailed Design | ID: BRANDED RESIDENCE | 2024-05-01 | 2024-06-30 | N | S030
23042 | Detailed Design | ID: BACK OF HOUSE | 2024-04-01 | 2024-06-30 | N | S030
23042 | Construction Administration | ID: MOCK-UP BRANDED RESIDENCE | 2024-05-01 | 2027-04-30 | N | S030
23042 | Construction Administration | ID: AMENITIES | 2024-07-01 | 2027-06-30 | N | S030
23042 | Construction Administration | ID: HOTEL GUESTROOMS | 2024-09-01 | 2027-08-31 | N | S030
23042 | Construction Administration | ID: BRANDED RESIDENCE | 2024-07-01 | 2027-06-30 | N | S030
23042 | Construction Administration | ID: BACK OF HOUSE | 2024-07-01 | 2027-06-30 | N | S030
1403206 | Contract Documentation | \N | 2021-09-01 | 2023-10-31 | N | S020
23072 | Project Initiation | AR | 2023-05-12 | 2023-05-12 | N | S020
23072 | Concept Design | AR | 2023-05-12 | 2023-08-31 | N | S020
23072 | Schematic Design | AR | 2023-09-01 | 2023-11-17 | N | S020
23072 | Contract Documentation | AR: FOR TENDER / FOR CONSTRUCTION | 2024-05-01 | 2024-06-30 | N | S020
23072 | Construction Administration | AR | 2024-07-01 | 2027-06-30 | N | S020
23072 | Design Development | AR: FOR REVIEW / FOR PERMIT | 2023-11-18 | 2024-04-30 | N | S020
1906502 | Construction Administration | AR | 2023-04-01 | 2023-04-01 | Y | \N
23067 | Project Initiation | AR | 2023-05-05 | 2023-05-05 | N | S020
23067 | Concept Design | AR | 2023-05-15 | 2023-06-20 | N | S020
23067 | Schematic Design | AR | 2023-06-21 | 2023-09-30 | N | S020
23067 | Contract Documentation | AR: FOR BID PLANS AND FOR CONSTRUCTION | 2024-01-01 | 2024-03-31 | N | S020
23067 | Construction Administration | AR | 2024-05-01 | 2028-04-30 | N | S020
23067 | Design Development | AR: FOR PERMIT AND FOR REVIEW | 2023-10-01 | 2023-12-31 | N | S020
23046 | Project Initiation | AR | 2023-05-05 | 2023-05-05 | N | S020
23046 | Concept Design | AR | 2023-05-15 | 2023-06-30 | N | S020
23046 | Schematic Design | AR | 2023-07-01 | 2023-09-30 | N | S020
23046 | Contract Documentation | AR: FOR TENDER/ FOR CONSTRUCTION | 2024-01-01 | 2024-04-30 | N | S020
23046 | Construction Administration | AR | 2024-05-01 | 2028-04-30 | N | S020
23046 | Design Development | AR: FOR REVIEW/ FOR PERMIT | 2023-10-01 | 2023-12-31 | N | S020
23078 | Project Initiation | AR | 2023-05-05 | 2023-05-05 | N | S020
23078 | Concept Design | AR | 2023-05-15 | 2023-06-14 | N | S020
23078 | Schematic Design | AR | 2023-07-15 | 2023-10-31 | N | S020
23078 | Contract Documentation | AR: FOR TENDER / FOR CONSTRUCTION | 2024-03-01 | 2024-03-31 | N | S020
23078 | Construction Administration | AR | 2024-05-01 | 2027-04-30 | N | S020
23078 | Design Development | AR: FOR REVIEW / FOR PERMIT | 2023-11-01 | 2024-02-29 | N | S020
23079 | Project Initiation | AR | 2023-05-08 | 2023-05-08 | N | S020
23079 | Concept Design | AR | 2023-05-08 | 2023-07-31 | N | S020
23079 | Schematic Design | AR: FOR REVIEW / FOR PERMIT | 2023-08-01 | 2024-01-31 | N | S020
23079 | Contract Documentation | AR: DETAILED DESIGN (FOR TENDER / FOR CONSTRUCTION ) | 2024-01-01 | 2024-06-30 | N | S020
23079 | Construction Administration | AR | 2024-07-01 | 2028-06-30 | N | S020
23068 | Project Initiation | \N | 2023-05-08 | 2023-05-08 | N | S020
23068 | Design Development | ON HOLD: FOR REVIEW / FOR PERMIT | 2023-05-08 | 2024-04-15 | Y | S020
23068 | Contract Documentation | ON HOLD: FOR TENDER / FOR CONSTRUCTION | 2024-04-16 | 2024-06-30 | Y | S020
23068 | Construction Administration | ON HOLD | 2024-07-01 | 2026-06-30 | Y | S020
23068 | Concept Design | ON HOLD: CODE COMPLIANCE | 2023-05-08 | 2023-11-30 | Y | S020
23068 | Schematic Design | ON HOLD: CODE COMPLIANCE | 2023-05-08 | 2024-01-31 | Y | S020
2207201 | Schematic Design | (CONCEPT/SD) | 2023-05-01 | 2023-07-31 | N | S030
2207201 | Tender | (DD/CD) | 2023-08-01 | 2023-12-31 | N | S030
2207201 | Construction Administration | XXX | 2023-05-01 | 2023-05-01 | Y | \N
2207203 | Project Initiation | \N | 2023-05-10 | 2023-05-10 | Y | S030
2207203 | Schematic Design | CONCEPT/SD | 2023-05-10 | 2023-06-06 | Y | S030
2207203 | Design Development | \N | 2023-06-07 | 2023-06-27 | Y | S030
2207203 | Tender | \N | 2023-06-28 | 2023-07-31 | Y | S030
2207203 | Construction Administration | \N | 2023-08-01 | 2024-07-31 | Y | S030
2207203 | Project Initiation | SUBCON | 2023-05-10 | 2023-05-10 | Y | S070
2207203 | Schematic Design | SUBCON - CONCEPT/SD | 2023-05-10 | 2023-06-06 | Y | S070
2207203 | Design Development | SUBCON | 2023-06-07 | 2023-06-27 | Y | S070
2207203 | Tender | SUBCON | 2023-06-28 | 2023-07-31 | Y | S070
2207203 | Construction Administration | SUBCON | 2023-08-01 | 2024-07-31 | Y | S070
2207205 | Project Initiation | ID | 2023-05-10 | 2023-05-10 | N | S030
2207205 | Schematic Design | ID CONCEPT/SD | 2023-05-10 | 2023-06-30 | N | S030
2207205 | Design Development | ID | 2023-07-01 | 2023-07-31 | N | S030
2207205 | Contract Documentation | ID | 2023-08-01 | 2023-12-31 | N | S030
2207205 | Construction Administration | ID | 2024-01-01 | 2025-02-28 | N | S030
2207205 | Schematic Design | XXX | 2023-05-10 | 2023-05-10 | Y | \N
2207205 | Design Development | XXX | 2023-05-10 | 2023-05-10 | Y | \N
2207205 | Contract Documentation | XXX | 2023-05-10 | 2023-05-10 | Y | \N
2207205 | Construction Administration | XXX | 2023-05-10 | 2023-05-10 | Y | \N
23086 | Project Initiation | ID | 2023-10-01 | 2023-10-01 | N | S030
23086 | Schematic Design | ID: CONCEPT/SD | 2023-10-01 | 2023-10-15 | N | S030
23086 | Design Development | ID | 2023-10-16 | 2023-10-31 | N | S030
23086 | Contract Documentation | ID | 2023-11-01 | 2023-12-31 | N | S030
23086 | Construction Administration | ID | 2024-01-01 | 2025-02-28 | N | S030
23087 | Project Initiation | ID | 2023-10-26 | 2023-10-26 | N | S030
23087 | Schematic Design | ID | 2023-10-01 | 2023-10-15 | N | S030
23087 | Design Development | ID | 2023-10-16 | 2023-10-31 | N | S030
23087 | Contract Documentation | ID | 2023-11-01 | 2023-12-31 | N | S030
23087 | Construction Administration | ID | 2024-01-01 | 2025-02-28 | N | S030
23082 | Project Initiation | DOWNPAYMENT | 2023-05-29 | 2023-05-29 | Y | S060
23082 | BIM LOD 300 Architecture and Structural Modelling | \N | 2023-05-29 | 2023-07-31 | Y | S060
23082 | BIM LOD 300 MEPF Modelling | \N | 2023-08-01 | 2023-09-30 | Y | S060
23082 | Clash Detection and Resolution | \N | 2023-10-01 | 2023-11-30 | Y | S060
23082 | 2D Combined Services Drawings | \N | 2023-12-01 | 2023-12-31 | Y | S060
23044 | Final Renderings | FINAL RENDERING/ ANIMATION | 2023-05-29 | 2023-08-15 | N | S050
22056 | Project Initiation | BIM | 2023-11-01 | 2023-11-01 | Y | S060
22056 | BIM LOD 300 Architecture and Structural Modelling | BIM | 2023-12-01 | 2024-01-31 | Y | S060
22056 | BIM LOD 300 MEPF Modelling | BIM | 2024-02-01 | 2024-04-30 | Y | S060
22056 | Clash Detection and Resolution | BIM | 2024-05-01 | 2024-06-30 | Y | S060
22056 | 2D Combined Services Drawings | BIM | 2024-07-01 | 2024-08-31 | Y | S060
1507702 | Construction Administration | \N | 2023-06-01 | 2024-01-31 | N | S020
2201101 | Schematic Design | AR | 2023-05-01 | 2023-05-01 | Y | S020
2201101 | Design Development | AR | 2023-05-01 | 2023-05-01 | Y | S020
2201101 | Contract Documentation | AR | 2023-05-01 | 2023-05-01 | Y | S020
2201101 | Construction Administration | AR | 2023-05-01 | 2023-05-01 | Y | S020
23118 | Concept Design | ID | 2023-06-01 | 2023-06-01 | Y | S030
23118 | Contract Documentation | ID: BUILDING PERMIT | 2023-06-01 | 2023-06-01 | Y | S030
1722305 | Construction Administration | AR | 2023-06-01 | 2024-12-31 | N | S020
16039J16 | Construction Administration | AIDEA ID | 2023-04-01 | 2023-07-31 | N | S030
16039J16 | Construction Administration | SUBCON | 2023-04-01 | 2023-07-31 | N | S070
2106001 | Contract Documentation | AR | 2022-10-01 | 2023-05-31 | N | S020
1601702 | Construction Administration | AR | 2024-04-01 | 2024-05-31 | N | S020
1601903 | Construction Administration | AR | 2023-11-01 | 2024-05-31 | N | S020
23112 | Project Initiation | AR | 2023-06-10 | 2023-06-10 | N | S020
23112 | Contract Documentation | AR | 2023-06-11 | 2024-03-31 | N | S020
23112 | Construction Administration | AR | 2024-04-01 | 2024-07-31 | N | S020
23100 | Project Initiation | AR | 2023-07-01 | 2023-07-01 | N | S020
23100 | Concept Design | AR | 2023-07-24 | 2024-03-15 | N | S020
23100 | Schematic Design | AR | 2024-03-16 | 2024-05-15 | N | S020
23100 | Design Development | AR | 2024-05-16 | 2024-08-15 | N | S020
23100 | Contract Documentation | AR | 2024-08-16 | 2024-11-30 | N | S020
23100 | Construction Administration | AR | 2024-12-01 | 2026-05-31 | N | S020
23100 | Project Initiation | STRUCTURAL | 2023-07-01 | 2023-07-01 | N | S070
23100 | Schematic Design | STRUCTURAL | 2024-04-01 | 2024-05-15 | N | S070
23100 | Design Development | STRUCTURAL | 2024-05-16 | 2024-08-15 | N | S070
23100 | Contract Documentation | STRUCTURAL | 2024-08-16 | 2024-11-30 | N | S070
23100 | Construction Administration | STRUCTURAL | 2024-12-01 | 2026-05-31 | N | S070
23100 | Project Initiation | MECHANICAL | 2023-07-01 | 2023-07-01 | N | S070
23100 | Schematic Design | MECHANICAL | 2024-04-01 | 2024-05-15 | N | S070
23100 | Design Development | MECHANICAL | 2024-05-16 | 2024-08-15 | N | S070
23100 | Contract Documentation | MECHANICAL | 2024-08-16 | 2024-11-30 | N | S070
23100 | Construction Administration | MECHANICAL | 2024-12-01 | 2026-05-31 | N | S070
23100 | Project Initiation | ELECTRICAL | 2023-07-01 | 2023-07-01 | N | S070
23100 | Schematic Design | ELECTRICAL | 2024-04-01 | 2024-05-15 | N | S070
23100 | Design Development | ELECTRICAL | 2024-05-16 | 2024-08-15 | N | S070
23100 | Contract Documentation | ELECTRICAL | 2024-08-16 | 2024-11-30 | N | S070
23100 | Construction Administration | ELECTRICAL | 2024-12-01 | 2026-05-31 | N | S070
23100 | Project Initiation | PLUMBING & FIRE PROTECTION | 2023-07-01 | 2023-07-01 | N | S070
23100 | Schematic Design | PLUMBING & FIRE PROTECTION | 2024-04-01 | 2024-05-15 | N | S070
23100 | Design Development | PLUMBING & FIRE PROTECTION | 2024-05-16 | 2024-08-15 | N | S070
23100 | Contract Documentation | PLUMBING & FIRE PROTECTION | 2024-08-16 | 2024-11-30 | N | S070
23100 | Construction Administration | PLUMBING & FIRE PROTECTION | 2024-12-01 | 2026-05-31 | N | S070
23100 | Project Initiation | FIRE LIFE SAFETY | 2023-07-01 | 2023-07-01 | N | S070
23100 | Schematic Design | FIRE LIFE SAFETY | 2024-04-01 | 2024-05-15 | N | S070
23100 | Design Development | FIRE LIFE SAFETY | 2024-05-16 | 2024-08-15 | N | S070
23100 | Contract Documentation | FIRE LIFE SAFETY | 2024-08-16 | 2024-11-30 | N | S070
23100 | Project Initiation | WELL: ON HOLD | 2023-07-01 | 2023-07-01 | Y | S080
23100 | Concept Design | WELL: ON HOLD | 2023-07-24 | 2024-03-15 | Y | S080
23100 | Schematic Design | WELL: ON HOLD | 2024-03-16 | 2024-05-15 | Y | S080
23100 | Design Development | WELL: ON HOLD | 2024-05-16 | 2024-08-15 | Y | S080
23100 | Contract Documentation | WELL: ON HOLD | 2024-08-16 | 2024-11-30 | Y | S080
23100 | Construction Administration | WELL: ON HOLD | 2024-12-01 | 2026-05-31 | Y | S080
23100 | Project Initiation | LEED | 2023-07-01 | 2023-07-01 | N | S070
23100 | Schematic Design | LEED | 2024-04-01 | 2024-05-15 | N | S070
23100 | Design Development | LEED | 2024-05-16 | 2024-08-15 | N | S070
23100 | Contract Documentation | LEED | 2024-08-16 | 2024-11-30 | N | S070
23100 | Construction Administration | LEED | 2024-12-01 | 2026-05-31 | N | S070
23092 | Test-Fit | ID | 2023-07-01 | 2023-07-15 | N | S030
1711506 | Project Initiation | ID | 2023-07-04 | 2023-07-04 | N | S030
1711506 | Contract Documentation | ID: COMPLETION OF FF&E DOCUMENTATION SCOPE | 2023-07-04 | 2023-09-30 | N | S030
1711506 | Construction Administration | ID | 2023-11-01 | 2024-02-29 | N | S030
23052 | Project Initiation | AR | 2023-07-01 | 2023-07-01 | N | S020
23052 | Concept Design | AR | 2023-07-01 | 2024-06-30 | N | S020
23052 | Schematic Design | AR | 2024-07-01 | 2024-09-30 | N | S020
23052 | Design Development | AR | 2024-10-01 | 2025-01-31 | N | S020
23052 | Contract Documentation | AR | 2025-02-01 | 2025-07-31 | N | S020
23052 | Construction Administration | AR | 2025-08-01 | 2033-01-31 | N | S020
23052 | Project Initiation | ID | 2023-07-01 | 2023-07-01 | N | S030
23052 | Concept Design | ID | 2023-07-01 | 2024-06-30 | N | S030
23052 | Schematic Design | ID | 2024-07-01 | 2024-09-30 | N | S030
23052 | Design Development | ID | 2024-10-01 | 2025-01-31 | N | S030
23052 | Contract Documentation | ID | 2025-02-01 | 2025-07-31 | N | S030
23052 | Construction Administration | ID | 2025-08-01 | 2033-01-31 | N | S030
23122 | Project Initiation | AR | 2023-07-01 | 2023-07-01 | N | S020
23122 | Concept Design | AR | 2023-07-01 | 2023-10-16 | N | S020
23123 | Project Initiation | TOWER 1 | 2023-10-02 | 2023-10-02 | N | S020
23123 | Schematic Design | TOWER 1 | 2023-10-02 | 2024-02-29 | N | S020
23123 | Detailed Design | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Tender | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Construction Administration | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Project Initiation | TOWER 2 | 2023-10-02 | 2023-10-02 | N | S020
23123 | Schematic Design | TOWER 2 | 2023-10-02 | 2024-02-29 | N | S020
23123 | Detailed Design | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Tender | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Construction Administration | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Project Initiation | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Schematic Design | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Detailed Design | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Tender | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
23123 | Construction Administration | NOT USED | 2023-10-02 | 2023-10-02 | Y | S020
2213601 | Animation | RENDERING SERVICES | 2023-07-05 | 2023-08-31 | N | S050
22153 | Project Initiation | MP | 2023-07-01 | 2023-07-01 | N | S010
22153 | Data Collection and Analysis | MP | 2023-07-01 | 2023-08-31 | N | S010
22153 | Visioning and Options Generation | MP | 2023-09-01 | 2023-11-30 | N | S010
22153 | Final Masterplanning | CONCEPTUAL MP (INCLUDING VISUALLIZATION) | 2023-12-01 | 2024-02-29 | N | S010
22154 | Project Initiation | MOBILIZATION FOR ALL | 2023-08-07 | 2023-08-07 | N | S020
22154 | Planning and Programming | AR | 2023-07-27 | 2023-09-07 | N | S020
22154 | Concept Design | AR | 2023-07-27 | 2023-10-20 | N | S020
22154 | Schematic Design | AR | 2023-10-23 | 2024-04-16 | N | S020
22154 | Design Development | AR | 2024-04-19 | 2024-06-21 | N | S020
22154 | Contract Documentation | AR | 2024-06-22 | 2024-07-31 | N | S020
22154 | Contract Documentation | AR: PROCUREMENT PHASE | 2024-08-01 | 2024-10-31 | N | S020
22154 | Construction Administration | AR: PHASE 1 | 2024-11-01 | 2026-10-31 | N | S020
22154 | Design Development | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Contract Documentation | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Contract Documentation | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Construction Administration | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Design Development | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Contract Documentation | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Contract Documentation | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Construction Administration | NOT USED | 2023-08-07 | 2023-08-07 | Y | \N
22154 | Construction Administration | AR: PHASE 2 | 2026-11-01 | 2027-10-31 | N | S020
22154 | Preliminary Design | ID | 2024-04-19 | 2024-06-21 | N | S030
22154 | Detailed Design | ID | 2024-06-24 | 2024-08-02 | N | S030
22154 | Contract Documentation | ID: PROCUREMENT PHASE | 2024-08-03 | 2024-10-31 | N | S030
22154 | Construction Administration | ID | 2024-11-01 | 2025-10-31 | N | S030
22154 | Preliminary Design | EGD | 2024-04-19 | 2024-06-21 | N | S040
22154 | Detailed Design | EGD | 2024-06-24 | 2024-08-02 | N | S040
22154 | Construction Administration | EGD | 2024-09-01 | 2025-08-31 | N | S040
22154 | Schematic Design | ACOUSTICS | 2023-10-23 | 2024-04-16 | N | S070
22154 | Design Development | ACOUSTICS | 2024-04-19 | 2024-06-21 | N | S070
22154 | Contract Documentation | ACOUSTICS | 2024-06-22 | 2024-10-31 | N | S070
22154 | Construction Administration | ACOUSTICS | 2024-11-01 | 2027-10-31 | N | S070
22154 | Schematic Design | LANDSCAPE & AUTOMATIC IRRIGATION | 2023-10-23 | 2024-04-16 | N | S070
22154 | Design Development | LANDSCAPE & AUTOMATIC IRRIGATION | 2024-04-19 | 2024-06-21 | N | S070
22154 | Contract Documentation | LANDSCAPE & AUTOMATIC IRRIGATION | 2024-06-22 | 2024-07-31 | N | S070
22154 | Contract Documentation | LANDSCAPE & AUTOMATIC IRRIGATION: PROCUREMENT PHASE | 2024-08-01 | 2024-10-31 | N | S070
22154 | Construction Administration | LANDSCAPE & AUTOMATIC IRRIGATION | 2024-11-01 | 2025-10-31 | N | S070
22154 | Schematic Design | KITCHEN | 2023-10-23 | 2024-04-16 | N | S070
22154 | Design Development | KITCHEN | 2024-04-19 | 2024-06-21 | N | S070
22154 | Contract Documentation | KITCHEN | 2024-06-22 | 2024-10-31 | N | S070
22154 | Construction Administration | KITCHEN | 2024-11-01 | 2026-10-31 | N | S070
22154 | Design Development | MEDICAL EQUIPMENT PLANNING | 2024-04-19 | 2024-06-21 | N | S070
22154 | Contract Documentation | MEDICAL EQUIPMENT PLANNING | 2024-06-22 | 2024-10-31 | N | S070
23018 | Project Initiation | AR | 2023-07-06 | 2023-07-06 | N | S020
23018 | Schematic Design | AR: CONCEPT/SD | 2023-07-06 | 2024-03-31 | N | S020
23018 | Design Development | AR | 2024-04-01 | 2024-05-31 | N | S020
23018 | Contract Documentation | AR | 2024-06-01 | 2024-07-31 | N | S020
23018 | Tender | AR: BIDDING, EVALUATION & NEGOTIATION PHASE | 2024-09-01 | 2024-10-31 | N | S020
23018 | Construction Administration | AR | 2024-11-01 | 2026-04-30 | N | S020
23097 | Project Initiation | AR | 2023-07-06 | 2023-07-06 | N | S020
23097 | Schematic Design | AR: CONCEPT/SD | 2023-07-06 | 2024-03-15 | N | S020
23097 | Design Development | AR | 2024-03-11 | 2024-06-15 | N | S020
23097 | Contract Documentation | AR | 2024-06-16 | 2024-09-15 | N | S020
23097 | Construction Administration | AR | 2024-09-16 | 2028-09-15 | N | S020
23097 | Project Initiation | STRUCTURAL | 2023-07-06 | 2023-07-06 | N | S070
23097 | Schematic Design | STRUCTURAL: CONCEPT/SD | 2023-07-06 | 2024-03-15 | N | S070
23097 | Design Development | STRUCTURAL | 2024-03-11 | 2024-06-15 | N | S070
23097 | Contract Documentation | STRUCTURAL | 2024-06-16 | 2024-09-15 | N | S070
23097 | Construction Administration | STRUCTURAL | 2024-09-16 | 2028-09-15 | N | S070
23097 | Project Initiation | MEPF | 2023-07-06 | 2023-07-06 | N | S070
23097 | Schematic Design | MEPF: CONCEPT/SD | 2023-07-06 | 2024-09-15 | N | S070
23097 | Design Development | MEPF | 2024-03-11 | 2024-06-15 | N | S070
23097 | Contract Documentation | MEPF | 2024-06-16 | 2024-09-15 | N | S070
23097 | Construction Administration | MEPF | 2024-09-16 | 2028-09-15 | N | S070
23097 | Project Initiation | FIRE LIFE AND SAFETY | 2023-07-06 | 2023-07-06 | N | S070
23097 | Schematic Design | FIRE LIFE AND SAFETY: CONCEPT/SD | 2023-07-06 | 2024-03-15 | N | S070
23097 | Design Development | FIRE LIFE AND SAFETY | 2024-03-11 | 2024-06-15 | N | S070
23097 | Contract Documentation | FIRE LIFE AND SAFETY | 2024-06-16 | 2024-09-15 | N | S070
23097 | Construction Administration | FIRE LIFE AND SAFETY | 2024-09-16 | 2028-09-15 | N | S070
23097 | Project Initiation | LEED CONSULTANCY | 2023-07-06 | 2023-07-06 | N | S070
23097 | Schematic Design | LEED CONSULTANCY: CONCEPT/SD | 2023-07-06 | 2024-03-15 | N | S070
23097 | Design Development | LEED CONSULTANCY | 2024-03-11 | 2024-06-15 | N | S070
23097 | Contract Documentation | LEED CONSULTANCY | 2024-06-16 | 2024-09-15 | N | S070
23097 | Construction Administration | LEED CONSULTANCY | 2024-09-16 | 2028-09-15 | N | S070
23097 | Project Initiation | WELL CONSULTANCY | 2023-07-06 | 2023-07-06 | N | S070
23097 | Schematic Design | WELL CONSULTANCY: CONCEPT/SD | 2023-07-06 | 2024-03-15 | N | S070
23097 | Design Development | WELL CONSULTANCY | 2024-03-11 | 2024-06-15 | N | S070
23097 | Contract Documentation | WELL CONSULTANCY | 2024-06-16 | 2024-09-15 | N | S070
23097 | Construction Administration | WELL CONSULTANCY | 2024-09-16 | 2028-09-15 | N | S070
23097 | Project Initiation | BIM LOD 300 | 2023-07-06 | 2023-07-06 | N | S060
23097 | Design Development | BIM LOD 300 | 2024-03-11 | 2024-06-15 | N | S060
23097 | Contract Documentation | BIM LOD 300 | 2024-06-16 | 2024-09-15 | N | S060
2110703 | Project Initiation | MF | 2023-06-01 | 2023-06-01 | N | S020
2110703 | Contract Documentation | MF | 2023-08-01 | 2024-05-31 | N | S020
2110703 | Construction Administration | MF | 2024-06-01 | 2030-05-31 | N | S020
2110703 | Post Construction Phase | MF | 2030-06-01 | 2030-06-30 | N | S020
2110703 | Project Initiation | SUBCON | 2023-06-01 | 2023-06-01 | N | S070
2110703 | Contract Documentation | SUBCON | 2023-08-01 | 2024-05-31 | N | S070
2110703 | Construction Administration | SUBCON | 2024-06-01 | 2030-05-31 | N | S070
2110703 | Post Construction Phase | SUBCON | 2030-06-01 | 2030-06-30 | N | S070
23129 | Concept Design | \N | 2023-07-10 | 2023-10-20 | Y | \N
1815101 | Schematic Design | AR: RE-DESIGN | 2023-07-24 | 2024-04-30 | N | S020
23128 | Project Initiation | ID | 2024-01-01 | 2024-01-01 | Y | \N
23128 | Concept Design | NOT USED | 2024-01-01 | 2024-01-01 | Y | \N
23128 | Schematic Design | NOT USED | 2024-01-01 | 2024-01-01 | Y | \N
23128 | Design Development | ID | 2024-01-01 | 2024-01-01 | Y | \N
23128 | Contract Documentation | ID | 2024-01-01 | 2024-01-01 | Y | \N
23128 | Construction Administration | ID | 2024-01-01 | 2024-01-01 | Y | \N
23163 | Concept Design | ID | 2023-07-24 | 2023-12-31 | Y | \N
23163 | Contract Documentation | ID: BUILDING PERMIT | 2023-07-24 | 2023-07-24 | Y | \N
23101 | Project Initiation | ID | 2023-07-17 | 2023-07-17 | N | S030
23101 | Concept Design | ID | 2023-07-17 | 2023-08-31 | N | S030
23101 | Schematic Design | ID | 2023-09-01 | 2023-11-30 | N | S030
23101 | Design Development | ID | 2024-01-31 | 2024-04-15 | N | S030
23101 | Contract Documentation | ID | 2024-04-16 | 2024-06-11 | N | S030
23101 | Construction Administration | ID | 2024-07-01 | 2028-06-30 | N | S030
23140 | Code Review | AIDEA | 2023-08-08 | 2023-09-22 | N | S020
23140 | Code Review | SUBCON | 2023-08-08 | 2023-09-22 | N | S070
23035 | Project Initiation | AR | 2023-08-10 | 2023-08-10 | N | S020
23035 | Preliminary Design | AR | 2023-09-01 | 2024-06-30 | N | S020
23035 | Detailed Design | AR | 2024-07-01 | 2024-10-31 | N | S020
23035 | Construction Administration | AR | 2024-11-01 | 2027-10-31 | N | S020
23145 | Project Initiation | \N | 2023-08-10 | 2023-08-10 | N | S050
23145 | Preliminary Renderings | \N | 2023-08-11 | 2023-12-31 | N | S050
23145 | Final Renderings | \N | 2024-01-01 | 2024-03-31 | N | S050
23138 | Project Initiation | ID | 2023-08-10 | 2023-08-10 | N | S030
23138 | Concept Design | ID | 2023-08-10 | 2024-04-30 | N | S030
23138 | Schematic Design | ID | 2024-05-01 | 2024-06-30 | N | S030
23138 | Design Development | ID | 2024-07-01 | 2024-07-31 | N | S030
23138 | Contract Documentation | ID | 2024-08-01 | 2024-09-30 | N | S030
23138 | Construction Administration | ID | 2024-10-01 | 2027-09-30 | N | S030
23108 | Project Initiation | \N | 2023-08-10 | 2023-08-10 | N | S050
23108 | Preliminary Renderings | \N | 2023-08-10 | 2023-09-30 | N | S050
23108 | Final Renderings | \N | 2023-10-01 | 2024-04-30 | N | S050
23136 | Project Initiation | ID | 2023-08-10 | 2023-08-10 | N | S030
23136 | Concept Design | ID | 2023-09-15 | 2024-04-30 | N | S030
23136 | Schematic Design | ID | 2024-05-01 | 2024-06-30 | N | S030
23136 | Design Development | ID | 2024-07-01 | 2024-08-31 | N | S030
23136 | Contract Documentation | ID | 2024-09-01 | 2024-10-31 | N | S030
23136 | Construction Administration | ID | 2025-11-01 | 2028-10-31 | N | S030
23144 | Project Initiation | \N | 2023-08-10 | 2023-08-10 | N | S050
23144 | Preliminary Renderings | \N | 2023-10-01 | 2024-03-31 | N | S050
23144 | Final Renderings | \N | 2024-04-01 | 2024-07-31 | N | S050
23146 | Project Initiation | \N | 2023-08-10 | 2023-08-10 | N | S050
23146 | Preliminary Renderings | \N | 2023-10-01 | 2024-04-30 | N | S050
23146 | Final Renderings | \N | 2024-05-01 | 2024-05-31 | N | S050
23147 | Project Initiation | \N | 2023-08-10 | 2023-08-10 | N | S050
23147 | Preliminary Renderings | \N | 2023-10-01 | 2024-03-31 | N | S050
23147 | Final Renderings | \N | 2024-04-01 | 2024-07-31 | N | S050
23134 | Project Initiation | ID | 2023-08-10 | 2023-08-10 | N | S030
23134 | Concept Design | ID | 2023-08-10 | 2024-03-31 | N | S030
23134 | Schematic Design | ID | 2024-04-01 | 2024-04-30 | N | S030
23134 | Design Development | ID | 2024-05-01 | 2024-06-30 | N | S030
23134 | Contract Documentation | ID | 2024-07-01 | 2024-08-31 | N | S030
23134 | Construction Administration | ID | 2024-09-01 | 2027-08-31 | N | S030
23137 | Project Initiation | ID | 2023-08-10 | 2023-08-10 | N | S030
23137 | Concept Design | ON HOLD: ID | 2024-01-03 | 2024-04-30 | Y | S030
23137 | Schematic Design | ON HOLD: ID | 2024-05-01 | 2024-06-30 | Y | S030
23137 | Design Development | ON HOLD: ID | 2024-07-01 | 2024-09-30 | Y | S030
23137 | Contract Documentation | ON HOLD: ID | 2024-10-01 | 2024-12-31 | Y | S030
23137 | Construction Administration | ON HOLD: ID | 2025-01-01 | 2028-12-31 | Y | S030
23135 | Project Initiation | ID | 2023-08-10 | 2023-08-10 | N | S030
23135 | Concept Design | ON HOLD: ID | 2023-08-10 | 2024-03-31 | Y | S030
23135 | Schematic Design | ON HOLD: ID | 2024-04-01 | 2024-05-31 | Y | S030
23135 | Design Development | ON HOLD: ID | 2024-06-01 | 2024-07-31 | Y | S030
23135 | Contract Documentation | ON HOLD: ID | 2024-08-01 | 2024-09-30 | Y | S030
23135 | Construction Administration | ON HOLD: ID | 2024-10-01 | 2027-09-30 | Y | S030
2108701 | Design Development | AR | 2023-08-16 | 2023-10-31 | N | S020
2208101 | Schematic Design | MP | 2023-07-27 | 2023-09-15 | N | S020
23061 | Project Initiation | AR | 2023-08-10 | 2023-08-10 | N | S020
23061 | Preliminary Design | AR | 2023-08-10 | 2024-04-30 | N | S020
23061 | Design Development | AR | 2024-05-01 | 2024-08-31 | N | S020
23061 | Contract Documentation | AR | 2024-09-01 | 2025-02-28 | N | S020
23061 | Construction Administration | AR | 2025-03-01 | 2027-02-28 | N | S020
23105 | Project Initiation | MP | 2023-08-21 | 2023-08-21 | Y | S010
23105 | Data Collection and Analysis | MP | 2023-08-21 | 2023-08-21 | Y | S010
23105 | Visioning and Options Generation | MP | 2023-08-21 | 2023-08-21 | Y | S010
23105 | Conceptual Masterplanning | MP | 2023-08-21 | 2023-08-21 | Y | S010
23105 | Detailed Masterplanning | MP | 2023-08-21 | 2023-08-21 | Y | S010
23161 | Project Initiation | AIDEA & SUBCON | 2023-08-01 | 2023-08-01 | N | S050
23161 | Final Renderings | AIDEA & SUBCON | 2023-08-01 | 2023-08-31 | N | S050
2204402 | Project Initiation | AR | 2023-08-31 | 2023-08-31 | N | S020
2204402 | Marketing Collaterals | ON HOLD: AR: Individual Lot Plans | 2023-09-01 | 2023-12-15 | Y | S020
23184 | Concept Design | AR | 2023-08-29 | 2023-09-30 | Y | \N
2109601 | Project Initiation | AR | 2023-09-05 | 2023-09-05 | N | S020
2109601 | Contract Documentation | AR | 2023-09-05 | 2023-10-22 | N | S020
23026 | Project Initiation | ID | 2023-09-08 | 2023-09-08 | N | S030
23026 | Preliminary Design | ID | 2023-09-08 | 2024-04-30 | N | S030
23154 | Project Initiation | ID | 2024-01-25 | 2024-01-25 | N | S030
23154 | Preliminary Design | ID | 2024-01-25 | 2024-04-30 | N | S030
1506818 | Construction Administration | AR | 2023-10-01 | 2024-02-29 | N | S020
1506819 | Construction Administration | AR | 2023-10-01 | 2024-02-29 | N | S020
16039J18 | Construction Administration | ID | 2023-08-01 | 2024-03-31 | N | S030
16039J18 | Construction Administration | SUBCON | 2023-08-01 | 2024-03-31 | N | S070
16039J19 | Construction Administration | AR | 2023-08-01 | 2024-03-31 | N | S020
16039J19 | Construction Administration | STRUCTURAL ENGINEERING | 2023-08-01 | 2024-03-31 | N | S070
16039J19 | Construction Administration | MECHANICAL ENGINEERING | 2023-08-01 | 2024-03-31 | N | S070
16039J19 | Construction Administration | ELECTRICAL ENGINEERING | 2023-08-01 | 2024-03-31 | N | S070
16039J19 | Construction Administration | PLUMB., SANIT. & FIRE PROTECT. | 2023-08-01 | 2024-03-31 | N | S070
23170 | Project Initiation | ID | 2023-09-14 | 2023-09-14 | N | S030
23170 | Concept Design | ID | 2023-09-14 | 2023-09-30 | N | S030
23170 | Schematic Design | ID | 2023-09-25 | 2023-10-06 | N | S030
23170 | Detailed Design | ID | 2023-10-09 | 2024-03-15 | N | S030
23170 | Construction Administration | ID | 2024-04-01 | 2024-07-31 | N | S030
23190 | Contract Documentation | TAX DECLARATION REQUIREMENTS | 2023-09-15 | 2024-01-31 | N | S020
1507501 | Schematic Design | AR | 2020-08-31 | 2020-08-31 | N | S020
1507502 | Schematic Design | AR | 2020-08-31 | 2020-08-31 | N | S020
1507503 | Schematic Design | AR | 2020-08-31 | 2020-08-31 | N | S020
1507505 | Design Development | AR | 2020-08-31 | 2020-08-31 | N | S020
23109 | Others | DUE DILIGENCE: PRELIMINARY REPORT | 2023-09-25 | 2023-12-03 | N | S080
23109 | Others | DUE DILIGENCE: FINAL REPORT | 2023-12-04 | 2024-01-03 | N | S080
23157 | Project Initiation | MF | 2023-10-03 | 2023-10-03 | N | S020
23157 | Schematic Design | MF | 2023-10-03 | 2024-02-29 | N | S020
23157 | Design Development | MF: FOR PERMIT | 2024-03-01 | 2024-03-31 | N | S020
23157 | Design Development | MF: FOR REVIEW | 2024-03-01 | 2024-03-31 | N | S020
23157 | Contract Documentation | MF: FOR TENDER | 2024-04-01 | 2024-04-30 | N | S020
23157 | Contract Documentation | MF: FOR CONSTRUCTION | 2024-04-01 | 2024-04-30 | N | S020
23157 | Construction Administration | MF: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2024-06-01 | 2028-05-31 | N | S020
23157 | Project Initiation | LANDSCAPE | 2023-10-03 | 2023-10-03 | N | S070
23157 | Schematic Design | LANDSCAPE | 2023-10-03 | 2024-02-29 | N | S070
23157 | Design Development | LANDSCAPE: FOR PERMIT | 2024-03-01 | 2024-03-31 | N | S070
23157 | Design Development | LANDSCAPE: FOR REVIEW | 2024-03-01 | 2024-03-31 | N | S070
23157 | Contract Documentation | LANDSCAPE: FOR TENDER | 2024-04-01 | 2024-04-30 | N | S070
23157 | Contract Documentation | LANDSCAPE: FOR CONSTRUCTION | 2024-04-01 | 2024-04-30 | N | S070
23157 | Construction Administration | LANDSCAPE: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2024-06-01 | 2028-05-31 | N | S070
23158 | Project Initiation | MF | 2023-10-03 | 2023-10-03 | N | S020
23158 | Schematic Design | ON HOLD: MF | 2023-10-03 | 2024-03-31 | Y | S020
23158 | Design Development | ON HOLD - MF: FOR PERMIT | 2024-04-01 | 2024-04-30 | Y | S020
23158 | Design Development | ON HOLD - MF: FOR REVIEW | 2024-05-01 | 2024-05-31 | Y | S020
23158 | Contract Documentation | ON HOLD - MF: FOR TENDER | 2024-06-01 | 2024-06-30 | Y | S020
23158 | Contract Documentation | ON HOLD - MF: FOR CONSTRUCTION | 2024-07-01 | 2024-07-31 | Y | S020
23158 | Construction Administration | ON HOLD - MF: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2024-08-01 | 2028-07-31 | Y | S020
23158 | Project Initiation | LANDSCAPE | 2023-10-03 | 2023-10-03 | N | S070
23158 | Schematic Design | ON HOLD - LANDSCAPE | 2023-10-03 | 2024-03-31 | Y | S070
23158 | Design Development | ON HOLD - LANDSCAPE: FOR PERMIT | 2024-04-01 | 2024-04-30 | Y | S070
23158 | Design Development | ON HOLD - LANDSCAPE: FOR REVIEW | 2024-05-01 | 2024-05-31 | Y | S070
23158 | Contract Documentation | ON HOLD - LANDSCAPE: FOR TENDER | 2024-06-01 | 2024-06-30 | Y | S070
23158 | Contract Documentation | ON HOLD - LANDSCAPE: FOR CONSTRUCTION | 2024-07-01 | 2024-07-31 | Y | S070
23158 | Construction Administration | ON HOLD - LANDSCAPE: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2024-08-01 | 2028-07-31 | Y | S070
23080 | Project Initiation | \N | 2023-10-04 | 2023-10-04 | N | S060
23080 | BIM Attendance | ON HOLD: BIM MANAGEMENT | 2023-10-04 | 2024-05-03 | Y | S060
23083 | Design Development | \N | 2024-04-14 | 2024-06-13 | N | S060
23083 | 2D Combined Services Drawings | UPON SUBMISSION OF 2D & 3D | 2024-03-14 | 2024-04-30 | N | S060
23083 | Contract Documentation | BID PLANS | 2024-05-01 | 2024-06-30 | N | S060
23083 | Contract Documentation | CONSTRUCTION PLANS | 2024-07-01 | 2024-08-31 | N | S060
23159 | Project Initiation | MF | 2023-10-03 | 2023-10-03 | N | S020
23159 | Schematic Design | MF | 2023-10-03 | 2024-04-30 | N | S020
23159 | Design Development | MF: FOR PERMIT | 2024-05-01 | 2024-05-31 | N | S020
23159 | Design Development | MF: FOR REVIEW | 2024-06-01 | 2024-06-30 | N | S020
23159 | Contract Documentation | MF: FOR TENDER | 2024-07-01 | 2024-07-31 | N | S020
23159 | Contract Documentation | MF: FOR CONSTRUCTION | 2024-08-01 | 2024-08-31 | N | S020
23159 | Construction Administration | MF: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2027-06-01 | 2031-05-31 | N | S020
23159 | Project Initiation | LANDSCAPE | 2023-10-03 | 2023-10-03 | N | S070
23159 | Schematic Design | LANDSCAPE | 2023-10-03 | 2024-04-30 | N | S070
23159 | Design Development | LANDSCAPE: FOR PERMIT | 2024-05-01 | 2024-05-31 | N | S070
23159 | Design Development | LANDSCAPE: FOR REVIEW | 2024-06-01 | 2024-06-30 | N | S070
23159 | Contract Documentation | LANDSCAPE: FOR TENDER | 2024-07-01 | 2024-07-31 | N | S070
23159 | Contract Documentation | LANDSCAPE: FOR CONSTRUCTION | 2024-08-01 | 2024-08-31 | N | S070
23159 | Construction Administration | LANDSCAPE: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2027-06-01 | 2031-05-31 | N | S070
23160 | Project Initiation | MF | 2023-10-03 | 2023-10-03 | N | S020
23160 | Schematic Design | MF | 2023-10-03 | 2024-03-31 | N | S020
23160 | Design Development | MF: FOR PERMIT | 2024-04-01 | 2024-04-30 | N | S020
23160 | Design Development | MF: FOR REVIEW | 2024-05-01 | 2024-05-31 | N | S020
23160 | Contract Documentation | MF: FOR TENDER | 2024-06-01 | 2024-06-30 | N | S020
23160 | Contract Documentation | MF: FOR CONSTRUCTION | 2024-07-01 | 2024-07-31 | N | S020
23160 | Construction Administration | MF: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2024-08-01 | 2028-07-31 | N | S020
23160 | Project Initiation | LANDSCAPE | 2023-10-03 | 2023-10-03 | N | S070
23160 | Schematic Design | LANDSCAPE | 2023-10-03 | 2024-03-31 | N | S070
23160 | Design Development | LANDSCAPE: FOR PERMIT | 2024-04-01 | 2024-04-30 | N | S070
23160 | Design Development | LANDSCAPE: FOR REVIEW | 2024-05-01 | 2024-05-31 | N | S070
23160 | Contract Documentation | LANDSCAPE: FOR TENDER | 2024-06-01 | 2024-06-30 | N | S070
23160 | Contract Documentation | LANDSCAPE: FOR CONSTRUCTION | 2024-07-01 | 2024-07-31 | N | S070
23160 | Construction Administration | LANDSCAPE: CA NO. OF MONTHS FOR DISCUSSION TO PM | 2024-08-01 | 2028-07-31 | N | S070
23211 | Test-Fit | \N | 2023-09-11 | 2023-09-11 | Y | S010
1818203 | Project Initiation | AR | 2023-10-09 | 2023-10-09 | N | S020
1818203 | Detailed Design | AR | 2023-10-09 | 2024-05-31 | N | S020
23192 | Project Initiation | AR | 2023-10-10 | 2023-10-10 | N | S020
23192 | Preliminary Design | AR | 2023-10-23 | 2024-04-19 | N | S020
23192 | Contract Documentation | AR | 2024-02-01 | 2024-05-06 | N | S020
23192 | Construction Administration | AR | 2024-06-01 | 2024-09-30 | N | S020
23192 | Project Initiation | ID | 2023-10-10 | 2023-10-10 | N | S030
23192 | Preliminary Design | ID | 2023-10-23 | 2024-04-19 | N | S030
23192 | Contract Documentation | ID | 2024-03-16 | 2024-06-03 | N | S030
23192 | Construction Administration | ID | 2024-07-01 | 2025-02-28 | N | S030
23180 | Project Initiation | ID | 2023-10-12 | 2023-10-12 | N | S030
23180 | Preliminary Design | ON HOLD: ID | 2023-10-12 | 2023-12-12 | Y | S030
23180 | Detailed Design | ON HOLD: ID | 2023-12-13 | 2024-02-29 | Y | S030
23180 | Construction Administration | ON HOLD: ID | 2024-03-01 | 2024-08-31 | Y | S030
23188 | Project Initiation | ID | 2023-10-09 | 2023-10-09 | N | S030
23188 | Preliminary Design | ID | 2023-10-09 | 2024-03-15 | N | S030
23188 | Detailed Design | ID | 2024-03-16 | 2024-04-30 | N | S030
23188 | Construction Administration | ID | 2024-05-01 | 2024-10-31 | N | S030
23194 | Project Initiation | \N | 2023-10-20 | 2023-10-20 | N | S050
23194 | Final Renderings | \N | 2023-10-20 | 2023-11-20 | N | S050
1926105 | For Construction Drawings | AR | 2023-10-20 | 2023-11-30 | N | S020
23142 | Project Initiation | \N | 2023-10-26 | 2023-10-26 | Y | S030
23142 | Interior Design Test-Fit | UPON SUBMISSION OF DRAFT LAYOUT/REPORT | 2023-10-26 | 2023-10-26 | Y | S030
23142 | Interior Design Test-Fit | UPON SUBMISSION OF FINAL LAYOUT/REPORT | 2023-10-26 | 2023-10-26 | Y | S030
23142 | Interior Design Test-Fit | UPON CLOSING SIGN-OFF | 2023-10-26 | 2023-10-26 | Y | S030
1902305 | Construction Administration | AR | 2023-10-01 | 2024-09-30 | N | S020
1607312 | Construction Administration | AR | 2023-11-01 | 2025-03-31 | N | S020
23116 | Project Initiation | \N | 2023-11-06 | 2023-11-06 | N | S080
23116 | Planning and Programming | UPON COMPLETION OF PRE-WORK AND DIRECTION SETTING STAGE | 2023-11-06 | 2023-12-01 | N | S080
23116 | Preliminary Design | UPON COMPLETION OF PRELIMINARY DESIGN STANDARDS AND GUIDELINES STAGE | 2023-12-02 | 2024-01-31 | N | S080
23116 | Detailed Design | UPON COMPLETION OF FINAL DESIGN STANDARDS AND GUIDELINES STAGE | 2024-02-01 | 2024-04-30 | N | S080
1908005 | Contract Documentation | AR | 2023-11-08 | 2023-11-08 | Y | S020
1908006 | Contract Documentation | AR | 2023-11-08 | 2023-11-08 | Y | S020
1908007 | Contract Documentation | AR | 2023-11-08 | 2023-11-08 | Y | S020
1922702 | Construction Administration | \N | 2023-11-01 | 2025-10-31 | N | S020
1907702 | Contract Documentation | AR | 2023-10-02 | 2023-12-31 | N | S020
2212802 | Project Initiation | ID | 2023-11-04 | 2023-11-04 | N | S030
2212802 | Preliminary Design | ID | 2023-11-04 | 2023-11-30 | N | S030
2212802 | Detailed Design | ID | 2023-12-01 | 2023-12-31 | N | S030
2212802 | Construction Administration | ID | 2024-03-01 | 2024-05-31 | N | S030
2212802 | Project Initiation | LIGHTING DESIGN | 2023-11-04 | 2023-11-04 | N | S070
2212802 | Preliminary Design | LIGHTING DESIGN | 2023-11-04 | 2023-11-30 | N | S070
2212802 | Detailed Design | LIGHTING DESIGN | 2023-12-01 | 2023-12-31 | N | S070
2212802 | Construction Administration | LIGHTING DESIGN | 2024-03-01 | 2024-05-31 | N | S070
2212802 | Project Initiation | MEPF DESIGN | 2023-11-04 | 2023-11-04 | N | S070
2212802 | Preliminary Design | MEPF DESIGN | 2023-11-04 | 2023-11-30 | N | S070
2212802 | Detailed Design | MEPF DESIGN | 2023-12-01 | 2023-12-31 | N | S070
2212802 | Construction Administration | MEPF DESIGN | 2024-03-01 | 2024-05-31 | N | S070
23214 | Design Development | ID | 2023-11-13 | 2023-12-02 | N | S030
23214 | Contract Documentation | ID | 2023-12-03 | 2024-01-31 | N | S030
23214 | Construction Administration | ID | 2024-02-01 | 2024-04-30 | N | S030
23214 | Design Development | MEPF FIT-OUT | 2023-11-13 | 2023-12-02 | N | S070
23214 | Contract Documentation | MEPF FIT-OUT | 2023-12-03 | 2024-01-31 | N | S070
23214 | Construction Administration | MEPF FIT-OUT | 2024-01-01 | 2024-03-31 | N | S070
23214 | Design Development | IT / ROUGHING INS | 2023-11-13 | 2023-12-02 | N | S070
23214 | Contract Documentation | IT / ROUGHING INS | 2023-12-03 | 2024-01-31 | N | S070
23214 | Construction Administration | IT / ROUGHING INS | 2024-02-01 | 2024-04-30 | N | S070
2012602 | Schematic Design | ID | 2021-01-01 | 2021-01-01 | N | S030
2012603 | Schematic Design | ID | 2021-01-01 | 2021-01-01 | N | S030
2012604 | Schematic Design | ID | 2021-01-01 | 2021-01-01 | N | S030
2012605 | Schematic Design | ID | 2021-01-01 | 2021-01-01 | N | S030
2216302 | Project Initiation | \N | 2023-11-16 | 2023-11-16 | N | S050
2216302 | Final Renderings | \N | 2023-11-16 | 2023-12-18 | N | S050
23186 | Project Initiation | \N | 2023-11-17 | 2023-11-17 | N | S010
23186 | Conceptual Masterplanning | PRELIMINARY CONCEPTUAL MP | 2023-11-17 | 2024-03-31 | Y | S010
23186 | Conceptual Masterplanning | FINAL CONCEPTUAL MP | 2024-04-01 | 2024-05-31 | Y | S010
23203 | Project Initiation | \N | 2024-02-01 | 2024-02-01 | N | \N
23203 | Detailed Design | \N | 2024-02-01 | 2024-06-30 | N | \N
23203 | Tender | BIDDING, EVALUATION, AND NEGOTIATION PHASE | 2024-07-01 | 2024-07-31 | N | \N
23203 | Construction Administration | \N | 2024-08-01 | 2027-10-31 | N | \N
23195 | Project Initiation | AR | 2024-01-04 | 2024-01-04 | N | S020
23195 | Preliminary Design | AR | 2024-01-04 | 2024-05-31 | N | S020
23195 | Design Development | AR | 2024-06-01 | 2024-06-30 | N | S020
23195 | Contract Documentation | AR | 2024-07-01 | 2024-08-31 | N | S020
23195 | Construction Administration | AR | 2024-09-01 | 2025-08-31 | N | S020
23195 | Project Initiation | CIVIL WORKS | 2024-01-04 | 2024-01-04 | N | S070
23195 | Preliminary Design | CIVIL WORKS | 2024-01-04 | 2024-05-31 | N | S070
23195 | Design Development | CIVIL WORKS | 2024-06-01 | 2024-06-30 | N | S070
23195 | Contract Documentation | CIVIL WORKS | 2024-07-01 | 2024-08-31 | N | S070
23195 | Construction Administration | CIVIL WORKS | 2024-09-01 | 2025-08-31 | N | S070
23195 | Project Initiation | MEPF ENGINEERING | 2024-01-04 | 2024-01-04 | N | S070
23195 | Preliminary Design | MEPF ENGINEERING | 2024-01-04 | 2024-05-31 | N | S070
23195 | Design Development | MEPF ENGINEERING | 2024-06-01 | 2024-06-30 | N | S070
23195 | Contract Documentation | MEPF ENGINEERING | 2024-07-01 | 2024-08-31 | N | S070
23195 | Construction Administration | MEPF ENGINEERING | 2024-09-01 | 2025-08-31 | N | S070
23195 | Project Initiation | STRUCTURAL ENGINEERING | 2024-01-04 | 2024-01-04 | N | S070
23195 | Preliminary Design | STRUCTURAL ENGINEERING | 2024-01-04 | 2024-05-31 | N | S070
23195 | Design Development | STRUCTURAL ENGINEERING | 2024-06-01 | 2024-06-30 | N | S070
23195 | Contract Documentation | STRUCTURAL ENGINEERING | 2024-07-01 | 2024-08-31 | N | S070
23195 | Construction Administration | STRUCTURAL ENGINEERING | 2024-09-01 | 2025-08-31 | N | S070
2206001 | Contract Documentation | AR | 2023-11-01 | 2023-12-31 | N | S020
1817231 | Detailed Architecture and Engineering Design | AR - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S020
1817231 | Project Initiation | AR - MOBILIZATION | 2023-08-30 | 2023-08-30 | N | S020
1817231 | Detailed Architecture and Engineering Design | STRUCTURAL - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | ID AIDEA - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S030
1817231 | Detailed Architecture and Engineering Design | MEPF - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | LANDSCAPE - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | ACOUSTIC- SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | BIM LOD 300 - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S060
1817231 | Detailed Architecture and Engineering Design | FACADE LIGHTING DESIGN - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | KITCHEN - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | TELECOM - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | SECURITY - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | ID BY7X - SUBMISSION AND APPROVAL | 2023-09-01 | \N | N | S070
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Detailed Architecture and Engineering Design | NOT USED | 2023-09-01 | 2023-09-01 | Y | \N
1817231 | Project Initiation | STRUCTURAL | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | MEPF | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | LANDSCAPE | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | ACOUSTIC | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | KITCHEN | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | TELECOM | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | SECURITY | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | ID AIDEA | 2023-08-30 | 2023-08-30 | N | S030
1817231 | Project Initiation | ID BY7X | 2023-08-30 | 2023-08-30 | N | S070
1817231 | Project Initiation | BIM LOD 300 | 2023-08-30 | 2023-08-30 | N | S060
1817231 | Project Initiation | FACADE LIGHTING DESIGN | 2023-08-30 | 2023-08-30 | N | S070
23234 | Construction Administration | PERMIT PLANS | 2023-12-01 | 2023-12-07 | N | S020
22110 | Project Initiation | AR | 2024-01-05 | 2024-01-05 | N | S020
22110 | Schematic Design | AR | 2024-04-01 | 2024-05-31 | N | S020
22110 | Detailed Design | AR | 2024-06-01 | 2024-08-15 | N | S020
22110 | Construction Administration | AR | 2024-09-01 | 2025-08-31 | N | S020
22110 | Schematic Design | ID | 2024-04-01 | 2024-05-31 | N | S030
22110 | Detailed Design | ID | 2024-06-01 | 2024-08-15 | N | S030
22110 | Construction Administration | ID | 2024-09-01 | 2025-08-31 | N | S030
22110 | Schematic Design | STRUCTURAL | 2024-04-01 | 2024-05-31 | N | S070
22110 | Detailed Design | STRUCTURAL | 2024-06-01 | 2024-08-15 | N | S070
22110 | Construction Administration | STRUCTURAL | 2024-09-01 | 2025-08-31 | N | S070
22110 | Schematic Design | MECHANICAL | 2024-04-01 | 2024-05-31 | N | S070
22110 | Detailed Design | MECHANICAL | 2024-06-01 | 2024-08-15 | N | S070
22110 | Construction Administration | MECHANICAL | 2024-09-01 | 2025-08-31 | N | S070
22110 | Schematic Design | FIRE AND LIFE SAFETY | 2024-04-01 | 2024-05-31 | N | S070
22110 | Detailed Design | FIRE AND LIFE SAFETY | 2024-06-01 | 2024-08-15 | N | S070
22110 | Schematic Design | CANCELLED: LIGHTING | 2024-01-05 | 2024-01-05 | Y | \N
22110 | Detailed Design | CANCELLED: LIGHTING | 2024-01-05 | 2024-01-05 | Y | \N
22110 | Construction Administration | CANCELLED: LIGHTING | 2024-01-05 | 2024-01-05 | Y | \N
22110 | Project Initiation | ID | 2024-01-05 | 2024-01-05 | N | S030
22110 | Project Initiation | STRUCTURAL | 2024-01-05 | 2024-01-05 | N | S070
22110 | Project Initiation | MECHANICAL | 2024-01-05 | 2024-01-05 | N | S070
22110 | Project Initiation | ELECTRICAL | 2024-01-05 | 2024-01-05 | N | S070
22110 | Schematic Design | ELECTRICAL | 2024-04-01 | 2024-05-31 | N | S070
22110 | Detailed Design | ELECTRICAL | 2024-06-01 | 2024-08-15 | N | S070
22110 | Construction Administration | ELECTRICAL | 2024-09-01 | 2025-08-31 | N | S070
22110 | Project Initiation | PLUMBING & FIRE PROTECTION | 2024-01-05 | 2024-01-05 | N | S070
22110 | Schematic Design | PLUMBING & FIRE PROTECTION | 2024-04-01 | 2024-05-31 | N | S070
22110 | Detailed Design | PLUMBING & FIRE PROTECTION | 2024-06-01 | 2024-08-15 | N | S070
22110 | Construction Administration | PLUMBING & FIRE PROTECTION | 2024-09-01 | 2025-08-31 | N | S070
22110 | Project Initiation | FIRE AND LIFE SAFETY | 2024-01-05 | 2024-01-05 | N | S070
22110 | Project Initiation | CANCELLED: LIGHTING | 2024-01-05 | 2024-01-05 | Y | S070
23199 | Project Initiation | AR | 2024-01-10 | 2024-01-10 | N | S020
23199 | Concept Design | AR | 2024-01-10 | 2024-04-09 | N | S020
23243 | Project Initiation | AR | 2024-01-11 | 2024-01-11 | N | S020
23243 | Concept Design | AR | 2024-02-01 | 2024-04-30 | N | S020
23243 | Schematic Design | AR | 2024-05-01 | 2024-06-30 | N | S020
23243 | Design Development | AR | 2024-07-01 | 2024-10-31 | N | S020
23243 | Contract Documentation | AR | 2024-11-01 | 2024-12-31 | N | S020
23243 | Construction Administration | AR | 2025-01-01 | 2027-12-31 | N | S020
23006 | Project Initiation | AR | 2024-01-11 | 2024-01-11 | N | S020
23006 | Preliminary Design | AR | 2024-01-11 | 2024-06-30 | N | S020
23006 | Detailed Design | AR | 2024-07-01 | 2024-09-30 | N | S020
23006 | Construction Administration | AR | 2024-10-01 | 2025-09-30 | N | S020
1926104 | Project Initiation | \N | 2024-01-04 | 2024-01-04 | N | \N
1926104 | Contract Documentation | \N | 2024-01-04 | 2024-03-31 | N | \N
1926104 | Tender | BIDDING, EVALUATION, AND NEGOTIATION PHASE | 2024-04-01 | 2024-04-30 | N | \N
1826001 | Construction Administration | 1st extension | 2024-01-01 | 2024-12-31 | N | S020
24008 | Interior Design Test-Fit | INITIAL TEST FIT RESULT | 2024-01-17 | 2024-02-02 | N | S030
24008 | Interior Design Test-Fit | FINAL TEST FIT RESULT | 2024-02-06 | 2024-03-31 | N | S030
24009 | Interior Design Test-Fit | INITIAL TEST FIT REPORT | 2024-01-17 | 2024-01-17 | Y | S030
24009 | Interior Design Test-Fit | FINAL TEST FIT REPORT | 2024-01-17 | 2024-01-17 | Y | S030
2212801 | Project Initiation | ID | 2024-01-15 | 2024-01-15 | N | S030
2212801 | Preliminary Design | ID | 2024-01-15 | 2024-01-19 | N | S030
2212801 | Detailed Design | ID | 2024-01-22 | 2024-01-31 | N | S030
2212801 | Construction Administration | ID | 2024-02-01 | 2024-02-29 | N | S030
2212801 | Post Construction Phase | ID | 2024-03-01 | 2024-05-15 | N | S030
24012 | Project Initiation | \N | 2024-02-02 | 2024-02-02 | N | S010
24012 | Conceptual Masterplanning | PRELIMINARY CONCEPTUAL MASTERPLAN | 2024-02-02 | 2024-03-01 | N | S010
24012 | Conceptual Masterplanning | FINAL CONCEPTUAL MASTERPLAN | 2024-03-04 | 2024-04-30 | N | S010
24013 | Design Development | ID: DD / 25% CONSTRUCTION DOCUMENTATION PACKAGE | 2024-01-26 | 2024-02-16 | N | S030
24013 | Contract Documentation | ID | 2024-02-17 | 2024-03-31 | N | S030
24013 | Construction Administration | ID | 2024-04-01 | 2024-09-30 | N | S030
24013 | Design Development | ACOUSTICS: DD / 25% CONSTRUCTION DOCUMENTATION PACKAGE | 2024-01-26 | 2024-02-16 | N | S070
24013 | Contract Documentation | ACOUSTICS | 2024-02-17 | 2024-03-31 | N | S070
24013 | Construction Administration | ACOUSTICS | 2024-04-01 | 2024-09-30 | N | S070
24013 | Design Development | MEPF: DD / 25% CONSTRUCTION DOCUMENTATION PACKAGE | 2024-01-26 | 2024-02-16 | N | S070
24013 | Contract Documentation | MEPF | 2024-02-17 | 2024-03-31 | N | S070
24013 | Construction Administration | MEPF | 2024-04-01 | 2024-09-30 | N | S070
24013 | Design Development | QS: DD / 25% CONSTRUCTION DOCUMENTATION PACKAGE | 2024-01-26 | 2024-02-16 | N | S070
24013 | Contract Documentation | QS | 2024-02-17 | 2024-03-31 | N | S070
24013 | Construction Administration | QS | 2024-04-01 | 2024-09-30 | N | S070
23229 | Project Initiation | ID | 2024-02-07 | 2024-02-07 | N | S030
23229 | Concept Design | ID | 2024-02-07 | 2024-04-30 | N | S030
23229 | Schematic Design | ID | 2024-04-07 | 2024-06-28 | N | S030
23229 | Contract Documentation | ID | 2024-06-07 | 2024-09-30 | N | S030
23229 | Construction Administration | ID | 2024-10-01 | 2024-12-31 | N | S030
2309703 | Project Initiation | AR | 2024-02-07 | 2024-02-07 | N | S020
2309703 | Schematic Design | AR MF: UPON SUBMISSION OF FINAL REPORT | 2024-02-07 | 2024-04-15 | N | S020
2309703 | Project Initiation | TIA | 2024-02-07 | 2024-02-07 | N | S070
2309703 | Schematic Design | TIA:UPON SUBMISSION OF FINAL REPORT | 2024-02-07 | 2024-04-15 | N | S070
23155 | Project Initiation | \N | 2024-01-04 | 2024-01-04 | Y | S010
23155 | Conceptual Masterplanning | PRELIMINARY CONCEPTUAL MP | 2024-01-04 | 2024-03-31 | Y | S010
23155 | Conceptual Masterplanning | FINAL CONCEPTUAL MP | 2024-04-01 | 2024-05-15 | Y | S010
1909904 | Contract Documentation | AR | 2024-02-14 | 2024-03-31 | N | S020
24001 | Project Initiation | AR | 2024-02-14 | 2024-02-14 | N | S020
24001 | Concept Design | AR | 2024-02-14 | 2024-08-13 | N | S020
24001 | Schematic Design | AR | 2024-08-14 | 2024-09-13 | N | S020
24001 | Design Development | AR | 2024-09-14 | 2024-10-13 | N | S020
24001 | Contract Documentation | AR | 2024-10-14 | 2024-12-31 | N | S020
24001 | Construction Administration | AR | 2025-01-01 | 2027-12-31 | N | S020
24001 | Project Initiation | STRUCTURAL | 2024-02-14 | 2024-02-14 | N | S070
24001 | Schematic Design | STRUCTURAL | 2024-08-14 | 2024-09-13 | N | S070
24001 | Design Development | STRUCTURAL | 2024-09-14 | 2024-10-13 | N | S070
24001 | Contract Documentation | STRUCTURAL | 2024-10-14 | 2024-12-31 | N | S070
24001 | Construction Administration | STRUCTURAL | 2025-01-01 | 2027-12-31 | N | S070
24001 | Project Initiation | MEPF | 2024-02-14 | 2024-02-14 | N | S070
24001 | Schematic Design | MEPF | 2024-08-14 | 2024-09-13 | N | S070
24001 | Design Development | MEPF | 2024-09-14 | 2024-10-13 | N | S070
24001 | Contract Documentation | MEPF | 2024-10-14 | 2024-12-31 | N | S070
24001 | Construction Administration | MEPF | 2025-01-01 | 2027-12-31 | N | S070
24001 | Project Initiation | FALAR | 2024-02-14 | 2024-02-14 | N | S070
24001 | Schematic Design | FALAR | 2024-08-14 | 2024-09-13 | N | S070
24001 | Design Development | FALAR | 2024-09-14 | 2024-10-13 | N | S070
24001 | Contract Documentation | FALAR | 2024-10-14 | 2024-12-31 | N | S070
2107402 | Project Initiation | ID | 2024-02-19 | 2024-02-19 | Y | S030
2107402 | Preliminary Design | ID | 2024-02-19 | 2024-05-18 | Y | S030
2107403 | Project Initiation | ID | 2024-02-19 | 2024-02-19 | Y | S030
2107403 | Preliminary Design | ID | 2024-02-19 | 2024-06-18 | Y | S030
2107404 | Project Initiation | ID | 2024-02-19 | 2024-02-19 | Y | S030
2107404 | Preliminary Design | ID | 2024-02-19 | 2024-03-18 | Y | S030
2107405 | Project Initiation | ID | 2024-02-19 | 2024-02-19 | Y | S030
2107405 | Preliminary Design | ID | 2024-02-19 | 2024-04-18 | Y | S030
24021 | Project Initiation | ID | 2024-02-19 | 2024-02-19 | N | S030
24021 | Preliminary Design | ID | 2024-02-19 | 2024-03-31 | N | S030
24021 | Detailed Design | ID | 2024-04-01 | 2024-05-31 | N | S030
24021 | Construction Administration | ID | 2024-06-01 | 2025-01-31 | N | S030
2309702 | Project Initiation | AR: MF | 2024-02-20 | 2024-02-20 | N | S020
2309702 | Schematic Design | AR: MF | 2024-02-20 | 2024-04-19 | N | S020
2309702 | Design Development | AR: MF | 2024-04-20 | 2024-07-19 | N | S020
2309702 | Contract Documentation | AR: MF | 2024-07-20 | 2024-10-31 | N | S020
2309702 | Construction Administration | AR: MF | 2024-11-01 | 2028-10-31 | N | S020
2309702 | Project Initiation | FACADE | 2024-02-20 | 2024-02-20 | N | S070
2309702 | Schematic Design | FACADE | 2024-02-20 | 2024-04-19 | N | S070
2309702 | Design Development | FACADE | 2024-04-20 | 2024-07-19 | N | S070
2309702 | Contract Documentation | FACADE | 2024-07-20 | 2024-10-31 | N | S070
2309702 | Construction Administration | FACADE | 2024-11-01 | 2028-10-31 | N | S070
2309702 | Project Initiation | BMU | 2024-02-20 | 2024-02-20 | N | S070
2309702 | Schematic Design | BMU | 2024-02-20 | 2024-04-19 | N | S070
2309702 | Design Development | BMU | 2024-04-20 | 2024-07-19 | N | S070
2309702 | Contract Documentation | BMU | 2024-07-20 | 2024-10-31 | N | S070
2309702 | Construction Administration | BMU | 2024-11-01 | 2028-10-31 | N | S070
2309704 | Project Initiation | MF | 2024-02-20 | 2024-02-20 | N | S020
2309704 | Pre-Design Services | MF: UPON COMPLETION OF TOPOGRAHIC SURVEY | 2024-02-20 | 2024-03-19 | N | S020
2309704 | Pre-Design Services | MF: UPON COMPLETION AND ACCEPTANCE OF REMAINING SURVEY DATA | 2024-03-20 | 2024-03-31 | N | S020
2309704 | Project Initiation | SITE SURVEYING | 2024-02-20 | 2024-02-20 | N | S070
2309704 | Pre-Design Services | SITE SURVEYING: UPON COMPLETION OF TOPOGRAHIC SURVEY | 2024-02-20 | 2024-03-19 | N | S070
2309704 | Pre-Design Services | SITE SURVEYING : UPON COMPLETION AND ACCEPTANCE OF REMAINING SURVEY DATA | 2024-03-20 | 2024-03-31 | N | S070
1920401 | Contract Documentation | \N | 2024-01-04 | 2024-01-04 | Y | \N
23237 | Project Initiation | ID | 2024-02-23 | 2024-02-23 | N | S030
23237 | Design Development | ID | 2024-02-23 | 2024-04-30 | N | S030
23237 | Contract Documentation | ID | 2024-05-01 | 2024-06-30 | N | S030
24016 | Project Initiation | WGC | 2024-02-16 | 2024-02-16 | N | S040
24016 | Preliminary Design | WGC | 2024-02-16 | 2024-04-05 | N | S040
24016 | Design Development | WGC | 2024-04-06 | 2024-07-05 | N | S040
24016 | Contract Documentation | WGC | 2024-07-06 | 2024-08-21 | N | S040
24016 | Construction Administration | WGC - TBD | 2024-08-22 | 2024-11-20 | N | S040
24016 | Project Initiation | WCC | 2024-02-16 | 2024-02-16 | N | S040
24016 | Preliminary Design | WCC | 2024-02-16 | 2024-05-20 | N | S040
24016 | Design Development | WCC | 2024-05-21 | 2024-07-20 | N | S040
24016 | Contract Documentation | WCC | 2024-07-21 | 2024-09-20 | N | S040
24016 | Construction Administration | WCC | 2024-09-21 | 2024-11-20 | N | S040
1926107 | BIM Attendance | AR | 2023-09-01 | 2024-03-31 | N | S020
1926109 | Project Initiation | \N | 2024-02-01 | 2024-02-01 | N | S050
1926109 | Final Renderings | \N | 2024-02-01 | 2024-03-31 | N | S050
2206002 | Detailed Design | \N | 2024-02-26 | \N | Y | S020
24024 | Project Initiation | AR | 2024-02-01 | 2024-02-01 | N | S020
24024 | Preliminary Design | AR | 2024-02-01 | 2024-03-31 | N | S020
24024 | Detailed Design | AR | 2024-04-01 | 2024-05-31 | N | S020
24024 | Construction Administration | AR | 2024-06-01 | 2025-05-31 | N | S020
2309706 | Project Initiation | MF | 2024-03-01 | 2024-03-01 | N | S020
2309706 | Schematic Design | MF | 2024-03-01 | 2024-04-30 | N | S020
2309706 | Design Development | MF | 2024-05-01 | 2024-07-31 | N | S020
2309706 | Contract Documentation | MF | 2024-08-01 | 2024-10-31 | N | S020
2309706 | Construction Administration | MF | 2024-11-01 | 2028-10-31 | N | S020
2309706 | Project Initiation | SUBCON | 2024-03-01 | 2024-03-01 | N | S070
2309706 | Schematic Design | SUBCON | 2024-03-01 | 2024-04-30 | N | S070
2309706 | Design Development | SUBCON | 2024-05-01 | 2024-07-31 | N | S070
2309706 | Contract Documentation | SUBCON | 2024-08-01 | 2024-10-31 | N | S070
2309706 | Construction Administration | SUBCON | 2024-11-01 | 2028-10-31 | N | S070
2309701 | Project Initiation | AR - MF | 2024-02-26 | 2024-02-26 | N | S020
2309701 | Schematic Design | AR - MF | 2024-02-26 | 2024-04-25 | N | S020
2309701 | Design Development | AR - MF | 2024-04-26 | 2024-07-25 | N | S020
2309701 | Contract Documentation | AR - MF | 2024-07-26 | 2024-10-25 | N | S020
2309701 | Construction Administration | AR - MF | 2024-10-25 | 2028-10-24 | N | S020
2309701 | Project Initiation | LANDSCAPE | 2024-02-26 | 2024-02-26 | N | S070
2309701 | Schematic Design | LANDSCAPE | 2024-02-26 | 2024-04-25 | N | S070
2309701 | Design Development | LANDSCAPE | 2024-04-26 | 2024-07-25 | N | S070
2309701 | Contract Documentation | LANDSCAPE | 2024-07-26 | 2024-10-25 | N | S070
2309701 | Construction Administration | LANDSCAPE | 2024-10-25 | 2028-10-24 | N | S070
1506820 | Construction Administration | AR | 2024-03-01 | 2024-06-30 | N | S020
1506821 | Construction Administration | AR | 2024-03-01 | 2024-10-31 | N | S020
22137 | Project Initiation | ID | 2024-03-01 | 2024-03-01 | N | S030
22137 | Concept Design | ID | 2024-03-01 | 2024-03-01 | N | S030
22137 | Schematic Design | ID | 2024-03-02 | 2024-03-15 | N | S030
22137 | Design Development | ID | 2024-03-16 | 2024-07-15 | N | S030
22137 | Contract Documentation | ID | 2024-08-16 | 2024-11-15 | N | S030
22137 | Construction Administration | ID | 2024-12-01 | 2025-11-30 | N | S030
2309705 | Project Initiation | AR | 2024-03-13 | 2024-03-13 | N | S020
2309705 | Schematic Design | AR | 2024-03-13 | 2024-05-12 | N | S020
2309705 | Design Development | AR | 2024-05-13 | 2024-08-12 | N | S020
2309705 | Contract Documentation | AR | 2024-08-13 | 2024-11-30 | N | S020
2309705 | Construction Administration | AR | 2024-12-01 | 2028-11-30 | N | S020
2309705 | Project Initiation | ACOUSTICS | 2024-03-13 | 2024-03-13 | N | S070
2309705 | Schematic Design | ACOUSTICS | 2024-03-13 | 2024-05-12 | N | S070
2309705 | Design Development | ACOUSTICS | 2024-05-13 | 2024-08-12 | N | S070
2309705 | Contract Documentation | ACOUSTICS | 2024-08-13 | 2024-11-30 | N | S070
2309705 | Construction Administration | ACOUSTICS | 2024-12-01 | 2028-11-30 | N | S070
2309705 | Project Initiation | SECURITY | 2024-03-13 | 2024-03-13 | N | S070
2309705 | Schematic Design | SECURITY | 2024-03-13 | 2024-05-12 | N | S070
2309705 | Design Development | SECURITY | 2024-05-13 | 2024-08-12 | N | S070
2309705 | Contract Documentation | SECURITY | 2024-08-13 | 2024-11-30 | N | S070
2309705 | Construction Administration | SECURITY | 2024-12-01 | 2028-11-30 | N | S070
23216 | Project Initiation | ID | 2024-03-18 | 2024-03-18 | N | S030
23216 | Schematic Design | XXX | 2024-03-18 | 2024-03-18 | Y | \N
23216 | Design Development | ID | 2024-03-18 | 2024-07-17 | N | S030
23216 | Contract Documentation | ID | 2024-07-18 | 2024-12-31 | N | S030
23216 | Construction Administration | ID | 2025-01-01 | 2026-12-31 | N | S030
2309707 | Project Initiation | MF | 2024-03-19 | 2024-03-19 | N | S020
2309707 | Design Development | MF: DETAILED WIND CLIMATE ANALYSIS & 3D WIND TUNNEL MODELS | 2024-03-19 | 2024-04-18 | N | S020
2309707 | Design Development | MF: FACADE PRESSURE WIND TUNNEL STUDY | 2024-04-19 | 2024-05-18 | N | S020
2309707 | Project Initiation | WIND TUNNEL | 2024-03-19 | 2024-03-19 | N | S070
2309707 | Design Development | WIND TUNNEL: DETAILED WIND CLIMATE ANALYSIS & 3D WIND TUNNEL MODELS | 2024-03-19 | 2024-04-18 | N | S070
2309707 | Design Development | WIND TUNNEL: FACADE PRESSURE WIND TUNNEL STUDY | 2024-04-19 | 2024-05-18 | N | S070
1926106 | Design Development | AR | 2023-12-01 | 2024-04-30 | N | S020
2308601 | Project Initiation | MF | 2024-03-25 | 2024-03-25 | N | S030
2308601 | Schematic Design | MF - CONCEPT / SD | 2024-03-25 | 2024-04-30 | N | S030
2308601 | Design Development | MF | 2024-05-01 | 2024-05-21 | N | S030
2308601 | Tender | MF - TENDER DOCUMENTATION AND VALUATION | 2024-05-22 | 2024-05-31 | N | S030
2308601 | Construction Administration | MF | 2024-06-01 | 2025-06-30 | N | S030
2308601 | Project Initiation | LIGHTING | 2024-03-25 | 2024-03-25 | N | S070
2308601 | Schematic Design | LIGHTING - CONCEPT / SD | 2024-03-25 | 2024-04-30 | N | S070
2308601 | Design Development | LIGHTING | 2024-05-01 | 2024-05-21 | N | S070
2308601 | Tender | LIGHTING - TENDER DOCUMENTATION AND VALUATION | 2024-05-22 | 2024-05-31 | N | S070
2308601 | Construction Administration | LIGHTING | 2024-06-01 | 2025-06-30 | N | S070
23236 | Project Initiation | \N | 2024-04-02 | 2024-04-02 | N | S060
23236 | BIM Attendance | \N | 2024-04-02 | 2024-11-30 | N | S060
1711511 | Construction Administration | AR | 2024-03-01 | 2024-08-31 | N | S020
24033 | Project Initiation | AR | 2024-04-03 | 2024-04-03 | N | S020
24033 | Test-Fit | AR | 2024-04-03 | 2024-05-12 | N | S020
24033 | Project Initiation | HOTEL PLANNING CONSULTANCY | 2024-04-03 | 2024-04-03 | N | S070
24033 | Test-Fit | HOTEL PLANNING CONSULTANCY | 2024-04-03 | 2024-05-12 | N | S070
24033 | Project Initiation | MARKET & FINANCIAL STUDIES | 2024-04-03 | 2024-04-03 | N | S070
24033 | Test-Fit | MARKET & FINANCIAL STUDIES | 2024-04-03 | 2024-05-12 | N | S070
2213701 | Final Renderings | PM TO PROVIDE CORRECT DATES: RENDERING VIEWS | 2024-04-05 | 2024-06-04 | N | S050
2309709 | Project Initiation | MF | 2024-04-04 | 2024-04-04 | N | S020
2309709 | Design Development | MF | 2024-04-04 | 2024-07-03 | N | S020
2309709 | Contract Documentation | MF | 2024-07-04 | 2024-10-03 | N | S020
2309709 | Construction Administration | MF: MID CONSTRUCTION REPORT | 2024-10-04 | 2026-10-03 | N | S020
2309709 | Construction Administration | MF: FULL CONSTRUCTION REPORT | 2026-10-04 | 2028-10-03 | N | S020
2309709 | Project Initiation | EDGE | 2024-04-04 | 2024-04-04 | N | S070
2309709 | Design Development | EDGE | 2024-04-04 | 2024-07-03 | N | S070
2309709 | Contract Documentation | EDGE | 2024-07-04 | 2024-10-03 | N | S070
2309709 | Construction Administration | EDGE: MID CONSTRUCTION REPORT | 2024-10-04 | 2026-10-03 | N | S070
2309709 | For Construction Drawings | EDGE: FULL CONSTRUCTION REPORT | 2026-10-04 | 2028-10-03 | N | S070
1817232 | Project Initiation | \N | 2024-04-05 | 2024-04-05 | N | S030
1817232 | Detailed Design | \N | 2024-04-05 | 2024-07-31 | N | S030